## DPR
report_date | supervisor | activity_code | wbs_code | wbs_name | qty_executed | unit | manpower_cost | equipment_cost | manpower_lines | equipment_lines | remarks
2026-01-24 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | saiffuddin | 1.1 | 1.1 | Site Establishment | 8.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-24 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 72.000 | lin.m. | 5600.00 | 0 | 1 | 0
2026-01-24 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 36.000 | sq.m. | 6100.00 | 0 | 2 | 0
2026-01-24 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 17.000 | cu.m. | 4800.00 | 0 | 1 | 0
2026-01-24 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 705.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-01-24 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1100.000 | cu.m. | 500.00 | 16000.00 | 1 | 2
2026-01-24 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 800.000 | cu.m. | 3000.00 | 25000.00 | 2 | 3
2026-01-24 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 250.000 | Sqm | 2000.00 | 11000.00 | 1 | 2
2026-01-24 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 180.000 | lin.m. | 4500.00 | 25500.00 | 2 | 5
2026-01-24 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 25.000 | cu.m. | 1500.00 | 8000.00 | 1 | 2
2026-01-24 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | ismaila | 2.6.6(i) | 2.6 | Pier | 256.000 | cu.m. | 2200.00 | 23500.00 | 2 | 4
2026-01-24 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 270.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-01-24 | ismaila | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 63.000 | kg. | 2700.00 | 0 | 1 | 0
2026-01-24 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 1.000 | sq.m. | 5600.00 | 0 | 1 | 0
2026-01-24 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 1.000 | Nos | 3600.00 | 6000.00 | 1 | 1
2026-01-24 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 350.000 | cu.m. | 2500.00 | 21500.00 | 1 | 5
2026-01-24 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-24 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | saiffuddin | 1.1 | 1.1 | Site Establishment | 5.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-25 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 152.000 | lin.m. | 1500.00 | 0 | 1 | 0
2026-01-25 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 48.000 | lin.m. | 5600.00 | 0 | 1 | 0
2026-01-25 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 3.000 | sq.m. | 4300.00 | 0 | 2 | 0
2026-01-25 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 48.000 | cu.m. | 4800.00 | 0 | 1 | 0
2026-01-25 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 650.000 | cu.m. | 2500.00 | 30000.00 | 2 | 3
2026-01-25 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | Sqm | 2000.00 | 8000.00 | 1 | 2
2026-01-25 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 425.000 | m | 1500.00 | 8000.00 | 1 | 2
2026-01-25 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 200.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-01-25 | ismaila | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 1000.00 | 5000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 500.000 | kg. | 1600.00 | 0 | 1 | 0
2026-01-25 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 1.000 | sq.m. | 5600.00 | 0 | 1 | 0
2026-01-25 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 1.000 | Nos | 3600.00 | 12000.00 | 1 | 1
2026-01-25 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 380.000 | cu.m. | 2000.00 | 20500.00 | 1 | 4
2026-01-25 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-25 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 1.1 | 1.1 | Site Establishment | 1.000 | Km | 500.00 | 5000.00 | 1 | 1
2026-01-26 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | saiffuddin | 1.1 | 1.1 | Site Establishment | 6.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-26 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 4300.00 | 4500.00 | 3 | 2
2026-01-26 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1250.000 | cu.m. | 1000.00 | 29000.00 | 1 | 3
2026-01-26 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 700.000 | cu.m. | 3000.00 | 26000.00 | 2 | 2
2026-01-26 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 180.000 | Sqm | 2000.00 | 8000.00 | 1 | 2
2026-01-26 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 250.000 | sq.m. | 0 | 9000.00 | 0 | 2
2026-01-26 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 2.6.6(i) | 2.6 | Pier | 270.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-01-26 | parvaiz | 2.6.6(i) | 2.6 | Pier | 120.000 | m | 3500.00 | 19000.00 | 2 | 4
2026-01-26 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 60.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-01-26 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 570.000 | cu.m. | 2200.00 | 29000.00 | 2 | 4
2026-01-26 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 200.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-01-26 | illayaraja | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 2400.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 160.000 | sq.m. | 2500.00 | 0 | 1 | 0
2026-01-26 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 70.000 | cu.m. | 4000.00 | 12000.00 | 1 | 4
2026-01-26 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-26 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | ismaila | 1.1 | 1.1 | Site Establishment | 525.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-01-27 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | saiffuddin | 1.1 | 1.1 | Site Establishment | 10.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-27 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.1.5 (i) | 2.1 | Setting Out & Layout | 200.000 | lin.m. | 500.00 | 5000.00 | 1 | 1
2026-01-27 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 370.000 | cu.m. | 0 | 10000.00 | 0 | 1
2026-01-27 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 100.000 | lin.m. | 500.00 | 7500.00 | 1 | 2
2026-01-27 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 650.000 | cu.m. | 500.00 | 16000.00 | 1 | 2
2026-01-27 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 3000.00 | 29000.00 | 2 | 3
2026-01-27 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-01-27 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 300.000 | cu.m. | 1500.00 | 13000.00 | 1 | 3
2026-01-27 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 300.000 | sq.m. | 0 | 9000.00 | 0 | 2
2026-01-27 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 1500.00 | 3000.00 | 1 | 1
2026-01-27 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | parvaiz | 2.6.6(i) | 2.6 | Pier | 100.000 | m | 3500.00 | 17000.00 | 2 | 4
2026-01-27 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 150.000 | lin.m. | 2500.00 | 16000.00 | 1 | 4
2026-01-27 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 200.000 | cu.m. | 0 | 16000.00 | 0 | 2
2026-01-27 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 352.000 | cu.m. | 2200.00 | 27000.00 | 2 | 3
2026-01-27 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 325.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-01-27 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 2400.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 200.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-01-27 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 400.000 | sq.m. | 5500.00 | 15000.00 | 2 | 4
2026-01-27 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-27 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | saiffuddin | 1.1 | 1.1 | Site Establishment | 5.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-28 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.1.5 (i) | 2.1 | Setting Out & Layout | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 2000.00 | 5500.00 | 1 | 2
2026-01-28 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1150.000 | cu.m. | 1700.00 | 19000.00 | 2 | 3
2026-01-28 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 2000.00 | 25000.00 | 2 | 3
2026-01-28 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 350.000 | cu.m. | 1000.00 | 9000.00 | 1 | 2
2026-01-28 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-01-28 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 60.000 | lin.m. | 2000.00 | 4000.00 | 1 | 1
2026-01-28 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 425.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-01-28 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 2000.00 | 6000.00 | 1 | 1
2026-01-28 | ismaila | 2.6.6(i) | 2.6 | Pier | 403.000 | cu.m. | 500.00 | 13500.00 | 1 | 3
2026-01-28 | kbarman | 2.6.6(i) | 2.6 | Pier | 310.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-01-28 | parvaiz | 2.6.6(i) | 2.6 | Pier | 160.000 | m | 1500.00 | 13000.00 | 1 | 3
2026-01-28 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | ismaila | 2.7.6 (i) | 2.7 | Abutment | 95.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-01-28 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 250.000 | cu.m. | 2500.00 | 17500.00 | 1 | 4
2026-01-28 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 150.000 | cu.m. | 0 | 10000.00 | 0 | 1
2026-01-28 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 1.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-01-28 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 3200.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 100.000 | cu.m. | 1300.00 | 15000.00 | 2 | 4
2026-01-28 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-28 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | saiffuddin | 1.1 | 1.1 | Site Establishment | 6.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-29 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.1.5 (i) | 2.1 | Setting Out & Layout | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 2000.00 | 5500.00 | 1 | 2
2026-01-29 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 1700.00 | 10000.00 | 2 | 1
2026-01-29 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 450.000 | cu.m. | 2000.00 | 25000.00 | 2 | 3
2026-01-29 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 500.00 | 11000.00 | 1 | 2
2026-01-29 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 310.000 | cu.m. | 1000.00 | 9000.00 | 1 | 2
2026-01-29 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-01-29 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 3200.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 496.000 | cu.m. | 0 | 8000.00 | 0 | 1
2026-01-29 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 70.000 | lin.m. | 3500.00 | 21000.00 | 2 | 4
2026-01-29 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 550.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-01-29 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 2000.00 | 6000.00 | 1 | 1
2026-01-29 | ismaila | 2.6.6(i) | 2.6 | Pier | 32.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-01-29 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 320.000 | cu.m. | 1500.00 | 13500.00 | 1 | 2
2026-01-29 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 200.000 | cu.m. | 0 | 10000.00 | 0 | 1
2026-01-29 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 500.00 | 3000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 300.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-01-29 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 47.000 | cu.m. | 0 | 2500.00 | 0 | 1
2026-01-29 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 160.000 | cu.m. | 500.00 | 9000.00 | 1 | 2
2026-01-29 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 12.000 | cu.m. | 4000.00 | 10000.00 | 1 | 3
2026-01-29 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-29 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 1 | 1.0 | Preliminaries | 500.000 | lin.m. | 500.00 | 5500.00 | 1 | 1
2026-01-30 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | saiffuddin | 1.1 | 1.1 | Site Establishment | 6.000 | m | 500.00 | 13000.00 | 1 | 2
2026-01-30 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.1.5 (i) | 2.1 | Setting Out & Layout | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 130.000 | cu.m. | 0 | 0 | 0 | 0
2026-01-30 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 160.000 | cu.m. | 1700.00 | 10000.00 | 2 | 1
2026-01-30 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 150.000 | cu.m. | 2000.00 | 5000.00 | 2 | 1
2026-01-30 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 5200.00 | 2000.00 | 2 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 280.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-01-30 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 170.000 | cu.m. | 1500.00 | 13500.00 | 1 | 2
2026-01-30 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 160.000 | cu.m. | 0 | 13500.00 | 0 | 3
2026-01-30 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-30 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | saiffuddin | 1.1 | 1.1 | Site Establishment | 7.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-01-31 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 100.000 | lin.m. | 3000.00 | 3000.00 | 1 | 1
2026-01-31 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 150.000 | cu.m. | 0 | 10000.00 | 0 | 1
2026-01-31 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 50.000 | lin.m. | 500.00 | 7500.00 | 1 | 2
2026-01-31 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 350.000 | cu.m. | 2000.00 | 19000.00 | 2 | 3
2026-01-31 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 560.000 | cu.m. | 500.00 | 14000.00 | 1 | 3
2026-01-31 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 1000.00 | 9000.00 | 1 | 2 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-01-31 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 5500.00 | 0 | 3 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | cu.m. | 1500.00 | 13500.00 | 1 | 2
2026-01-31 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 360.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-01-31 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 1500.00 | 3000.00 | 1 | 1
2026-01-31 | ismaila | 2.6.6(i) | 2.6 | Pier | 336.000 | cu.m. | 0 | 7000.00 | 0 | 2
2026-01-31 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 150.000 | cu.m. | 0 | 15000.00 | 0 | 1
2026-01-31 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 16.000 | cu.m. | 4000.00 | 10000.00 | 1 | 3
2026-01-31 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 100.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-01-31 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 216.000 | cu.m. | 1700.00 | 9500.00 | 2 | 3
2026-01-31 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 290.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-01-31 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 300.000 | sq.m. | 2000.00 | 13500.00 | 1 | 3
2026-01-31 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-01-31 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | saiffuddin | 1.1 | 1.1 | Site Establishment | 6.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-02-01 | vijaykumar | 1.1 | 1.1 | Site Establishment | 350.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-01 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 150.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-02-01 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 2000.00 | 19000.00 | 2 | 3
2026-02-01 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1450.000 | cu.m. | 3200.00 | 79000.00 | 2 | 3
2026-02-01 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 0 | 24000.00 | 0 | 3
2026-02-01 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 450.000 | cu.m. | 0 | 9000.00 | 0 | 2
2026-02-01 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-01 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 250.000 | cu.m. | 5500.00 | 13000.00 | 3 | 2
2026-02-01 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | cu.m. | 1000.00 | 16000.00 | 1 | 3
2026-02-01 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 325.000 | cu.m. | 500.00 | 18000.00 | 1 | 3
2026-02-01 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.6.6(i) | 2.6 | Pier | 100.000 | Sqm | 1000.00 | 3000.00 | 1 | 1
2026-02-01 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 450.000 | cu.m. | 0 | 15000.00 | 0 | 1
2026-02-01 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 20.000 | lin.m. | 0 | 0 | 0 | 0
2026-02-01 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 200.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-02-01 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 368.000 | cu.m. | 2200.00 | 27000.00 | 2 | 3
2026-02-01 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 540.000 | cu.m. | 500.00 | 11000.00 | 1 | 3
2026-02-01 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 800.000 | Sqm | 0 | 33000.00 | 0 | 5
2026-02-01 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 300.000 | sq.m. | 1000.00 | 26000.00 | 1 | 5
2026-02-01 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-01 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | saiffuddin | 1.1 | 1.1 | Site Establishment | 6.000 | m | 1500.00 | 10000.00 | 1 | 1
2026-02-02 | vijaykumar | 1.1 | 1.1 | Site Establishment | 600.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-02 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 375.000 | cu.m. | 1700.00 | 39000.00 | 2 | 3
2026-02-02 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 240.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-02-02 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 2000.00 | 19000.00 | 2 | 3
2026-02-02 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 950.000 | cu.m. | 3200.00 | 86000.00 | 2 | 3
2026-02-02 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 420.000 | cu.m. | 1000.00 | 5000.00 | 1 | 1
2026-02-02 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-02 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 6000.00 | 5000.00 | 4 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 130.000 | cu.m. | 1000.00 | 8500.00 | 1 | 2
2026-02-02 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 600.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-02 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 1500.00 | 3000.00 | 1 | 1
2026-02-02 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 105.000 | cu.m. | 1000.00 | 8500.00 | 1 | 2
2026-02-02 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 410.000 | cu.m. | 0 | 15000.00 | 0 | 1
2026-02-02 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 20.000 | lin.m. | 0 | 0 | 0 | 0
2026-02-02 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 300.000 | lin.m. | 2000.00 | 6000.00 | 1 | 1
2026-02-02 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 300.000 | cu.m. | 500.00 | 13500.00 | 1 | 3
2026-02-02 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 140.000 | lin.m. | 3500.00 | 17000.00 | 2 | 4
2026-02-02 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 800.000 | Sqm | 0 | 23000.00 | 0 | 3
2026-02-02 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 300.000 | cu.m. | 7300.00 | 35000.00 | 2 | 5
2026-02-02 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-02 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | saiffuddin | 1.1 | 1.1 | Site Establishment | 10.000 | m | 500.00 | 10000.00 | 1 | 1
2026-02-03 | vijaykumar | 1.1 | 1.1 | Site Establishment | 480.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-03 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 80.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-02-03 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 245.000 | sq.m. | 2500.00 | 5000.00 | 1 | 1
2026-02-03 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 630.000 | cu.m. | 1700.00 | 16000.00 | 2 | 2
2026-02-03 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | lin.m. | 500.00 | 7500.00 | 1 | 2
2026-02-03 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 5200.00 | 75000.00 | 3 | 3
2026-02-03 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 1500.00 | 33000.00 | 1 | 3
2026-02-03 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-03 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 200.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-02-03 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 150.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-03 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 50.000 | lin.m. | 0 | 2000.00 | 0 | 1
2026-02-03 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 600.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-02-03 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 2.6.6(i) | 2.6 | Pier | 100.000 | Sqm | 3000.00 | 6000.00 | 1 | 1
2026-02-03 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | parvaiz | 2.6.6(i) | 2.6 | Pier | 70.000 | m | 3000.00 | 9000.00 | 2 | 2
2026-02-03 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 170.000 | cu.m. | 1500.00 | 11500.00 | 1 | 3
2026-02-03 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 340.000 | cu.m. | 0 | 15000.00 | 0 | 1
2026-02-03 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 20.000 | lin.m. | 0 | 0 | 0 | 0
2026-02-03 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 365.000 | cu.m. | 500.00 | 9500.00 | 1 | 3
2026-02-03 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 750.000 | Sqm | 0 | 31000.00 | 0 | 3
2026-02-03 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 250.000 | cu.m. | 500.00 | 10000.00 | 1 | 1
2026-02-03 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 215.000 | cu.m. | 0 | 14000.00 | 0 | 2
2026-02-03 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 90.000 | cu.m. | 4800.00 | 17500.00 | 1 | 5
2026-02-03 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-03 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | saiffuddin | 1.1 | 1.1 | Site Establishment | 11.000 | m | 500.00 | 10000.00 | 1 | 1
2026-02-04 | vijaykumar | 1.1 | 1.1 | Site Establishment | 250.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-04 | kbarman | 13.1.7(ix)a | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 60.000 | cu.m. | 1000.00 | 8000.00 | 1 | 2
2026-02-04 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 0 | 13000.00 | 0 | 2
2026-02-04 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 60.000 | cu.m. | 1000.00 | 8000.00 | 1 | 2
2026-02-04 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 180.000 | cu.m. | 500.00 | 7500.00 | 1 | 2
2026-02-04 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 600.000 | cu.m. | 5200.00 | 66000.00 | 3 | 3
2026-02-04 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 900.000 | cu.m. | 3500.00 | 39000.00 | 2 | 3
2026-02-04 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 500.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-04 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 250.000 | cu.m. | 3200.00 | 15500.00 | 1 | 3
2026-02-04 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 180.000 | cu.m. | 500.00 | 14000.00 | 1 | 2
2026-02-04 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 130.000 | cu.m. | 1000.00 | 9000.00 | 1 | 2
2026-02-04 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 50.000 | lin.m. | 0 | 6000.00 | 0 | 2
2026-02-04 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 530.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-04 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.6.6(i) | 2.6 | Pier | 50.000 | Sqm | 2500.00 | 3000.00 | 1 | 1
2026-02-04 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 100.000 | cu.m. | 1500.00 | 8500.00 | 1 | 2
2026-02-04 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 240.000 | cu.m. | 0 | 15000.00 | 0 | 1
2026-02-04 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 250.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-02-04 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 105.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-02-04 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 730.000 | lin.m. | 3500.00 | 9000.00 | 2 | 2
2026-02-04 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 250.000 | Sqm | 0 | 32000.00 | 0 | 4
2026-02-04 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 100.000 | cu.m. | 1700.00 | 5000.00 | 2 | 1
2026-02-04 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 80.000 | cu.m. | 4800.00 | 13000.00 | 1 | 3
2026-02-04 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-04 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | saiffuddin | 1.1 | 1.1 | Site Establishment | 4.000 | m | 500.00 | 10000.00 | 1 | 1
2026-02-05 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 50.000 | lin.m. | 500.00 | 8000.00 | 1 | 2
2026-02-05 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 60.000 | cu.m. | 500.00 | 3000.00 | 1 | 1
2026-02-05 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2400.000 | cu.m. | 1700.00 | 25000.00 | 2 | 3
2026-02-05 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-02-05 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 120.000 | cu.m. | 5700.00 | 3000.00 | 2 | 1
2026-02-05 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 450.000 | cu.m. | 500.00 | 15500.00 | 1 | 3
2026-02-05 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 250.000 | cu.m. | 500.00 | 10000.00 | 1 | 1
2026-02-05 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 550.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-02-05 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.6.6(i) | 2.6 | Pier | 70.000 | Sqm | 2500.00 | 3000.00 | 1 | 1
2026-02-05 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 2.6.6(i) | 2.6 | Pier | 110.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-05 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 260.000 | cu.m. | 0 | 15000.00 | 0 | 1
2026-02-05 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 250.000 | lin.m. | 1500.00 | 10000.00 | 1 | 1
2026-02-05 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 200.000 | lin.m. | 1500.00 | 14000.00 | 1 | 3
2026-02-05 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 162.000 | cu.m. | 2800.00 | 0 | 3 | 0
2026-02-05 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 80.000 | cu.m. | 5300.00 | 13000.00 | 2 | 3
2026-02-05 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-05 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 1.1 | 1.1 | Site Establishment | 300.000 | cu.m. | 0 | 6000.00 | 0 | 1
2026-02-06 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | saiffuddin | 1.1 | 1.1 | Site Establishment | 280.000 | m | 2000.00 | 11000.00 | 1 | 2
2026-02-06 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2600.000 | cu.m. | 2700.00 | 25000.00 | 2 | 1
2026-02-06 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 2000.00 | 40000.00 | 2 | 3 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 150.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-02-06 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-06 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | ismaila | 1.1 | 1.1 | Site Establishment | 1200.000 | Sqm | 0 | 0 | 0 | 0
2026-02-07 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | saiffuddin | 1.1 | 1.1 | Site Establishment | 10.000 | m | 2000.00 | 5000.00 | 1 | 1
2026-02-07 | vijaykumar | 1.1 | 1.1 | Site Establishment | 350.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-07 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 70.000 | cu.m. | 500.00 | 3000.00 | 1 | 1
2026-02-07 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 2200.00 | 21000.00 | 2 | 2
2026-02-07 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 90.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-02-07 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1350.000 | cu.m. | 7400.00 | 87000.00 | 3 | 2
2026-02-07 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2000.000 | cu.m. | 0 | 12000.00 | 0 | 1
2026-02-07 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 2000.00 | 40000.00 | 2 | 3 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1100.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-07 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 10.000 | cu.m. | 5200.00 | 0 | 2 | 0
2026-02-07 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 305.000 | cu.m. | 0 | 6500.00 | 0 | 2
2026-02-07 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 250.000 | cu.m. | 1000.00 | 10000.00 | 1 | 1
2026-02-07 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 150.000 | cu.m. | 3000.00 | 15000.00 | 2 | 4
2026-02-07 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 2000.00 | 0 | 1 | 0
2026-02-07 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | parvaiz | 2.6.6(i) | 2.6 | Pier | 150.000 | m | 0 | 9000.00 | 0 | 2
2026-02-07 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 450.000 | Sqm | 0 | 41000.00 | 0 | 5
2026-02-07 | ismaila | 2.6.6(i)a | 2.6 | Pier | 400.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-02-07 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 220.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-02-07 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 100.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-02-07 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 150.000 | lin.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-07 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 675.000 | cu.m. | 0 | 9000.00 | 0 | 2
2026-02-07 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 175.000 | cu.m. | 5800.00 | 23000.00 | 2 | 4
2026-02-07 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-07 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 1 | 1.0 | Preliminaries | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | ismaila | 1.1 | 1.1 | Site Establishment | 2250.000 | Sqm | 1700.00 | 18000.00 | 2 | 2
2026-02-08 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 1500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | vijaykumar | 1.1 | 1.1 | Site Establishment | 340.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-08 | manzar | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | manzar | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | manzar | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 80.000 | cu.m. | 1500.00 | 5000.00 | 1 | 1
2026-02-08 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1300.000 | cu.m. | 6900.00 | 104000.00 | 3 | 3
2026-02-08 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-02-08 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 2000.00 | 35000.00 | 2 | 3
2026-02-08 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 250.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-08 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 170.000 | cu.m. | 3700.00 | 5500.00 | 2 | 2
2026-02-08 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 315.000 | cu.m. | 0 | 9500.00 | 0 | 3
2026-02-08 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 200.000 | cu.m. | 2000.00 | 14000.00 | 1 | 3
2026-02-08 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 313.000 | cu.m. | 1500.00 | 15300.00 | 1 | 4
2026-02-08 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.6.6(i) | 2.6 | Pier | 12.000 | Sqm | 4100.00 | 0 | 3 | 0
2026-02-08 | ismaila | 2.6.6(i) | 2.6 | Pier | 195.000 | cu.m. | 500.00 | 12000.00 | 1 | 3
2026-02-08 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | parvaiz | 2.6.6(i) | 2.6 | Pier | 300.000 | cu.m. | 3500.00 | 13000.00 | 2 | 3
2026-02-08 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 1200.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-08 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-08 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 12.000 | lin.m. | 500.00 | 8000.00 | 1 | 2
2026-02-08 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 80.000 | lin.m. | 1000.00 | 9000.00 | 1 | 2
2026-02-08 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | vijaykumar | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 750.000 | Sqm | 0 | 24000.00 | 0 | 3
2026-02-08 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 200.000 | Sqm | 0 | 5000.00 | 0 | 1
2026-02-08 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 90.000 | cu.m. | 1000.00 | 8000.00 | 1 | 2
2026-02-08 | manzar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | manzar | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | manzar | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | manzar | 9.1.6 (iii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 16.000 | cu.m. | 5300.00 | 7000.00 | 2 | 3
2026-02-08 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | manzar | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-08 | sohail | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 1500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | vijaykumar | 1.1 | 1.1 | Site Establishment | 250.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-09 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 70.000 | sq.m. | 8800.00 | 6000.00 | 1 | 1
2026-02-09 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 702.000 | kg. | 4500.00 | 0 | 1 | 0
2026-02-09 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 450.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-09 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 150.000 | cu.m. | 1500.00 | 7500.00 | 1 | 2
2026-02-09 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 1700.00 | 15000.00 | 2 | 1
2026-02-09 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1250.000 | cu.m. | 5200.00 | 78000.00 | 3 | 2
2026-02-09 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1700.000 | cu.m. | 500.00 | 30500.00 | 1 | 5
2026-02-09 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 750.000 | cu.m. | 2000.00 | 40000.00 | 2 | 3
2026-02-09 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-09 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 120.000 | cu.m. | 3000.00 | 21000.00 | 2 | 5
2026-02-09 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 240.000 | cu.m. | 1500.00 | 17300.00 | 1 | 3
2026-02-09 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.6.6(i) | 2.6 | Pier | 200.000 | Sqm | 8800.00 | 3000.00 | 5 | 1
2026-02-09 | ismaila | 2.6.6(i) | 2.6 | Pier | 550.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-09 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 1450.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-09 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 250.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-02-09 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | vijaykumar | 2.7.6 (i) | 2.7 | Abutment | 300.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-09 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 300.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-09 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 130.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-09 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 360.000 | cu.m. | 3000.00 | 15000.00 | 2 | 4
2026-02-09 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | vijaykumar | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 800.000 | Sqm | 0 | 21000.00 | 0 | 2
2026-02-09 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 10.000 | cu.m. | 2500.00 | 0 | 1 | 0
2026-02-09 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-09 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 70.000 | cu.m. | 5300.00 | 15000.00 | 2 | 4
2026-02-09 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | ismaila | 1.1 | 1.1 | Site Establishment | 350.000 | cu.m. | 500.00 | 13000.00 | 1 | 2
2026-02-10 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 1500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | vijaykumar | 1.1 | 1.1 | Site Establishment | 650.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-10 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 40.000 | sq.m. | 8000.00 | 0 | 1 | 0
2026-02-10 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 380.000 | kg. | 2700.00 | 0 | 1 | 0
2026-02-10 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 1.000 | Nos | 1000.00 | 3000.00 | 1 | 1
2026-02-10 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1720.000 | cu.m. | 2000.00 | 103000.00 | 2 | 4
2026-02-10 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2300.000 | cu.m. | 1700.00 | 22000.00 | 2 | 2
2026-02-10 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 950.000 | cu.m. | 2000.00 | 40000.00 | 2 | 3
2026-02-10 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-10 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 10.000 | cu.m. | 2500.00 | 0 | 1 | 0
2026-02-10 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 560.000 | cu.m. | 500.00 | 18500.00 | 1 | 4
2026-02-10 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 160.000 | cu.m. | 3000.00 | 18000.00 | 1 | 2
2026-02-10 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 343.000 | cu.m. | 1500.00 | 25300.00 | 1 | 4
2026-02-10 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.6.6(i) | 2.6 | Pier | 12.000 | Sqm | 2600.00 | 0 | 2 | 0
2026-02-10 | ismaila | 2.6.6(i) | 2.6 | Pier | 400.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-02-10 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | parvaiz | 2.6.6(i) | 2.6 | Pier | 12.000 | Sqm | 4100.00 | 0 | 3 | 0
2026-02-10 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 1200.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-10 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | vijaykumar | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 20.000 | cu.m. | 1000.00 | 5500.00 | 1 | 2
2026-02-10 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | vijaykumar | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 800.000 | Sqm | 0 | 11000.00 | 0 | 2
2026-02-10 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 37.000 | cu.m. | 2400.00 | 0 | 1 | 0
2026-02-10 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 3200.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 3.000 | Nos | 1000.00 | 10000.00 | 1 | 1
2026-02-10 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-10 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 300.000 | cu.m. | 7800.00 | 28500.00 | 2 | 5
2026-02-10 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 1500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | vijaykumar | 1.1 | 1.1 | Site Establishment | 300.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-11 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | Nos | 1500.00 | 3000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 1500.00 | 5500.00 | 1 | 2
2026-02-11 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 630.000 | cu.m. | 0 | 10000.00 | 0 | 1
2026-02-11 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1250.000 | cu.m. | 1000.00 | 92000.00 | 1 | 3
2026-02-11 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 1700.00 | 14000.00 | 2 | 3
2026-02-11 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 720.000 | cu.m. | 2000.00 | 40000.00 | 2 | 3
2026-02-11 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-11 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 405.000 | cu.m. | 500.00 | 18500.00 | 1 | 4
2026-02-11 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 120.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-11 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 620.000 | cu.m. | 1500.00 | 25300.00 | 1 | 4
2026-02-11 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 7300.00 | 0 | 4 | 0
2026-02-11 | kbarman | 2.6.6(i) | 2.6 | Pier | 120.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-11 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 2.6.6(i)a | 2.6 | Pier | 430.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-02-11 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | vijaykumar | 3.2.6 (ii)a | 3.2 | Concrete RCC | 1500.000 | Sqm | 4700.00 | 30000.00 | 3 | 2
2026-02-11 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 62.000 | cu.m. | 1600.00 | 0 | 1 | 0
2026-02-11 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 100.000 | sq.m. | 1000.00 | 2500.00 | 1 | 1
2026-02-11 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-11 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 45.000 | sq.m. | 8800.00 | 0 | 1 | 0
2026-02-11 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 654.000 | kg. | 5400.00 | 0 | 1 | 0
2026-02-11 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | sq.m. | 6300.00 | 20000.00 | 2 | 4
2026-02-11 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 1500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | vijaykumar | 1.1 | 1.1 | Site Establishment | 300.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-12 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 4.500 | cu.m. | 1000.00 | 2000.00 | 1 | 1
2026-02-12 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 1500.00 | 5500.00 | 1 | 2
2026-02-12 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 990.000 | cu.m. | 500.00 | 23000.00 | 1 | 2
2026-02-12 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1250.000 | cu.m. | 5700.00 | 79000.00 | 3 | 2
2026-02-12 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1300.000 | cu.m. | 1700.00 | 17000.00 | 2 | 2
2026-02-12 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 820.000 | cu.m. | 2000.00 | 35000.00 | 2 | 3
2026-02-12 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-12 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 270.000 | sq.m. | 0 | 0 | 0 | 0
2026-02-12 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 600.000 | cu.m. | 1000.00 | 13000.00 | 1 | 2
2026-02-12 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 2.6.6(i) | 2.6 | Pier | 85.000 | Sqm | 1500.00 | 3000.00 | 1 | 1
2026-02-12 | ismaila | 2.6.6(i) | 2.6 | Pier | 415.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-12 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 1300.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-12 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 270.000 | cu.m. | 0 | 13500.00 | 0 | 3
2026-02-12 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 210.000 | cu.m. | 1500.00 | 9000.00 | 1 | 2
2026-02-12 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | vijaykumar | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 600.000 | Sqm | 0 | 16000.00 | 0 | 1
2026-02-12 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 6.000 | cu.m. | 3200.00 | 0 | 1 | 0
2026-02-12 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 6.000 | cu.m. | 1500.00 | 2000.00 | 1 | 1
2026-02-12 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 90.000 | sq.m. | 12000.00 | 12000.00 | 1 | 1
2026-02-12 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-12 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 12.000 | cu.m. | 4100.00 | 0 | 3 | 0
2026-02-12 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | cu.m. | 5300.00 | 15000.00 | 2 | 4
2026-02-12 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 170.000 | cu.m. | 3000.00 | 3000.00 | 1 | 1
2026-02-13 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 190.000 | cu.m. | 0 | 13000.00 | 0 | 2
2026-02-13 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 70.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-02-13 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 680.000 | cu.m. | 1700.00 | 17000.00 | 2 | 2
2026-02-13 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 550.000 | cu.m. | 1500.00 | 35000.00 | 1 | 3
2026-02-13 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 256.000 | cu.m. | 1000.00 | 13000.00 | 1 | 2
2026-02-13 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | akmishra | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 1500.00 | 5000.00 | 1 | 2
2026-02-13 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 2.6.6(i)a | 2.6 | Pier | 210.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-13 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 270.000 | cu.m. | 500.00 | 18000.00 | 1 | 3
2026-02-13 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | vijaykumar | 3.3.6 (ii) | 3.3 | Pre-stressed Members | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 120.000 | sq.m. | 1500.00 | 5000.00 | 1 | 1
2026-02-13 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 22.000 | Sqm | 2300.00 | 0 | 2 | 0
2026-02-13 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 50.000 | kg. | 2700.00 | 0 | 1 | 0
2026-02-13 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-13 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | saiffuddin | 1.1 | 1.1 | Site Establishment | 30.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-02-14 | vijaykumar | 1.1 | 1.1 | Site Establishment | 400.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-14 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 230.000 | lin.m. | 4000.00 | 8000.00 | 1 | 2
2026-02-14 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 18.3.6(ii) | 18.3 | Bituminous Layers | 0.010 | cu.m. | 1500.00 | 3000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 680.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-14 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 1500.00 | 5500.00 | 1 | 2
2026-02-14 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1600.000 | cu.m. | 500.00 | 18000.00 | 1 | 2
2026-02-14 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 50.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-02-14 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1250.000 | cu.m. | 6400.00 | 93000.00 | 3 | 2
2026-02-14 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1650.000 | cu.m. | 0 | 17000.00 | 0 | 2
2026-02-14 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 2500.00 | 30000.00 | 2 | 3
2026-02-14 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | akmishra | 2.4.6(i) | 2.4 | Pile Cap | 150.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-14 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 260.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-14 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | vijaykumar | 2.4.6(i) | 2.4 | Pile Cap | 600.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-14 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 1000.00 | 3000.00 | 1 | 1
2026-02-14 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 2.6.6(i) | 2.6 | Pier | 668.000 | Sqm | 3500.00 | 6500.00 | 2 | 2
2026-02-14 | ismaila | 2.6.6(i)a | 2.6 | Pier | 400.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-02-14 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 375.000 | cu.m. | 1700.00 | 13500.00 | 2 | 3
2026-02-14 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 700.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-14 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 400.000 | lin.m. | 3700.00 | 3000.00 | 2 | 1
2026-02-14 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 282.000 | sq.m. | 4500.00 | 0 | 1 | 0
2026-02-14 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 480.000 | cu.m. | 0 | 21000.00 | 0 | 3
2026-02-14 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 120.000 | sq.m. | 9600.00 | 0 | 1 | 0
2026-02-14 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 12.000 | Sqm | 4100.00 | 0 | 3 | 0
2026-02-14 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 410.000 | kg. | 4500.00 | 0 | 1 | 0
2026-02-14 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-14 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | sq.m. | 500.00 | 10000.00 | 1 | 1
2026-02-14 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | ismaila | 1.1 | 1.1 | Site Establishment | 1250.000 | cu.m. | 0 | 16000.00 | 0 | 2
2026-02-15 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | saiffuddin | 1.1 | 1.1 | Site Establishment | 63.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-02-15 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 18.3.6(ii) | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 80.000 | cu.m. | 1500.00 | 5000.00 | 1 | 1
2026-02-15 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 768.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-02-15 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 45.000 | lin.m. | 500.00 | 5000.00 | 1 | 1
2026-02-15 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 920.000 | cu.m. | 2500.00 | 25000.00 | 2 | 3
2026-02-15 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 150.000 | Sqm | 0 | 5000.00 | 0 | 1
2026-02-15 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | akmishra | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 480.000 | cu.m. | 500.00 | 9000.00 | 1 | 2
2026-02-15 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | cu.m. | 1000.00 | 0 | 1 | 0
2026-02-15 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | vijaykumar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | ismaila | 2.6.6(i) | 2.6 | Pier | 346.000 | cu.m. | 1700.00 | 16500.00 | 2 | 3
2026-02-15 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | ismaila | 2.6.6(i)a | 2.6 | Pier | 500.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-02-15 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | vijaykumar | 3.3.6 (ii)a | 3.3 | Pre-stressed Members | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 75.000 | cu.m. | 1600.00 | 0 | 1 | 0
2026-02-15 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 10.000 | cu.m. | 5700.00 | 0 | 2 | 0
2026-02-15 | ismaila | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 732.000 | cu.m. | 3500.00 | 15000.00 | 2 | 4
2026-02-15 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 40.000 | sq.m. | 6400.00 | 0 | 1 | 0
2026-02-15 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 12.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-15 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 436.000 | kg. | 5400.00 | 0 | 1 | 0
2026-02-15 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-15 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 250.000 | sq.m. | 5300.00 | 24000.00 | 2 | 3
2026-02-15 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | saiffuddin | 1.1 | 1.1 | Site Establishment | 63.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-02-16 | vijaykumar | 1.1 | 1.1 | Site Establishment | 650.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-02-16 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | Nos | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 18.3.6(ii) | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 525.000 | cu.m. | 500.00 | 14000.00 | 1 | 2
2026-02-16 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 2000.00 | 5500.00 | 1 | 2
2026-02-16 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 20.000 | lin.m. | 500.00 | 5000.00 | 1 | 1
2026-02-16 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1300.000 | cu.m. | 5700.00 | 79000.00 | 3 | 3
2026-02-16 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1150.000 | cu.m. | 0 | 17000.00 | 0 | 2
2026-02-16 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 3000.00 | 43000.00 | 2 | 3
2026-02-16 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | Sqm | 1000.00 | 10000.00 | 1 | 1
2026-02-16 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 330.000 | sq.m. | 0 | 0 | 0 | 0
2026-02-16 | akmishra | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 4500.00 | 24000.00 | 2 | 4 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.6.6(i) | 2.6 | Pier | 120.000 | Sqm | 1500.00 | 3000.00 | 1 | 1
2026-02-16 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | ismaila | 2.6.6(i)a | 2.6 | Pier | 400.000 | cu.m. | 500.00 | 13000.00 | 1 | 3
2026-02-16 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 1050.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-16 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 110.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-02-16 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | illayaraja | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | kbarman | 2.8.6 (i) | 2.8 | Wing Walls | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 270.000 | cu.m. | 1700.00 | 9500.00 | 2 | 3
2026-02-16 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 75.000 | cu.m. | 4800.00 | 0 | 1 | 0
2026-02-16 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 7.000 | cu.m. | 3200.00 | 0 | 1 | 0
2026-02-16 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 1200.000 | sq.m. | 3500.00 | 11500.00 | 1 | 3
2026-02-16 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 57.000 | sq.m. | 4000.00 | 0 | 1 | 0
2026-02-16 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 12.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-16 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 71.200 | cu.m. | 3000.00 | 3000.00 | 1 | 1
2026-02-16 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-16 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 370.000 | kg. | 5400.00 | 0 | 1 | 0
2026-02-16 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 80.000 | kg. | 4100.00 | 0 | 3 | 0
2026-02-16 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 570.000 | kg. | 3000.00 | 0 | 1 | 0
2026-02-16 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 180.000 | cu.m. | 5300.00 | 18000.00 | 2 | 4
2026-02-16 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | akmishra | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | saiffuddin | 1.1 | 1.1 | Site Establishment | 35.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-02-17 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | anirban | 1.2 | 1.2 | Mobilization | 0.010 | sq.m. | 1000.00 | 6000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 10.000 | cu.m. | 1500.00 | 3000.00 | 1 | 1
2026-02-17 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 5.000 | Nos | 500.00 | 0 | 1 | 0
2026-02-17 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 18.3.6(ii) | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | akmishra | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 250.000 | cu.m. | 1500.00 | 7500.00 | 1 | 2
2026-02-17 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | vpgupta | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 950.000 | cu.m. | 3000.00 | 53000.00 | 2 | 3
2026-02-17 | akmishra | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-02-17 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | akmishra | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 80.000 | lin.m. | 4000.00 | 17000.00 | 2 | 3
2026-02-17 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 2.6.6(i) | 2.6 | Pier | 836.000 | cu.m. | 0 | 0 | 0 | 0
2026-02-17 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 80.000 | lin.m. | 500.00 | 3000.00 | 1 | 1
2026-02-17 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 75.000 | cu.m. | 800.00 | 0 | 1 | 0
2026-02-17 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 7.000 | cu.m. | 3200.00 | 0 | 1 | 0
2026-02-17 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 72.000 | sq.m. | 11900.00 | 5000.00 | 3 | 1
2026-02-17 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 9000.00 | 0 | 2 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 70.000 | sq.m. | 6400.00 | 0 | 1 | 0
2026-02-17 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 80.000 | kg. | 1800.00 | 0 | 1 | 0
2026-02-17 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 100.000 | lin.m. | 1000.00 | 0 | 1 | 0
2026-02-17 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 1000.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 336.000 | kg. | 4500.00 | 0 | 1 | 0
2026-02-17 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 18.000 | kg. | 2300.00 | 0 | 2 | 0
2026-02-17 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-02-17 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 20.000 | cu.m. | 4800.00 | 10000.00 | 1 | 3
2026-02-17 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | saiffuddin | 1.1 | 1.1 | Site Establishment | 11.000 | m | 1500.00 | 5000.00 | 1 | 1
2026-03-01 | vijaykumar | 1.1 | 1.1 | Site Establishment | 550.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-01 | anirban | 1.2 | 1.2 | Mobilization | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 9600.00 | 18000.00 | 1 | 1
2026-03-01 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 7.000 | sq.m. | 2400.00 | 0 | 1 | 0
2026-03-01 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 70.000 | lin.m. | 1600.00 | 1200.00 | 1 | 1
2026-03-01 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 385.000 | lin.m. | 3800.00 | 4200.00 | 2 | 2
2026-03-01 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 2000.00 | 10500.00 | 1 | 3
2026-03-01 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 315.000 | cu.m. | 0 | 8000.00 | 0 | 1
2026-03-01 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 6900.00 | 36000.00 | 3 | 2
2026-03-01 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1150.000 | cu.m. | 1700.00 | 19000.00 | 2 | 3
2026-03-01 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 920.000 | cu.m. | 3500.00 | 49000.00 | 2 | 3
2026-03-01 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 4780.000 | cu.m. | 0 | 37000.00 | 0 | 3
2026-03-01 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 1.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-03-01 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | lin.m. | 3000.00 | 10000.00 | 2 | 3 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | ismaila | 2.6.6(i) | 2.6 | Pier | 165.000 | cu.m. | 500.00 | 23000.00 | 1 | 3
2026-03-01 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 2.6.6(i) | 2.6 | Pier | 323.000 | cu.m. | 0 | 2500.00 | 0 | 1
2026-03-01 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 400.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-01 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 14000.00 | 1 | 3
2026-03-01 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 370.000 | lin.m. | 4000.00 | 3000.00 | 1 | 1
2026-03-01 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 1236.000 | layer | 1500.00 | 13000.00 | 1 | 3
2026-03-01 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 30.000 | lin.m. | 800.00 | 0 | 1 | 0
2026-03-01 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 10.000 | cu.m. | 5700.00 | 0 | 2 | 0
2026-03-01 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 18.000 | sq.m. | 2300.00 | 0 | 2 | 0
2026-03-01 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-01 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-01 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 80.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-03-01 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | saiffuddin | 1.1 | 1.1 | Site Establishment | 9.000 | m | 1500.00 | 5000.00 | 1 | 1
2026-03-02 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | anirban | 1.2 | 1.2 | Mobilization | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 20.000 | sq.m. | 3100.00 | 0 | 2 | 0
2026-03-02 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 772.000 | lin.m. | 5600.00 | 4200.00 | 2 | 2
2026-03-02 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 230.000 | lin.m. | 2000.00 | 3000.00 | 1 | 1
2026-03-02 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | cu.m. | 1500.00 | 5500.00 | 1 | 2
2026-03-02 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 2260.000 | cu.m. | 1700.00 | 25000.00 | 2 | 3
2026-03-02 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 550.000 | cu.m. | 5700.00 | 36000.00 | 3 | 2
2026-03-02 | anirban | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 24.000 | lin.m. | 9600.00 | 18000.00 | 1 | 1
2026-03-02 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 960.000 | cu.m. | 3500.00 | 49000.00 | 2 | 3
2026-03-02 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 3000.000 | cu.m. | 0 | 56000.00 | 0 | 3
2026-03-02 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 6736.000 | cu.m. | 2000.00 | 19500.00 | 1 | 4
2026-03-02 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 2.6.6(i) | 2.6 | Pier | 12.000 | cu.m. | 1800.00 | 0 | 1 | 0
2026-03-02 | ismaila | 2.6.6(i) | 2.6 | Pier | 600.000 | cu.m. | 500.00 | 15500.00 | 1 | 3
2026-03-02 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 650.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-02 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 11000.00 | 1 | 2
2026-03-02 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 8966.000 | cu.m. | 3500.00 | 10000.00 | 2 | 3
2026-03-02 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 42.000 | lin.m. | 2400.00 | 0 | 1 | 0
2026-03-02 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 10.000 | cu.m. | 6200.00 | 0 | 2 | 0
2026-03-02 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 2300.00 | 0 | 2 | 0
2026-03-02 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-02 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 150.000 | cu.m. | 7100.00 | 10000.00 | 2 | 3
2026-03-02 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | saiffuddin | 1.1 | 1.1 | Site Establishment | 24.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-03 | anirban | 1.2 | 1.2 | Mobilization | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 56.000 | sq.m. | 3100.00 | 0 | 2 | 0
2026-03-03 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 38.000 | lin.m. | 5500.00 | 3000.00 | 2 | 1
2026-03-03 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | cu.m. | 0 | 7500.00 | 0 | 2
2026-03-03 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1350.000 | cu.m. | 1700.00 | 16000.00 | 2 | 2
2026-03-03 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | saiffuddin | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 450.000 | cu.m. | 6900.00 | 45000.00 | 3 | 3
2026-03-03 | anirban | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 24.000 | lin.m. | 9600.00 | 18000.00 | 1 | 1
2026-03-03 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 920.000 | cu.m. | 3500.00 | 44000.00 | 2 | 3
2026-03-03 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 3800.000 | cu.m. | 0 | 68000.00 | 0 | 2
2026-03-03 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 0 | 3000.00 | 0 | 1
2026-03-03 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 120.000 | cu.m. | 0 | 13000.00 | 0 | 3
2026-03-03 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 10768.000 | cu.m. | 5000.00 | 27000.00 | 2 | 4
2026-03-03 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 400.000 | cu.m. | 0 | 6000.00 | 0 | 1
2026-03-03 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | ismaila | 2.6.6(i) | 2.6 | Pier | 270.000 | cu.m. | 500.00 | 15500.00 | 1 | 3
2026-03-03 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | vijaykumar | 2.6.6(i) | 2.6 | Pier | 350.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-03 | ismaila | 2.6.6(i)a | 2.6 | Pier | 400.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-03 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 130.000 | cu.m. | 500.00 | 2500.00 | 1 | 1
2026-03-03 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 36.000 | lin.m. | 2100.00 | 0 | 2 | 0
2026-03-03 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 18.000 | cu.m. | 4900.00 | 0 | 2 | 0
2026-03-03 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 18.000 | sq.m. | 1800.00 | 0 | 1 | 0
2026-03-03 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 2300.00 | 0 | 2 | 0
2026-03-03 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-03 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 150.000 | cu.m. | 6100.00 | 10000.00 | 2 | 3
2026-03-03 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | saiffuddin | 1.1 | 1.1 | Site Establishment | 24.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-04 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 36.000 | lin.m. | 3200.00 | 0 | 1 | 0
2026-03-04 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | anirban | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 20.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-03-04 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 150.000 | cu.m. | 1500.00 | 7500.00 | 1 | 2
2026-03-04 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1200.000 | cu.m. | 2200.00 | 20000.00 | 2 | 3
2026-03-04 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 450.000 | cu.m. | 6900.00 | 0 | 3 | 0
2026-03-04 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 830.000 | cu.m. | 3500.00 | 44000.00 | 2 | 3
2026-03-04 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 4000.000 | cu.m. | 0 | 78000.00 | 0 | 4
2026-03-04 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 150.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-03-04 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 5000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 600.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-04 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 415.000 | cu.m. | 500.00 | 17500.00 | 1 | 4
2026-03-04 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 250.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-04 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 250.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-04 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 117.000 | kg. | 900.00 | 0 | 1 | 0
2026-03-04 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-04 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 25.000 | cu.m. | 6600.00 | 5000.00 | 2 | 2
2026-03-04 | ismaila | 9.1.6(ii) | 9.0 | Approach Slab | 40.000 | lin.m. | 0 | 0 | 0 | 0
2026-03-04 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | saiffuddin | 1.1 | 1.1 | Site Establishment | 21.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-05 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5800.00 | 12000.00 | 2 | 1
2026-03-05 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 703.000 | cu.m. | 7700.00 | 0 | 2 | 0
2026-03-05 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 352.000 | kg. | 8500.00 | 3000.00 | 4 | 1
2026-03-05 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | anirban | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 30.000 | lin.m. | 1000.00 | 3000.00 | 1 | 1
2026-03-05 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 1500.00 | 7500.00 | 1 | 2
2026-03-05 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 1050.000 | cu.m. | 1700.00 | 11000.00 | 2 | 2
2026-03-05 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 600.000 | cu.m. | 6900.00 | 24000.00 | 3 | 3
2026-03-05 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 3500.00 | 44000.00 | 2 | 3
2026-03-05 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 3000.000 | cu.m. | 0 | 80000.00 | 0 | 3
2026-03-05 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 130.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-03-05 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 200.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-03-05 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 180.000 | cu.m. | 2000.00 | 12500.00 | 1 | 2
2026-03-05 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 2.6.6(i) | 2.6 | Pier | 570.000 | cu.m. | 500.00 | 18500.00 | 1 | 4
2026-03-05 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 14000.00 | 1 | 3
2026-03-05 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 250.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-05 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 350.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-05 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 1600.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 250.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-05 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 127.000 | sq.m. | 2000.00 | 0 | 1 | 0
2026-03-05 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 682.000 | kg. | 4500.00 | 0 | 1 | 0
2026-03-05 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-05 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 150.000 | cu.m. | 0 | 13000.00 | 0 | 3
2026-03-05 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 3500.00 | 3000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | saiffuddin | 1.1 | 1.1 | Site Establishment | 24.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-03-06 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | anirban | 1.2 | 1.2 | Mobilization | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 550.000 | cu.m. | 1700.00 | 6000.00 | 2 | 1
2026-03-06 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 3500.00 | 39000.00 | 2 | 3
2026-03-06 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 120.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-03-06 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.6.6(i) | 2.6 | Pier | 645.000 | cu.m. | 500.00 | 18500.00 | 1 | 4
2026-03-06 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 2.6.6(i)a | 2.6 | Pier | 210.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-06 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 300.000 | cu.m. | 1000.00 | 4500.00 | 1 | 2
2026-03-06 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 300.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-06 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-06 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 25.000 | cu.m. | 4800.00 | 5000.00 | 1 | 2
2026-03-06 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | saiffuddin | 1.1 | 1.1 | Site Establishment | 6.000 | m | 500.00 | 10000.00 | 1 | 1
2026-03-07 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5600.00 | 9000.00 | 1 | 1
2026-03-07 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 775.000 | lin.m. | 12200.00 | 0 | 2 | 0
2026-03-07 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 1500.00 | 5500.00 | 1 | 2
2026-03-07 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 800.000 | cu.m. | 1700.00 | 22000.00 | 2 | 2
2026-03-07 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 6900.00 | 26000.00 | 3 | 2
2026-03-07 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 510.000 | cu.m. | 2500.00 | 31000.00 | 2 | 3
2026-03-07 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 3500.000 | cu.m. | 0 | 66000.00 | 0 | 3
2026-03-07 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 150.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-03-07 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 200.000 | cu.m. | 1000.00 | 9000.00 | 1 | 2
2026-03-07 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | lin.m. | 3500.00 | 19500.00 | 2 | 4
2026-03-07 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | ismaila | 2.6.6(i) | 2.6 | Pier | 1850.000 | cu.m. | 500.00 | 23500.00 | 1 | 4
2026-03-07 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 380.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-07 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 230.000 | cu.m. | 3000.00 | 6500.00 | 1 | 2
2026-03-07 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 60.000 | cu.m. | 1500.00 | 17000.00 | 1 | 3
2026-03-07 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 200.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-07 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 1600.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 350.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-07 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 75.000 | sq.m. | 14400.00 | 0 | 1 | 0
2026-03-07 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 12.000 | sq.m. | 3200.00 | 0 | 1 | 0
2026-03-07 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-07 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 370.000 | cu.m. | 5600.00 | 16000.00 | 1 | 3
2026-03-07 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | ismaila | 1 | 1.0 | Preliminaries | 415.000 | sq.m. | 0 | 8500.00 | 0 | 2
2026-03-08 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | saiffuddin | 1.1 | 1.1 | Site Establishment | 29.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-03-08 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5600.00 | 9000.00 | 1 | 1
2026-03-08 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 35.000 | sq.m. | 3200.00 | 0 | 1 | 0
2026-03-08 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 30.000 | lin.m. | 5500.00 | 3000.00 | 2 | 1
2026-03-08 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | sq.m. | 1500.00 | 4500.00 | 1 | 2
2026-03-08 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 450.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-08 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 900.000 | cu.m. | 5200.00 | 20000.00 | 3 | 1
2026-03-08 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1800.000 | cu.m. | 1700.00 | 11000.00 | 2 | 2
2026-03-08 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 720.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-08 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2100.000 | cu.m. | 0 | 57000.00 | 0 | 2
2026-03-08 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | cu.m. | 0 | 10000.00 | 0 | 2
2026-03-08 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 200.000 | cu.m. | 3000.00 | 14500.00 | 1 | 4
2026-03-08 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | lin.m. | 3000.00 | 13000.00 | 2 | 3
2026-03-08 | sanjar | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | trip | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | ismaila | 2.6.6(i) | 2.6 | Pier | 240.000 | cu.m. | 0 | 13000.00 | 0 | 2
2026-03-08 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 2.6.6(i) | 2.6 | Pier | 60.000 | m | 1500.00 | 11000.00 | 1 | 3
2026-03-08 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 600.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-08 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 60.000 | lin.m. | 1000.00 | 7000.00 | 1 | 2
2026-03-08 | vijaykumar | 2.7.6 (i) | 2.7 | Abutment | 200.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-08 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 340.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-08 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 18.000 | cu.m. | 6200.00 | 0 | 2 | 0
2026-03-08 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 89.000 | sq.m. | 19200.00 | 0 | 1 | 0
2026-03-08 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 18.000 | sq.m. | 2700.00 | 0 | 1 | 0
2026-03-08 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 32.000 | sq.m. | 4800.00 | 0 | 1 | 0
2026-03-08 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 60.000 | sq.m. | 1000.00 | 0 | 1 | 0
2026-03-08 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 2300.00 | 0 | 2 | 0
2026-03-08 | kbarman | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-08 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 50.000 | cu.m. | 500.00 | 3000.00 | 1 | 1
2026-03-08 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | saiffuddin | 1.1 | 1.1 | Site Establishment | 24.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-03-09 | vijaykumar | 1.1 | 1.1 | Site Establishment | 300.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-09 | anirban | 1.2 | 1.2 | Mobilization | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5600.00 | 9000.00 | 1 | 1
2026-03-09 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 235.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-09 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | anirban | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 30.000 | sq.m. | 2000.00 | 6000.00 | 1 | 1
2026-03-09 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 380.000 | cu.m. | 0 | 13000.00 | 0 | 2
2026-03-09 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 6400.00 | 56000.00 | 3 | 2
2026-03-09 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1300.000 | cu.m. | 1700.00 | 11000.00 | 2 | 2
2026-03-09 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 700.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-09 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1500.000 | cu.m. | 0 | 32000.00 | 0 | 2
2026-03-09 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 0 | 17000.00 | 0 | 2
2026-03-09 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | lin.m. | 4000.00 | 19000.00 | 2 | 4
2026-03-09 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.6.6(i) | 2.6 | Pier | 270.000 | cu.m. | 500.00 | 13000.00 | 1 | 2
2026-03-09 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | ismaila | 2.6.6(i)a | 2.6 | Pier | 850.000 | cu.m. | 500.00 | 10500.00 | 1 | 3
2026-03-09 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 650.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-09 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | vijaykumar | 2.7.6 (i) | 2.7 | Abutment | 350.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-09 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 60.000 | lin.m. | 1000.00 | 5500.00 | 1 | 1
2026-03-09 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 360.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-09 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 84.000 | sq.m. | 10400.00 | 9000.00 | 1 | 1
2026-03-09 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-09 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 375.000 | kg. | 3600.00 | 0 | 1 | 0
2026-03-09 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | cu.m. | 7100.00 | 25500.00 | 2 | 4
2026-03-09 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | saiffuddin | 1.1 | 1.1 | Site Establishment | 21.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-03-10 | vijaykumar | 1.1 | 1.1 | Site Establishment | 200.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-10 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5600.00 | 9000.00 | 1 | 1
2026-03-10 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 586.000 | kg. | 2700.00 | 0 | 1 | 0
2026-03-10 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 235.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-10 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 3500.00 | 10500.00 | 1 | 3
2026-03-10 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 255.000 | cu.m. | 500.00 | 23000.00 | 1 | 2
2026-03-10 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 4700.00 | 25000.00 | 3 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 1700.00 | 11000.00 | 2 | 2
2026-03-10 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 750.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-10 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1800.000 | cu.m. | 0 | 62000.00 | 0 | 2
2026-03-10 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 280.000 | sq.m. | 0 | 15000.00 | 0 | 1
2026-03-10 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 110.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-03-10 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 80.000 | cu.m. | 3000.00 | 8000.00 | 1 | 2
2026-03-10 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 100.000 | lin.m. | 3000.00 | 13000.00 | 2 | 3
2026-03-10 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 2.6.6(i) | 2.6 | Pier | 450.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-03-10 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 2.6.6(i)a | 2.6 | Pier | 400.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-10 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 650.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-10 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 500.00 | 6500.00 | 1 | 2 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 60.000 | lin.m. | 1500.00 | 15000.00 | 1 | 4
2026-03-10 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 400.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-10 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 250.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-10 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 48.000 | sq.m. | 6400.00 | 9000.00 | 1 | 1
2026-03-10 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 18.000 | sq.m. | 1800.00 | 0 | 1 | 0
2026-03-10 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-10 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 18.000 | sq.m. | 1800.00 | 0 | 1 | 0
2026-03-10 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 250.000 | kg. | 2000.00 | 0 | 1 | 0
2026-03-10 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 412.000 | kg. | 3600.00 | 0 | 1 | 0
2026-03-10 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 160.000 | cu.m. | 7100.00 | 0 | 2 | 0
2026-03-10 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 1.1 | 1.1 | Site Establishment | 60.000 | cu.m. | 0 | 6000.00 | 0 | 1
2026-03-11 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | saiffuddin | 1.1 | 1.1 | Site Establishment | 40.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-03-11 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | anirban | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 1700.00 | 21000.00 | 2 | 2
2026-03-11 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 800.000 | cu.m. | 4700.00 | 25000.00 | 3 | 1
2026-03-11 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 720.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-11 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2500.000 | cu.m. | 0 | 21000.00 | 0 | 2
2026-03-11 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-03-11 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 150.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-11 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 60.000 | cu.m. | 2000.00 | 8000.00 | 1 | 2
2026-03-11 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 397.000 | sq.m. | 1500.00 | 17500.00 | 1 | 3
2026-03-11 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 450.000 | cu.m. | 500.00 | 10000.00 | 1 | 1
2026-03-11 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 2.6.6(i) | 2.6 | Pier | 150.000 | Sqm | 1000.00 | 5000.00 | 1 | 1
2026-03-11 | ismaila | 2.6.6(i) | 2.6 | Pier | 215.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-03-11 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 2.6.6(i) | 2.6 | Pier | 10.000 | m | 3000.00 | 15000.00 | 2 | 4
2026-03-11 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 300.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-11 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 360.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-11 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 60.000 | lin.m. | 2400.00 | 0 | 1 | 0
2026-03-11 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 18.000 | cu.m. | 4400.00 | 0 | 2 | 0
2026-03-11 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 350.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-11 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 16.000 | sq.m. | 12800.00 | 0 | 1 | 0
2026-03-11 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 16.000 | sq.m. | 2300.00 | 0 | 2 | 0
2026-03-11 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 500.00 | 0 | 1 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-11 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-11 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | cu.m. | 2000.00 | 6000.00 | 1 | 1
2026-03-11 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 1.1 | 1.1 | Site Establishment | 70.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-12 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | saiffuddin | 1.1 | 1.1 | Site Establishment | 14.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-12 | vijaykumar | 1.1 | 1.1 | Site Establishment | 200.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-12 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5600.00 | 9000.00 | 1 | 1
2026-03-12 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 756.000 | kg. | 5400.00 | 0 | 1 | 0
2026-03-12 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 350.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-12 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 120.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-03-12 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 240.000 | cu.m. | 1700.00 | 23000.00 | 2 | 2
2026-03-12 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 950.000 | cu.m. | 4700.00 | 50000.00 | 3 | 1
2026-03-12 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1330.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-12 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1800.000 | cu.m. | 0 | 49000.00 | 0 | 3
2026-03-12 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 350.000 | sq.m. | 0 | 28000.00 | 0 | 2
2026-03-12 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 30.000 | cu.m. | 3000.00 | 5000.00 | 1 | 1
2026-03-12 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 3500.00 | 20500.00 | 2 | 3 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 2.6.6(i) | 2.6 | Pier | 150.000 | cu.m. | 500.00 | 10000.00 | 1 | 1
2026-03-12 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | parvaiz | 2.6.6(i) | 2.6 | Pier | 893.000 | m | 500.00 | 19000.00 | 1 | 4
2026-03-12 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 6000.00 | 1 | 1
2026-03-12 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 700.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-12 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 400.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-12 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 26.000 | lin.m. | 2400.00 | 0 | 1 | 0
2026-03-12 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 18.000 | cu.m. | 5200.00 | 0 | 2 | 0
2026-03-12 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 16.000 | sq.m. | 8800.00 | 9000.00 | 1 | 1
2026-03-12 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 20.000 | sq.m. | 2300.00 | 0 | 2 | 0
2026-03-12 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 40.000 | sq.m. | 0 | 0 | 0 | 0
2026-03-12 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-12 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-12 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 150.000 | cu.m. | 8600.00 | 15500.00 | 2 | 4
2026-03-12 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | saiffuddin | 1.1 | 1.1 | Site Establishment | 3.000 | m | 1000.00 | 5000.00 | 1 | 1
2026-03-13 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 210.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-03-13 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 420.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-13 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 40.000 | cu.m. | 2500.00 | 5000.00 | 1 | 1
2026-03-13 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 500.000 | cu.m. | 1700.00 | 10500.00 | 2 | 3
2026-03-13 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 2.6.6(i) | 2.6 | Pier | 825.000 | cu.m. | 500.00 | 13000.00 | 1 | 2
2026-03-13 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 2.6.6(i)a | 2.6 | Pier | 500.000 | cu.m. | 500.00 | 11000.00 | 1 | 2
2026-03-13 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 250.000 | cu.m. | 500.00 | 2000.00 | 1 | 1
2026-03-13 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 280.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-13 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-13 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | saiffuddin | 1.1 | 1.1 | Site Establishment | 13.000 | m | 1500.00 | 5000.00 | 1 | 1
2026-03-14 | vijaykumar | 1.1 | 1.1 | Site Establishment | 200.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-14 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 92.000 | lin.m. | 8000.00 | 6000.00 | 1 | 1
2026-03-14 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | cu.m. | 1500.00 | 10500.00 | 1 | 3
2026-03-14 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 250.000 | cu.m. | 1700.00 | 10000.00 | 2 | 1
2026-03-14 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 5200.00 | 20000.00 | 3 | 1
2026-03-14 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1100.000 | sq.m. | 500.00 | 19000.00 | 1 | 3
2026-03-14 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 650.000 | cu.m. | 3500.00 | 33000.00 | 2 | 3
2026-03-14 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 4000.000 | cu.m. | 0 | 68000.00 | 0 | 2
2026-03-14 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 0 | 44000.00 | 0 | 3
2026-03-14 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 1500.00 | 10000.00 | 1 | 3 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 2.6.6(i) | 2.6 | Pier | 100.000 | m | 1500.00 | 11000.00 | 1 | 3
2026-03-14 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 18500.00 | 1 | 4
2026-03-14 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 700.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-14 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 420.000 | cu.m. | 0 | 15000.00 | 0 | 2
2026-03-14 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 8.000 | cu.m. | 3200.00 | 0 | 1 | 0
2026-03-14 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 2000.00 | 10000.00 | 2 | 3 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 38.000 | sq.m. | 4800.00 | 0 | 1 | 0
2026-03-14 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 18.000 | sq.m. | 2300.00 | 0 | 2 | 0
2026-03-14 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 10.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-14 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-14 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 714.000 | kg. | 4500.00 | 0 | 1 | 0
2026-03-14 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | sq.m. | 1500.00 | 11000.00 | 1 | 2
2026-03-14 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 3000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | saiffuddin | 1.1 | 1.1 | Site Establishment | 9.000 | m | 1500.00 | 5000.00 | 1 | 1
2026-03-15 | vijaykumar | 1.1 | 1.1 | Site Establishment | 300.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-15 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 26.000 | lin.m. | 7200.00 | 9000.00 | 1 | 1
2026-03-15 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 775.000 | kg. | 3600.00 | 0 | 1 | 0
2026-03-15 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | sq.m. | 1000.00 | 10500.00 | 1 | 3
2026-03-15 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 210.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-03-15 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 100.000 | lin.m. | 0 | 5000.00 | 0 | 1
2026-03-15 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 5200.00 | 40000.00 | 3 | 1
2026-03-15 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1150.000 | sq.m. | 2200.00 | 19000.00 | 2 | 3
2026-03-15 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 3500.00 | 38000.00 | 2 | 3
2026-03-15 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 4000.000 | cu.m. | 0 | 64000.00 | 0 | 3
2026-03-15 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 320.000 | sq.m. | 0 | 26000.00 | 0 | 2
2026-03-15 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 70.000 | cu.m. | 3000.00 | 8000.00 | 1 | 2
2026-03-15 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 3000.00 | 16000.00 | 2 | 4 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | ismaila | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | ismaila | 2.6.6(i) | 2.6 | Pier | 500.000 | cu.m. | 0 | 8000.00 | 0 | 2
2026-03-15 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | parvaiz | 2.6.6(i) | 2.6 | Pier | 60.000 | m | 1500.00 | 11000.00 | 1 | 3
2026-03-15 | ismaila | 2.6.6(i)a | 2.6 | Pier | 500.000 | cu.m. | 500.00 | 17500.00 | 1 | 4
2026-03-15 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 4000.000 | cu.m. | 0 | 0 | 0 | 0
2026-03-15 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 400.000 | cu.m. | 0 | 20000.00 | 0 | 2
2026-03-15 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 24.000 | lin.m. | 800.00 | 0 | 1 | 0
2026-03-15 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 60.000 | cu.m. | 6200.00 | 3000.00 | 2 | 1
2026-03-15 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 13.000 | cu.m. | 500.00 | 3000.00 | 1 | 1
2026-03-15 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 21.000 | sq.m. | 9600.00 | 0 | 1 | 0
2026-03-15 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 20.000 | sq.m. | 2300.00 | 0 | 2 | 0
2026-03-15 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 65.000 | sq.m. | 4000.00 | 0 | 1 | 0
2026-03-15 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 70.000 | sq.m. | 1500.00 | 0 | 1 | 0
2026-03-15 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 2300.00 | 0 | 2 | 0
2026-03-15 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-15 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 150.000 | sq.m. | 1500.00 | 11000.00 | 1 | 2
2026-03-15 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 6000.00 | 0 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | saiffuddin | 1.1 | 1.1 | Site Establishment | 29.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-16 | vijaykumar | 1.1 | 1.1 | Site Establishment | 550.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-16 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 13600.00 | 6000.00 | 1 | 1
2026-03-16 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 775.000 | kg. | 4500.00 | 0 | 1 | 0
2026-03-16 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 250.000 | cu.m. | 500.00 | 10500.00 | 1 | 3
2026-03-16 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 75.000 | cu.m. | 0 | 5000.00 | 0 | 1
2026-03-16 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 850.000 | cu.m. | 6900.00 | 15000.00 | 3 | 1
2026-03-16 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1650.000 | cu.m. | 1000.00 | 30000.00 | 1 | 3
2026-03-16 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 600.000 | cu.m. | 3500.00 | 45000.00 | 2 | 3
2026-03-16 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 2700.000 | cu.m. | 0 | 69000.00 | 0 | 3
2026-03-16 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 330.000 | sq.m. | 0 | 31000.00 | 0 | 2
2026-03-16 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 50.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-03-16 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 500.000 | cu.m. | 1700.00 | 15500.00 | 2 | 3
2026-03-16 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 60.000 | sq.m. | 1500.00 | 20500.00 | 1 | 3
2026-03-16 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 2.6.6(i) | 2.6 | Pier | 130.000 | m | 3000.00 | 16000.00 | 2 | 4
2026-03-16 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 500.000 | cu.m. | 0 | 6000.00 | 0 | 1
2026-03-16 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 27.000 | cu.m. | 1600.00 | 0 | 1 | 0
2026-03-16 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 60.000 | cu.m. | 6200.00 | 3000.00 | 2 | 1
2026-03-16 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 140.000 | sq.m. | 13600.00 | 9000.00 | 1 | 1
2026-03-16 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 100.000 | kg. | 2300.00 | 0 | 2 | 0
2026-03-16 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 20.000 | sq.m. | 1800.00 | 0 | 1 | 0
2026-03-16 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-16 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 753.000 | kg. | 3600.00 | 0 | 1 | 0
2026-03-16 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 150.000 | sq.m. | 1000.00 | 8000.00 | 1 | 2
2026-03-16 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | saiffuddin | 1.1 | 1.1 | Site Establishment | 25.000 | m | 1500.00 | 12300.00 | 1 | 3
2026-03-17 | vijaykumar | 1.1 | 1.1 | Site Establishment | 400.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-17 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 48.000 | lin.m. | 8000.00 | 9000.00 | 1 | 1
2026-03-17 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 387.000 | kg. | 9000.00 | 0 | 1 | 0
2026-03-17 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | cu.m. | 1500.00 | 5000.00 | 1 | 1
2026-03-17 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 750.000 | cu.m. | 5700.00 | 46000.00 | 3 | 2
2026-03-17 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 510.000 | cu.m. | 3500.00 | 38000.00 | 2 | 3
2026-03-17 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 3800.000 | cu.m. | 0 | 37000.00 | 0 | 3
2026-03-17 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 220.000 | sq.m. | 0 | 20000.00 | 0 | 1
2026-03-17 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 13.000 | sq.m. | 2000.00 | 20000.00 | 1 | 4
2026-03-17 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 2.6.6(i) | 2.6 | Pier | 130.000 | m | 3000.00 | 23000.00 | 2 | 4
2026-03-17 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 120.000 | cu.m. | 0 | 6000.00 | 0 | 1
2026-03-17 | illayaraja | 2.7.6 (i) | 2.7 | Abutment | 100.000 | cu.m. | 2000.00 | 6500.00 | 1 | 2
2026-03-17 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | saiffuddin | 3.2.6 (ii)a | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 36.000 | cu.m. | 1600.00 | 0 | 1 | 0
2026-03-17 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 80.000 | cu.m. | 6700.00 | 2500.00 | 2 | 1
2026-03-17 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | anirban | 5.1.7 (iii)a | 5.1 | Bearings | 274.000 | sq.m. | 17600.00 | 0 | 1 | 0
2026-03-17 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 16.000 | Sqm | 2300.00 | 0 | 2 | 0
2026-03-17 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-17 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-17 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 260.000 | cu.m. | 2500.00 | 16500.00 | 1 | 3
2026-03-17 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | saiffuddin | 1.1 | 1.1 | Site Establishment | 24.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-18 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 24.000 | lin.m. | 5600.00 | 9000.00 | 1 | 1
2026-03-18 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-03-18 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 430.000 | cu.m. | 1700.00 | 20000.00 | 2 | 1
2026-03-18 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 150.000 | cu.m. | 500.00 | 25000.00 | 1 | 3
2026-03-18 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 820.000 | cu.m. | 1000.00 | 30000.00 | 1 | 3
2026-03-18 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 60.000 | cu.m. | 0 | 2500.00 | 0 | 1
2026-03-18 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 60.000 | sq.m. | 3000.00 | 25000.00 | 1 | 5
2026-03-18 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 450.000 | cu.m. | 2500.00 | 8000.00 | 2 | 2
2026-03-18 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | ismaila | 2.6.6(i) | 2.6 | Pier | 345.000 | cu.m. | 500.00 | 13500.00 | 1 | 3
2026-03-18 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 90.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-03-18 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 130.000 | lin.m. | 3000.00 | 15000.00 | 2 | 4
2026-03-18 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 24.000 | cu.m. | 8000.00 | 0 | 1 | 0
2026-03-18 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 80.000 | cu.m. | 7300.00 | 11000.00 | 2 | 2
2026-03-18 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 20.000 | Sqm | 1600.00 | 0 | 1 | 0
2026-03-18 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | illayaraja | 5.2.6 (ii) | 5.2 | Expansion Joints | 80.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-18 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 2432.000 | kg. | 9900.00 | 0 | 1 | 0
2026-03-18 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-18 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | saiffuddin | 1.1 | 1.1 | Site Establishment | 26.000 | m | 1500.00 | 7300.00 | 1 | 3
2026-03-19 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 200.000 | cu.m. | 6000.00 | 10500.00 | 4 | 3
2026-03-19 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 175.000 | cu.m. | 1700.00 | 5000.00 | 2 | 1
2026-03-19 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 60.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-19 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 600.000 | cu.m. | 1000.00 | 30000.00 | 1 | 3
2026-03-19 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 300.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-03-19 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | saiffuddin | 2.4.6(i) | 2.4 | Pile Cap | 500.000 | cu.m. | 2500.00 | 8000.00 | 2 | 2
2026-03-19 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 2.6.6(i) | 2.6 | Pier | 350.000 | cu.m. | 500.00 | 5000.00 | 1 | 1
2026-03-19 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 200.000 | sq.m. | 2500.00 | 3000.00 | 1 | 1
2026-03-19 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-19 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 100.000 | kg. | 5400.00 | 0 | 1 | 0
2026-03-19 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 60.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-19 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-21 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 10.000 | cu.m. | 5000.00 | 0 | 2 | 0
2026-03-22 | ismaila | 1 | 1.0 | Preliminaries | 350.000 | sq.m. | 0 | 5500.00 | 0 | 2
2026-03-22 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | saiffuddin | 1.1 | 1.1 | Site Establishment | 21.000 | m | 1000.00 | 5000.00 | 1 | 1
2026-03-22 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 300.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-22 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 288.000 | cu.m. | 500.00 | 10000.00 | 1 | 1
2026-03-22 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 1800.000 | cu.m. | 2200.00 | 30000.00 | 2 | 3
2026-03-22 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 510.000 | cu.m. | 500.00 | 18000.00 | 1 | 2
2026-03-22 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 2500.00 | 11000.00 | 1 | 2
2026-03-22 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 2256.000 | sq.m. | 2500.00 | 15500.00 | 2 | 4
2026-03-22 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 900.000 | cu.m. | 2500.00 | 25000.00 | 2 | 3
2026-03-22 | ismaila | 2.6.6(i)a | 2.6 | Pier | 450.000 | cu.m. | 500.00 | 8000.00 | 1 | 2
2026-03-22 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 3362.000 | cu.m. | 1500.00 | 5500.00 | 1 | 2
2026-03-22 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 5.000 | cu.m. | 2900.00 | 0 | 2 | 0
2026-03-22 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 50.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-22 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-22 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | saiffuddin | 1.1 | 1.1 | Site Establishment | 3.000 | m | 1500.00 | 5000.00 | 1 | 1
2026-03-23 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 60.000 | cu.m. | 2500.00 | 5000.00 | 1 | 1
2026-03-23 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 520.000 | cu.m. | 1000.00 | 18000.00 | 1 | 2
2026-03-23 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 200.000 | Sqm | 500.00 | 5000.00 | 1 | 1
2026-03-23 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 2.6.6(i) | 2.6 | Pier | 150.000 | Sqm | 0 | 3000.00 | 0 | 1
2026-03-23 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 600.000 | cu.m. | 2500.00 | 30000.00 | 2 | 3
2026-03-23 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 4.500 | cu.m. | 3200.00 | 0 | 1 | 0
2026-03-23 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 10.000 | Sqm | 2300.00 | 0 | 2 | 0
2026-03-23 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-23 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 50.000 | kg. | 1800.00 | 0 | 1 | 0
2026-03-23 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 50.000 | cu.m. | 0 | 3000.00 | 0 | 1
2026-03-23 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | saiffuddin | 1.1 | 1.1 | Site Establishment | 700.000 | m | 500.00 | 23000.00 | 1 | 2
2026-03-24 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 3000.00 | 6000.00 | 1 | 1 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 2.6.6(i) | 2.6 | Pier | 80.000 | Sqm | 2000.00 | 6000.00 | 1 | 1
2026-03-24 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 900.000 | cu.m. | 2000.00 | 35000.00 | 2 | 3
2026-03-24 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 8.000 | cu.m. | 7400.00 | 0 | 2 | 0
2026-03-24 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 18.000 | Sqm | 1800.00 | 0 | 1 | 0
2026-03-24 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 80.000 | kg. | 5500.00 | 0 | 2 | 0
2026-03-24 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-24 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 1.1 | 1.1 | Site Establishment | 6.000 | Km | 4000.00 | 9000.00 | 1 | 1
2026-03-25 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | saiffuddin | 1.1 | 1.1 | Site Establishment | 700.000 | m | 1000.00 | 11000.00 | 1 | 2
2026-03-25 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 2.6.6(i) | 2.6 | Pier | 18.000 | Sqm | 3100.00 | 0 | 2 | 0
2026-03-25 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 700.000 | cu.m. | 3000.00 | 20000.00 | 2 | 3
2026-03-25 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 12.000 | cu.m. | 4800.00 | 0 | 1 | 0
2026-03-25 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 160.000 | kg. | 5400.00 | 0 | 1 | 0
2026-03-25 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-25 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 1.1 | 1.1 | Site Establishment | 6.000 | Km | 4000.00 | 6000.00 | 1 | 1
2026-03-26 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | saiffuddin | 1.1 | 1.1 | Site Establishment | 700.000 | m | 1000.00 | 11000.00 | 1 | 2
2026-03-26 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 730.000 | cu.m. | 3000.00 | 35000.00 | 2 | 3
2026-03-26 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-26 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 1.1 | 1.1 | Site Establishment | 70.000 | lin.m. | 1500.00 | 5500.00 | 1 | 2
2026-03-27 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | saiffuddin | 1.1 | 1.1 | Site Establishment | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 2.6.6(i) | 2.6 | Pier | 24.000 | Sqm | 2100.00 | 0 | 2 | 0
2026-03-27 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 250.000 | cu.m. | 0 | 5500.00 | 0 | 2
2026-03-27 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-27 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 200.000 | sq.m. | 2000.00 | 3000.00 | 1 | 1
2026-03-27 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 1.1 | 1.1 | Site Establishment | 6.000 | Km | 4000.00 | 6000.00 | 1 | 1
2026-03-28 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | saiffuddin | 1.1 | 1.1 | Site Establishment | 700.000 | m | 1500.00 | 23000.00 | 1 | 2
2026-03-28 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 400.000 | cu.m. | 2500.00 | 0 | 1 | 0
2026-03-28 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 2.6.6(i) | 2.6 | Pier | 250.000 | Sqm | 2000.00 | 5500.00 | 1 | 2
2026-03-28 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | saiffuddin | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 530.000 | cu.m. | 3000.00 | 30000.00 | 2 | 3
2026-03-28 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-28 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 1 | 1.0 | Preliminaries | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 1.1 | 1.1 | Site Establishment | 0.010 | Km | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | saiffuddin | 1.1 | 1.1 | Site Establishment | 50.000 | m | 1500.00 | 5000.00 | 1 | 1
2026-03-29 | vijaykumar | 1.1 | 1.1 | Site Establishment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | anirban | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 13.1.7(ix)b | 13.0 | Drainage | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | anirban | 13.1.7(ix)b1 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 13.1.7(ix)b2 | 13.0 | Drainage | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 18.3 | 18.3 | Bituminous Layers | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 18.3.6 | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 18.3.6(i) | 18.3 | Bituminous Layers | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.3.6(i) | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | vijaykumar | 2.3.6(i)a | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | saiffuddin | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 820.000 | cu.m. | 500.00 | 25000.00 | 1 | 3
2026-03-29 | vijaykumar | 2.3.6(i)b | 2.3 | Bored Cast In-Situ Piling | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | vijaykumar | 2.3.6(i)d | 2.3 | Bored Cast In-Situ Piling | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 2.4.6(i) | 2.4 | Pile Cap | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | sanjar | 2.4.6(i)a | 2.4 | Pile Cap | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 2.6.6(i) | 2.6 | Pier | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.6.6(i) | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 2.6.6(i) | 2.6 | Pier | 0.010 | m | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | vijaykumar | 2.6.6(i)a | 2.6 | Pier | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 2.7.6 (i) | 2.7 | Abutment | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | saiffuddin | 2.7.6 (i) | 2.7 | Abutment | 540.000 | cu.m. | 3000.00 | 23000.00 | 2 | 2
2026-03-29 | illayaraja | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | ismaila | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 3.2.6 (ii) | 3.2 | Concrete RCC | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | anirban | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | lin.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | vijaykumar | 5.1.7 (iii) | 5.1 | Bearings | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | Sqm | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 5.1.7 (iii)a | 5.1 | Bearings | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | parvaiz | 5.10.6 (i) | 5.10 | Anchor Blocks | 0.010 | cu.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 5.2.6 (ii) | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | anirban | 5.2.6 (ii)a | 5.2 | Expansion Joints | 0.010 | kg. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | illayaraja | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)
2026-03-29 | kbarman | 9.1.6(ii) | 9.0 | Approach Slab | 0.010 | sq.m. | 0 | 0 | 0 | 0 | Source qty=0 — resource deployment only (idle/no-output day)

## By-Supervisor
supervisor | dpr_count | total_qty | total_manpower_cost | total_equipment_cost
kbarman | 859 | 21535.12 | 252600 | 703400
illayaraja | 646 | 28221.8 | 580200 | 1201000
parvaiz | 468 | 41482.2 | 133100 | 747500
ismaila | 428 | 96680.64 | 113900 | 2149500
vijaykumar | 263 | 114951.47 | 150700 | 2868000
saiffuddin | 184 | 53888.42 | 232000 | 2737300
anirban | 133 | 13021.66 | 404900 | 223200
manzar | 128 | 792.16 | 53900 | 18000
sohail | 112 | 1.12 | 0 | 0
akmishra | 100 | 150.99 | 0 | 3000
sanjar | 85 | 0.85 | 0 | 0
vpgupta | 25 | 0.25 | 0 | 0

## By-Activity
activity_code | dpr_count | total_qty | total_manpower_cost | total_equipment_cost
2.3.6(i)a | 336 | 54658.25 | 254000 | 2326500
2.4.6(i) | 259 | 35674.78 | 168900 | 1016700
1.1 | 253 | 17536.75 | 85200 | 595600
2.3.6(i)b | 245 | 116279.53 | 162300 | 2875500
5.1.7 (iii) | 239 | 8391.29 | 194100 | 175500
2.6.6(i) | 210 | 24664.31 | 119300 | 699500
2.3.6(i)d | 206 | 7632.75 | 17000 | 312000
3.2.6 (ii) | 183 | 9159.47 | 43200 | 399500
2.7.6 (i) | 162 | 23395.22 | 48000 | 465500
2.4.6(i)a | 148 | 5571.36 | 6700 | 123500
9.1.6(ii) | 138 | 6903.95 | 165700 | 552000
5.1.7 (iii)a | 124 | 2216.02 | 230100 | 59000
18.3.6(i) | 104 | 750.49 | 13500 | 24000
2.3.6(i) | 100 | 2810.93 | 2200 | 69000
13.1.7(ix)b | 97 | 918.75 | 130300 | 120000
1 | 78 | 1265.75 | 4000 | 58500
5.2.6 (ii)a | 75 | 8488.52 | 95500 | 18000
13.1.7(ix)b2 | 67 | 6373.48 | 85900 | 37600
2.6.6(i)a | 62 | 20150.29 | 9500 | 222500
5.10.6 (i) | 57 | 397.52 | 7500 | 0
5.2.6 (ii) | 53 | 1393.39 | 29200 | 0
13.1.7(ix)b1 | 38 | 1877.33 | 23000 | 0
2.8.6 (i) | 37 | 1289.25 | 12000 | 52000
3.2.6 (ii)a | 35 | 5560.22 | 4700 | 215000
18.3.6 | 35 | 236.32 | 5000 | 9000
18.3 | 28 | 10.27 | 1500 | 3000
9.1.6 (iii) | 16 | 0.16 | 0 | 0
13.1.7(ix)a | 12 | 0.12 | 0 | 0
3.3.6 (ii) | 10 | 3620.03 | 0 | 88500
3.3.6 (ii)a | 10 | 3300.05 | 0 | 119000
1.2 | 6 | 0.06 | 1000 | 6000
2.1.5 (i) | 4 | 200.03 | 500 | 5000
18.3.6(ii) | 4 | 0.04 | 1500 | 3000

## By-Date
date | dpr_count | total_qty | total_manpower_cost | total_equipment_cost
2026-01-24 | 74 | 4134.58 | 46100 | 163000
2026-01-25 | 73 | 2713.6 | 37500 | 99000
2026-01-26 | 74 | 4237.6 | 28900 | 169000
2026-01-27 | 73 | 4962.55 | 27600 | 223500
2026-01-28 | 74 | 4539.57 | 25200 | 182500
2026-01-29 | 74 | 5033.56 | 25400 | 172500
2026-01-30 | 75 | 1556.67 | 11900 | 70500
2026-01-31 | 74 | 3365.57 | 27700 | 169000
2026-02-01 | 73 | 7409.54 | 19900 | 316000
2026-02-02 | 74 | 7276.55 | 33200 | 306500
2026-02-03 | 74 | 8615.51 | 28200 | 305000
2026-02-04 | 74 | 5906.51 | 31900 | 301000
2026-02-05 | 73 | 5316.57 | 29000 | 184500
2026-02-06 | 73 | 3330.69 | 6700 | 87000
2026-02-07 | 73 | 9585.51 | 33600 | 322500
2026-02-08 | 73 | 10573.51 | 37700 | 323300
2026-02-09 | 61 | 10602.38 | 53300 | 300300
2026-02-10 | 62 | 10448.4 | 49500 | 313800
2026-02-11 | 62 | 8586.43 | 50300 | 296800
2026-02-12 | 63 | 9228.92 | 45000 | 261000
2026-02-13 | 60 | 2668.48 | 17700 | 120000
2026-02-14 | 62 | 12177.37 | 52500 | 275800
2026-02-15 | 63 | 6257.45 | 37600 | 145800
2026-02-16 | 65 | 10410.6 | 59200 | 268800
2026-02-17 | 66 | 3224.48 | 52200 | 125800
2026-03-01 | 63 | 12525.39 | 54100 | 269400
2026-03-02 | 65 | 25721.45 | 60500 | 270700
2026-03-03 | 63 | 19902.41 | 55500 | 293800
2026-03-04 | 63 | 8557.47 | 27800 | 213300
2026-03-05 | 63 | 10269.42 | 49200 | 283800
2026-03-06 | 63 | 3024.54 | 17000 | 116300
2026-03-07 | 62 | 10742.42 | 65200 | 287000
2026-03-08 | 62 | 8950.35 | 73400 | 255800
2026-03-09 | 63 | 8942.42 | 49600 | 292800
2026-03-10 | 63 | 8257.37 | 57200 | 294800
2026-03-11 | 63 | 7652.4 | 46600 | 210800
2026-03-12 | 63 | 9177.38 | 59500 | 316300
2026-03-13 | 63 | 3028.54 | 10200 | 99500
2026-03-14 | 63 | 10313.43 | 45500 | 297000
2026-03-15 | 61 | 14923.34 | 60900 | 325000
2026-03-16 | 63 | 10323.4 | 67800 | 311300
2026-03-17 | 63 | 7449.44 | 68700 | 244800
2026-03-18 | 63 | 5419.46 | 48400 | 176800
2026-03-19 | 63 | 2571.52 | 22100 | 84800
2026-03-21 | 1 | 10 | 5000 | 0
2026-03-22 | 62 | 10492.49 | 18900 | 141500
2026-03-23 | 62 | 1648.02 | 15300 | 69000
2026-03-24 | 62 | 1786.56 | 22200 | 70000
2026-03-25 | 62 | 1596.56 | 21300 | 40000
2026-03-26 | 62 | 1436.59 | 8000 | 52000
2026-03-27 | 61 | 544.57 | 5600 | 14000
2026-03-28 | 61 | 1886.56 | 13000 | 64500
2026-03-29 | 61 | 1410.58 | 5000 | 53000