## README
IC-PMS SAMPLE TEST DATA — README & DATA DICTIONARY
DOCUMENT TITLE: | IC-PMS Sample Test Data — Industrial Corridor Project Management System
CONTEXT: | Delhi Mumbai Industrial Corridor (DMIC) — Multi-Node Infrastructure Programme
SPONSOR: | NICDC / Ministry of Commerce & Industry, Government of India
DATA PURPOSE: | Realistic sample data for testing all 9 IC-PMS modules — unit testing, UAT, demo, and load testing
VERSION: | 1.0 ¦ March 2026 ¦ Prepared by BIPROS GovTech Advisory
WORKSHEETS:
M1_WBS_GIS | 35 WBS elements (6 nodes, 3-4 levels deep) with codes, budgets, GIS polygon IDs, phases
M2_Schedule_Activities | 34 Activities covering DMIC-N03 Dholera SIR — CPM activities with EVM BCWS/BCWP/ACWP, float, critical path
M3_Satellite_Monitoring | 25 Satellite scene records — AI progress vs contractor claimed, alert flags, CVI, EDI, NDVI
M4_Cost_RA_Bills | 16 RA Bill records — PFMS-style with deductions (Mob Advance, Retention, TDS, GST), Satellite Gate status
M5_Contract_Register | 15 Contract / LOA records — EPC, PMC, Survey; SPI/CPI linkage, VO register, performance scores
M6_Document_Register | 30 Documents — Drawings (IFC/IFA), Specs, RFIs, Meeting Minutes, Contract Docs, MPRs
M7_Risk_Register | 22 risks + 2 opportunities — ISO 31000 format with P×I score, RAG rating, owner, response, trend
M8_Resource_Register | 32 Resources — Labour (12 categories), Equipment (14 types), Material (6 key items) with SOR rates
M9_Reports_Analytics | 18 EVM monthly data rows across 5 nodes + 14 KPI dashboard rows with RAG status
MasterData_OrgUsers | 20 users across NICDC, SPV, PMC, Contractor roles with module access matrix
MasterData_Calendars | 6 working calendars — 6-day, 7-day, office, night shift, monsoon restricted, testing
DATA CONSISTENCY NOTES:
Cross-module linkage: | WBS codes in M2/M3/M4/M5/M6/M7/M8 all reference M1 WBS codes exactly
Financial linkage: | M4 bills are tied to M5 contract LOA numbers; BCWP in M9 matches M2 activity % × BAC
EVM linkage: | SPI values in M5 contract register match M9 EVM summary; ACWP in M9 = sum of M4 bills paid
Satellite linkage: | M3 AI progress % for DMIC-N03 = 54% (latest) matches M4 Satellite Gate values exactly
Risk linkage: | M7 risk IDs RISK-DMIC-001 and 002 match the SPI/CPI alerts in M9 KPI dashboard RED cells
TEST SCENARIO SUGGESTIONS:
Scenario 1: | Submit RA Bill DMIC-N03-P01-RA-006 — AI=51%, Contractor Claim=58% → Satellite Gate should HOLD
Scenario 2: | Mark Risk RISK-DMIC-001 as 'Closed' → M9 dashboard RED risk count should update to 11
Scenario 3: | Advance data date past 31-Jan-2025 → Activity N03-M001 milestone should auto-mark complete
Scenario 4: | Update N03-A010 (WMM Layer) % complete to 25% → BCWP should recalculate; SPI should change
Scenario 5: | Add new WBS node DMIC-N03-P05 → verify it appears in M2, M4, M5 dropdown lists
Scenario 6: | BG for DMIC/P01/LOA/2024-012 expires 30-Jun-2025 → Risk M7 alert should fire 30 days before
Scenario 7: | Satellite scene SCN-N04-250328 shows 12% variance → M4 should gate N04 bills automatically
Scenario 8: | Resource EQP-EXCAV-20T at 93.8% utilisation → should appear AMBER in M8 histogram

## M1_WBS_GIS
IC-PMS MODULE 1 — WBS & GIS MASTER REGISTER ¦ DMIC Industrial Corridor Programme ¦ Test Data v1.0
WBS Code | WBS Name | WBS Level | WBS Type | Parent WBS Code | Phase | Status | Responsible Organisation | Planned Start | Planned Finish | Budget (₹ Cr) | GIS Polygon ID
DMIC | Delhi Mumbai Industrial Corridor (DMIC) Programme | 1 | Programme | — | Programme | Active | NICDC HQ | 01-Jan-2023 | 31-Dec-2030 | 44500.00 | POLY-DMIC-MASTER
DMIC-N03 | DMIC Node 3 — Dholera Special Investment Region (DSIR) | 2 | Node | DMIC | Construction | Active | DSIR SPV Ltd. | 01-Apr-2023 | 31-Mar-2028 | 8450.00 | POLY-N03-DSIR
DMIC-N03-P01 | DMIC-N03 Package P01 — Trunk Infrastructure Zone A | 3 | Package | DMIC-N03 | Construction | Active | L&T Construction Ltd. | 01-Jul-2024 | 30-Jun-2026 | 1280.00 | POLY-N03-P01
DMIC-N03-P01-WP01 | Earth Work & Grading Zone A-1 (Ch 0+000 to Ch 5+000) | 4 | Work Package | DMIC-N03-P01 | Construction | In Progress | L&T Construction Ltd. | 01-Jul-2024 | 31-Dec-2024 | 142.00 | POLY-N03-P01-WP01
DMIC-N03-P01-WP02 | Sub-Base Granular Course Ch 0+000 to Ch 5+000 | 4 | Work Package | DMIC-N03-P01 | Construction | In Progress | L&T Construction Ltd. | 15-Nov-2024 | 15-Mar-2025 | 168.00 | POLY-N03-P01-WP02
DMIC-N03-P01-WP03 | Wet Mix Macadam Layer Ch 0+000 to Ch 5+000 | 4 | Work Package | DMIC-N03-P01 | Construction | Not Started | L&T Construction Ltd. | 01-Mar-2025 | 31-Jul-2025 | 198.00 | POLY-N03-P01-WP03
DMIC-N03-P01-WP04 | Dense Bituminous Macadam & Bituminous Concrete Ch 0-5 | 4 | Work Package | DMIC-N03-P01 | Construction | Not Started | L&T Construction Ltd. | 01-Jun-2025 | 31-Oct-2025 | 224.00 | POLY-N03-P01-WP04
DMIC-N03-P01-WP05 | Earth Work & Grading Zone A-2 (Ch 5+000 to Ch 10+000) | 4 | Work Package | DMIC-N03-P01 | Construction | In Progress | L&T Construction Ltd. | 01-Sep-2024 | 28-Feb-2025 | 138.00 | POLY-N03-P01-WP05
DMIC-N03-P02 | DMIC-N03 Package P02 — Water Supply & Sewerage System | 3 | Package | DMIC-N03 | Construction | Active | SPML Infra Ltd. | 01-Sep-2024 | 31-Aug-2027 | 680.00 | POLY-N03-P02
DMIC-N03-P02-WP01 | Water Treatment Plant (100 MLD Capacity) Civil Works | 4 | Work Package | DMIC-N03-P02 | Construction | In Progress | SPML Infra Ltd. | 01-Sep-2024 | 30-Jun-2025 | 245.00 | POLY-N03-P02-WP01
DMIC-N03-P02-WP02 | Main Water Transmission Line (28 km, DN 1200mm) | 4 | Work Package | DMIC-N03-P02 | Construction | In Progress | SPML Infra Ltd. | 01-Nov-2024 | 30-Sep-2025 | 198.00 | POLY-N03-P02-WP02
DMIC-N03-P02-WP03 | Sewage Treatment Plant (75 MLD Capacity) | 4 | Work Package | DMIC-N03-P02 | Construction | Not Started | SPML Infra Ltd. | 01-Apr-2025 | 31-Dec-2025 | 237.00 | POLY-N03-P02-WP03
DMIC-N03-P03 | DMIC-N03 Package P03 — Power Sub-station (220/33kV) | 3 | Package | DMIC-N03 | Construction | Active | L&T Power Ltd. | 01-May-2024 | 31-Dec-2025 | 388.00 | POLY-N03-P03
DMIC-N03-P03-WP01 | Civil Works — Sub-station Building & Compound | 4 | Work Package | DMIC-N03-P03 | Construction | Completed | L&T Power Ltd. | 01-May-2024 | 31-Oct-2024 | 84.00 | POLY-N03-P03-WP01
DMIC-N03-P03-WP02 | Electrical Works — Transformer & Switchgear Installation | 4 | Work Package | DMIC-N03-P03 | Construction | In Progress | L&T Power Ltd. | 01-Oct-2024 | 30-Apr-2025 | 186.00 | POLY-N03-P03-WP02
DMIC-N03-P03-WP03 | Testing, Commissioning & HV Energisation | 4 | Work Package | DMIC-N03-P03 | Construction | Not Started | L&T Power Ltd. | 01-May-2025 | 31-Dec-2025 | 118.00 | POLY-N03-P03-WP03
DMIC-N03-P04 | DMIC-N03 Package P04 — ICT & Smart Infrastructure | 3 | Package | DMIC-N03 | Mobilisation | Active | Sterlite Technologies Ltd. | 01-Oct-2024 | 30-Sep-2027 | 950.00 | POLY-N03-P04
DMIC-N03-P04-WP01 | Optical Fibre Network — Backbone Ring (45 km) | 4 | Work Package | DMIC-N03-P04 | Mobilisation | In Progress | Sterlite Technologies Ltd. | 01-Oct-2024 | 30-Sep-2025 | 285.00 | POLY-N03-P04-WP01
DMIC-N03-P04-WP02 | Smart Command & Control Centre (SCCC) Building | 4 | Work Package | DMIC-N03-P04 | Mobilisation | Not Started | Sterlite Technologies Ltd. | 01-Apr-2025 | 31-Mar-2026 | 320.00 | POLY-N03-P04-WP02
DMIC-N03-P04-WP03 | Surveillance & Traffic Management System (STMS) | 4 | Work Package | DMIC-N03-P04 | Mobilisation | Not Started | Sterlite Technologies Ltd. | 01-Oct-2025 | 31-Mar-2027 | 345.00 | POLY-N03-P04-WP03
DMIC-N04 | DMIC Node 4 — Shendra-Bidkin Industrial Park (SBIP) | 2 | Node | DMIC | Construction | Active | MIDC / AURIC SPV | 01-Jan-2023 | 31-Dec-2027 | 9200.00 | POLY-N04-SBIP
DMIC-N04-P01 | DMIC-N04 Package P01 — External Development Infrastructure | 3 | Package | DMIC-N04 | Construction | Delayed | Larsen & Toubro Ltd. | 15-Feb-2024 | 14-Feb-2027 | 420.00 | POLY-N04-P01
DMIC-N04-P01-WP01 | Internal Roads & Drainage (Zone 1 — 8 km total) | 4 | Work Package | DMIC-N04-P01 | Construction | Delayed | Larsen & Toubro Ltd. | 15-Feb-2024 | 14-Aug-2024 | 105.00 | POLY-N04-P01-WP01
DMIC-N04-P01-WP02 | Internal Roads & Drainage (Zone 2 — 6.5 km total) | 4 | Work Package | DMIC-N04-P01 | Construction | In Progress | Larsen & Toubro Ltd. | 01-May-2024 | 31-Oct-2024 | 88.00 | POLY-N04-P01-WP02
DMIC-N04-P02 | DMIC-N04 Package P02 — Common Effluent Treatment Plant | 3 | Package | DMIC-N04 | Tender | At Risk | — | 01-Nov-2024 | 31-Oct-2027 | 305.00 | POLY-N04-P02
DMIC-N05 | DMIC Node 5 — Pithampur-Dhar-Mhow Investment Region | 2 | Node | DMIC | Construction | Active | PIPRDA / MP Govt SPV | 01-Jan-2024 | 31-Dec-2028 | 7800.00 | POLY-N05-PDMIR
DMIC-N05-P01 | DMIC-N05 Package P01 — Trunk Road Network (15 km) | 3 | Package | DMIC-N05 | Construction | Active | Dilip Buildcon Ltd. | 01-Apr-2024 | 31-Mar-2026 | 520.00 | POLY-N05-P01
DMIC-N06 | DMIC Node 6 — Dhule-Nardana Investment Region | 2 | Node | DMIC | Planning | Active | NMIA / MH Govt SPV | 01-Jul-2024 | 31-Dec-2029 | 8700.00 | POLY-N06-DNIR
DMIC-N06-P01 | DMIC-N06 Package P01 — Land Development Phase 1 | 3 | Package | DMIC-N06 | Planning | Not Started | — | 01-Jan-2025 | 31-Dec-2026 | 380.00 | POLY-N06-P01
DMIC-N07 | DMIC Node 7 — Greater Noida Node (JNPT Hinterland Zone) | 2 | Node | DMIC | Construction | Active | UP NRI City Ltd. SPV | 01-Oct-2022 | 31-Mar-2027 | 9200.00 | POLY-N07-GNN
DMIC-N07-P01 | DMIC-N07 Package P01 — NBCC Residential + Commercial | 3 | Package | DMIC-N07 | Construction | Active | NBCC (India) Ltd. | 01-Jan-2023 | 31-Dec-2025 | 1240.00 | POLY-N07-P01
DMIC-N07-P02 | DMIC-N07 Package P02 — Industrial Plot Development | 3 | Package | DMIC-N07 | Construction | Active | Shapoorji Pallonji Co. | 01-Apr-2023 | 31-Mar-2026 | 980.00 | POLY-N07-P02
DMIC-N08 | DMIC Node 8 — Surat-Navsari Industrial Park (SNIP) | 2 | Node | DMIC | Construction | Active | GIDC / Gujarat Govt SPV | 01-Apr-2023 | 31-Mar-2028 | 9000.00 | POLY-N08-SNIP
DMIC-N08-P01 | DMIC-N08 Package P01 — Plug & Play Factory Buildings | 3 | Package | DMIC-N08 | Construction | Active | VA Tech WABAG Ltd. | 01-Oct-2023 | 30-Sep-2026 | 685.00 | POLY-N08-P01
DMIC-N08-P02 | DMIC-N08 Package P02 — Social Infrastructure (School, Hospital) | 3 | Package | DMIC-N08 | Construction | Active | Shapoorji Pallonji Co. | 01-Jan-2024 | 31-Dec-2026 | 498.00 | POLY-N08-P02

## M2_Schedule_Activities
IC-PMS MODULE 2 — SCHEDULE & EVM — ACTIVITY MASTER ¦ DMIC-N03 Dholera SIR ¦ Data Date: 28 Mar 2026
Activity ID | Activity Name | WBS Code | Activity Type | Calendar | Planned Start | Planned Finish | Actual Start | Actual Finish | Original Duration (days) | Remaining Duration (days) | % Complete (Physical) | % Complete (Duration) | Total Float (days) | Critical Path | BCWS (₹ Lakh) | BCWP (₹ Lakh) | ACWP (₹ Lakh)
N03-A001 | Mobilisation & Site Establishment — Dholera SIR Zone A | DMIC-N03-P01 | Task-Dependent | DMIC-6day | 01-Jul-2024 | 15-Aug-2024 | 01-Jul-2024 | 20-Aug-2024 | 45 | 0 | 10000% | 100 | 0 | Yes | 285 | 285 | 295
N03-A002 | Topographic Survey & Ground Investigation Zone A-1 | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 01-Jul-2024 | 31-Jul-2024 | 01-Jul-2024 | 02-Aug-2024 | 30 | 0 | 10000% | 100 | 0 | Yes | 48 | 48 | 51
N03-A003 | Soil Testing & Geotechnical Report (25 boreholes) | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 15-Jul-2024 | 14-Aug-2024 | 15-Jul-2024 | 22-Aug-2024 | 30 | 0 | 10000% | 100 | 2 | No | 22 | 22 | 24
N03-A004 | Clearing & Grubbing Zone A-1 (580 Hectares) | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 01-Aug-2024 | 30-Sep-2024 | 01-Aug-2024 | 05-Oct-2024 | 60 | 0 | 10000% | 100 | 0 | Yes | 125 | 125 | 130
N03-A005 | Earthwork Excavation — Zone A-1 Ch 0+000 to Ch 5+000 | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 01-Sep-2024 | 30-Nov-2024 | 01-Sep-2024 | — | 90 | 12 | 8700% | 87 | 0 | Yes | 485 | 422 | 440
N03-A006 | Earthwork Embankment — Zone A-1 (1.2 M Cum Fill) | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 01-Oct-2024 | 31-Jan-2025 | 01-Oct-2024 | — | 120 | 35 | 7100% | 71 | 0 | Yes | 620 | 440 | 462
N03-A007 | Compaction & Proof Rolling Zone A-1 | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 01-Nov-2024 | 28-Feb-2025 | 10-Nov-2024 | — | 119 | 55 | 5400% | 54 | 0 | Yes | 168 | 91 | 95
N03-A008 | Formation Level Checking & FRL Correction | DMIC-N03-P01-WP01 | Task-Dependent | DMIC-6day | 01-Dec-2024 | 31-Mar-2025 | — | — | 120 | 120 | 0% | 0 | 8 | No | 45 | 0 | 0
N03-A009 | Granular Sub-Base (GSB) Zone A-1 — 350mm thick | DMIC-N03-P01-WP02 | Task-Dependent | DMIC-6day | 15-Nov-2024 | 14-Mar-2025 | 20-Nov-2024 | — | 119 | 62 | 4800% | 48 | 0 | Yes | 385 | 185 | 195
N03-A010 | Wet Mix Macadam (WMM) Layer Zone A-1 — 250mm | DMIC-N03-P01-WP03 | Task-Dependent | DMIC-6day | 01-Mar-2025 | 30-Jun-2025 | — | — | 121 | 121 | 0% | 0 | 0 | Yes | 420 | 0 | 0
N03-A011 | Dense Bituminous Macadam (DBM) Zone A-1 | DMIC-N03-P01-WP04 | Task-Dependent | DMIC-6day | 01-Jun-2025 | 31-Aug-2025 | — | — | 91 | 91 | 0% | 0 | 0 | Yes | 380 | 0 | 0
N03-A012 | Bituminous Concrete (BC) Surface Course Zone A-1 | DMIC-N03-P01-WP04 | Task-Dependent | DMIC-6day | 01-Sep-2025 | 31-Oct-2025 | — | — | 60 | 60 | 0% | 0 | 0 | Yes | 210 | 0 | 0
N03-A013 | Road Markings, Kerbs & Street Furniture Zone A-1 | DMIC-N03-P01-WP04 | Task-Dependent | DMIC-6day | 01-Nov-2025 | 30-Nov-2025 | — | — | 30 | 30 | 0% | 0 | 4 | No | 68 | 0 | 0
N03-A014 | Earthwork Zone A-2 Ch 5+000 to Ch 10+000 | DMIC-N03-P01-WP05 | Task-Dependent | DMIC-6day | 01-Sep-2024 | 31-Jan-2025 | 05-Sep-2024 | — | 152 | 38 | 7500% | 75 | 0 | Yes | 485 | 364 | 380
N03-A015 | Sub-Base Zone A-2 | DMIC-N03-P01-WP05 | Task-Dependent | DMIC-6day | 01-Jan-2025 | 30-Apr-2025 | — | — | 119 | 119 | 0% | 0 | 0 | Yes | 365 | 0 | 0
N03-A016 | Intake Works & Raw Water Pumping Main | DMIC-N03-P02-WP01 | Task-Dependent | DMIC-6day | 01-Sep-2024 | 28-Feb-2025 | 05-Sep-2024 | — | 180 | 46 | 7400% | 74 | 0 | Yes | 485 | 359 | 375
N03-A017 | WTP Civil Works — Clarifiers, Filters, Sludge Thickeners | DMIC-N03-P02-WP01 | Task-Dependent | DMIC-6day | 01-Oct-2024 | 30-Apr-2025 | 10-Oct-2024 | — | 210 | 72 | 6600% | 66 | 0 | Yes | 620 | 409 | 428
N03-A018 | WTP Mechanical & Electrical Works | DMIC-N03-P02-WP01 | Task-Dependent | DMIC-6day | 01-Mar-2025 | 30-Jun-2025 | — | — | 121 | 121 | 0% | 0 | 0 | Yes | 380 | 0 | 0
N03-A019 | Water Transmission Main (DN 1200mm) — 0-10 km | DMIC-N03-P02-WP02 | Task-Dependent | DMIC-6day | 01-Nov-2024 | 30-Apr-2025 | 05-Nov-2024 | — | 180 | 60 | 6700% | 67 | 0 | Yes | 490 | 328 | 345
N03-A020 | Water Transmission Main (DN 1200mm) — 10-28 km | DMIC-N03-P02-WP02 | Task-Dependent | DMIC-6day | 01-Feb-2025 | 30-Sep-2025 | — | — | 241 | 241 | 0% | 0 | 0 | Yes | 710 | 0 | 0
N03-A021 | Sub-station Civil Works — Main Building & GIS Room | DMIC-N03-P03-WP01 | Task-Dependent | DMIC-6day | 01-May-2024 | 31-Oct-2024 | 01-May-2024 | 05-Nov-2024 | 183 | 0 | 10000% | 100 | 0 | Yes | 485 | 485 | 498
N03-A022 | 220kV GIS Switchgear Supply & Erection | DMIC-N03-P03-WP02 | Task-Dependent | DMIC-6day | 01-Oct-2024 | 31-Jan-2025 | 05-Oct-2024 | — | 122 | 28 | 7700% | 77 | 0 | Yes | 620 | 477 | 492
N03-A023 | 220/33kV Power Transformer Supply & Erection (3×100MVA) | DMIC-N03-P03-WP02 | Task-Dependent | DMIC-6day | 01-Nov-2024 | 28-Feb-2025 | 10-Nov-2024 | — | 119 | 35 | 7100% | 71 | 0 | Yes | 810 | 575 | 595
N03-A024 | 33kV Switchgear, Busbar & Protection Systems | DMIC-N03-P03-WP02 | Task-Dependent | DMIC-6day | 01-Jan-2025 | 31-Mar-2025 | — | — | 90 | 90 | 0% | 0 | 5 | No | 295 | 0 | 0
N03-A025 | HV Testing & Commissioning 220kV Bay | DMIC-N03-P03-WP03 | Task-Dependent | DMIC-6day | 01-Apr-2025 | 31-Jul-2025 | — | — | 121 | 121 | 0% | 0 | 0 | Yes | 180 | 0 | 0
N03-A026 | Fibre Optic Cable Laying — Backbone Ring Segment 1 (15 km) | DMIC-N03-P04-WP01 | Task-Dependent | DMIC-6day | 01-Oct-2024 | 31-Jan-2025 | 08-Oct-2024 | — | 122 | 32 | 7400% | 74 | 0 | Yes | 285 | 211 | 225
N03-A027 | Fibre Optic Cable Laying — Backbone Ring Segment 2 (15 km) | DMIC-N03-P04-WP01 | Task-Dependent | DMIC-6day | 01-Jan-2025 | 30-Apr-2025 | — | — | 119 | 119 | 0% | 0 | 0 | Yes | 285 | 0 | 0
N03-A028 | Fibre Optic Cable Laying — Backbone Ring Segment 3 (15 km) | DMIC-N03-P04-WP01 | Task-Dependent | DMIC-6day | 01-Apr-2025 | 31-Jul-2025 | — | — | 121 | 121 | 0% | 0 | 0 | Yes | 285 | 0 | 0
N03-A029 | OFC Joint Pits, Manholes & Surface Restoration | DMIC-N03-P04-WP01 | Task-Dependent | DMIC-6day | 01-Aug-2025 | 30-Sep-2025 | — | — | 61 | 61 | 0% | 0 | 3 | No | 68 | 0 | 0
N03-A030 | SCCC Building Civil Works | DMIC-N03-P04-WP02 | Task-Dependent | DMIC-6day | 01-Apr-2025 | 31-Dec-2025 | — | — | 274 | 274 | 0% | 0 | 0 | Yes | 485 | 0 | 0
N03-M001 | Milestone — Zone A-1 Earthwork Completion | DMIC-N03-P01-WP01 | Milestone | DMIC-6day | 31-Jan-2025 | 31-Jan-2025 | — | — | 0 | 0 | 0% | 0 | 0 | Yes | 0 | 0 | 0
N03-M002 | Milestone — Sub-station 220kV Energisation | DMIC-N03-P03-WP03 | Milestone | DMIC-6day | 31-Jul-2025 | 31-Jul-2025 | — | — | 0 | 0 | 0% | 0 | 0 | Yes | 0 | 0 | 0
N03-M003 | Milestone — WTP Commissioning (Phase 1) | DMIC-N03-P02-WP01 | Milestone | DMIC-6day | 30-Jun-2025 | 30-Jun-2025 | — | — | 0 | 0 | 0% | 0 | 0 | Yes | 0 | 0 | 0
N03-M004 | Milestone — Trunk Road Zone A-1 Substantial Completion | DMIC-N03-P01 | Milestone | DMIC-6day | 30-Nov-2025 | 30-Nov-2025 | — | — | 0 | 0 | 0% | 0 | 0 | Yes | 0 | 0 | 0

## M3_Satellite_Monitoring
IC-PMS MODULE 3 — SATELLITE MONITORING & AI ANALYTICS ¦ DMIC Corridor ¦ Scene Data Register
Scene ID | WBS Node | Satellite Source | Scene Date | Cloud Cover % | Resolution (m) | AI Progress % (U-Net) | Contractor Claimed % | Variance % | Alert Flag | CVI (Construction Velocity Index) | EDI (Equipment Density Index) | NDVI Change | Processing Status
SCN-N03-240701 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 01-Jul-2024 | 2.1 | 0.25 | 5 | 8 | 3 | Green | 0.12 | 0.08 | −0.02 | Processed
SCN-N03-240801 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 05-Aug-2024 | 8.4 | 0.25 | 14 | 18 | 4 | Green | 0.38 | 0.22 | −0.08 | Processed
SCN-N03-240901 | DMIC-N03 Dholera SIR | Planet Scope | 02-Sep-2024 | 3.2 | 3.0 | 22 | 26 | 4 | Green | 0.52 | 0.35 | −0.14 | Processed
SCN-N03-241001 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 04-Oct-2024 | 1.8 | 0.25 | 31 | 35 | 4 | Green | 0.68 | 0.48 | −0.22 | Processed
SCN-N03-241101 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 06-Nov-2024 | 0.5 | 0.25 | 38 | 42 | 4 | Green | 0.82 | 0.58 | −0.31 | Processed
SCN-N03-241201 | DMIC-N03 Dholera SIR | Planet Scope | 03-Dec-2024 | 4.8 | 3.0 | 45 | 52 | 7 | AMBER — Variance >5% | 0.92 | 0.68 | −0.38 | Processed
SCN-N03-250101 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 08-Jan-2025 | 0.9 | 0.25 | 51 | 58 | 7 | AMBER — Variance >5% | 1.04 | 0.78 | −0.44 | Processed
SCN-N03-250201 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 05-Feb-2025 | 12.8 | 0.25 | 54 | 62 | 8 | AMBER — Variance >5% | 1.08 | 0.82 | −0.48 | Processed
SCN-N03-250301 | DMIC-N03 Dholera SIR | Planet Scope | 04-Mar-2025 | 3.6 | 3.0 | 54 | 61 | 7 | AMBER — Variance >5% | 1.08 | 0.82 | −0.48 | Processed
SCN-N03-250328 | DMIC-N03 Dholera SIR | ISRO Cartosat-3 | 25-Mar-2026 | 3.2 | 0.25 | 54 | 61 | 7 | AMBER — Variance >5% | 1.09 | 0.84 | −0.48 | Processed
SCN-N04-240801 | DMIC-N04 Shendra-Bidkin | ISRO Cartosat-3 | 08-Aug-2024 | 5.2 | 0.25 | 8 | 12 | 4 | Green | 0.24 | 0.16 | −0.05 | Processed
SCN-N04-241001 | DMIC-N04 Shendra-Bidkin | Planet Scope | 10-Oct-2024 | 2.4 | 3.0 | 18 | 24 | 6 | AMBER — Variance >5% | 0.48 | 0.32 | −0.14 | Processed
SCN-N04-241201 | DMIC-N04 Shendra-Bidkin | ISRO Cartosat-3 | 12-Dec-2024 | 7.8 | 0.25 | 24 | 34 | 10 | RED — Variance >10% | 0.62 | 0.42 | −0.22 | Processed
SCN-N04-250201 | DMIC-N04 Shendra-Bidkin | ISRO Cartosat-3 | 14-Feb-2025 | 4.5 | 0.25 | 28 | 40 | 12 | RED — Variance >10% | 0.72 | 0.52 | −0.28 | Processed
SCN-N04-250328 | DMIC-N04 Shendra-Bidkin | ISRO Cartosat-3 | 26-Mar-2026 | 1.8 | 0.25 | 32 | 44 | 12 | RED — Variance >10% | 0.78 | 0.55 | −0.32 | Processed
SCN-N05-241101 | DMIC-N05 Pithampur | Planet Scope | 15-Nov-2024 | 6.2 | 3.0 | 12 | 15 | 3 | Green | 0.32 | 0.24 | −0.08 | Processed
SCN-N05-250201 | DMIC-N05 Pithampur | ISRO Cartosat-3 | 18-Feb-2025 | 2.8 | 0.25 | 22 | 26 | 4 | Green | 0.55 | 0.38 | −0.14 | Processed
SCN-N05-250328 | DMIC-N05 Pithampur | ISRO Cartosat-3 | 27-Mar-2026 | 4.1 | 0.25 | 28 | 30 | 2 | Green | 0.68 | 0.48 | −0.18 | Processed
SCN-N07-240601 | DMIC-N07 Greater Noida | ISRO Cartosat-3 | 05-Jun-2024 | 1.2 | 0.25 | 35 | 38 | 3 | Green | 0.88 | 0.62 | −0.28 | Processed
SCN-N07-241201 | DMIC-N07 Greater Noida | Planet Scope | 08-Dec-2024 | 0.8 | 3.0 | 62 | 65 | 3 | Green | 1.42 | 0.98 | −0.52 | Processed
SCN-N07-250328 | DMIC-N07 Greater Noida | ISRO Cartosat-3 | 28-Mar-2026 | 2.4 | 0.25 | 72 | 74 | 2 | Green | 1.68 | 1.12 | −0.62 | Processed
SCN-N08-241001 | DMIC-N08 Surat-Navsari | Planet Scope | 12-Oct-2024 | 3.8 | 3.0 | 28 | 30 | 2 | Green | 0.72 | 0.52 | −0.22 | Processed
SCN-N08-250328 | DMIC-N08 Surat-Navsari | ISRO Cartosat-3 | 29-Mar-2026 | 5.1 | 0.25 | 48 | 50 | 2 | Green | 1.18 | 0.84 | −0.38 | Processed
SCN-N03-ALERT-01 | DMIC-N03 Zone A-2 (Encroachment) | Planet Scope | 15-Jan-2025 | 2.2 | 3.0 | — | — | — | RED — Encroachment Detected | — | — | −0.12 | Alert — Manual Review
SCN-N04-ALERT-01 | DMIC-N04 Zone B (Idle >14 days) | ISRO Cartosat-3 | 20-Feb-2025 | 1.5 | 0.25 | — | — | — | AMBER — Idle Zone Detected | 0.05 | 0.02 | −0.02 | Alert — Manual Review

## M4_Cost_RA_Bills
IC-PMS MODULE 4 — COST MANAGEMENT ¦ RA BILL REGISTER ¦ DMIC-N03 Dholera SIR
Bill No. | LOA No. | WBS Package | Contractor | Bill Date | Period From | Period To | Gross Bill (₹ Cr) | Mob. Advance Recovery (₹ Cr) | Retention (5%) (₹ Cr) | TDS (2%) (₹ Cr) | GST (18%) (₹ Cr) | Net Payable (₹ Cr) | AI Satellite % (M3) | Contractor Claimed % | Satellite Gate | Approval Status | PFMS DPA Ref | Payment Date
DMIC-N03-P01-RA-001 | DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | L&T Construction Ltd. | 15-Sep-2024 | 01-Jul-2024 | 31-Aug-2024 | 12.4 | 0.62 | 0.62 | 0.25 | 2.23 | 13.14 | 8 | 8 | PASS | Paid | PFMS/2024/DPA/04521 | 05-Oct-2024
DMIC-N03-P01-RA-002 | DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | L&T Construction Ltd. | 15-Oct-2024 | 01-Sep-2024 | 30-Sep-2024 | 18.6 | 1.86 | 0.93 | 0.37 | 3.35 | 18.79 | 22 | 22 | PASS | Paid | PFMS/2024/DPA/05218 | 05-Nov-2024
DMIC-N03-P01-RA-003 | DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | L&T Construction Ltd. | 15-Nov-2024 | 01-Oct-2024 | 31-Oct-2024 | 24.8 | 2.48 | 1.24 | 0.5 | 4.46 | 25.04 | 31 | 31 | PASS | Paid | PFMS/2024/DPA/06122 | 05-Dec-2024
DMIC-N03-P01-RA-004 | DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | L&T Construction Ltd. | 15-Dec-2024 | 01-Nov-2024 | 30-Nov-2024 | 31.2 | 3.12 | 1.56 | 0.62 | 5.62 | 31.52 | 38 | 42 | HOLD — Variance 4% | Paid — PMC Override | PFMS/2024/DPA/07045 | 05-Jan-2025
DMIC-N03-P01-RA-005 | DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | L&T Construction Ltd. | 15-Jan-2025 | 01-Dec-2024 | 31-Dec-2024 | 38.5 | 3.85 | 1.93 | 0.77 | 6.93 | 38.88 | 45 | 52 | HOLD — Variance 7% | Paid — PMC Override | PFMS/2025/DPA/00381 | 05-Feb-2025
DMIC-N03-P01-RA-006 | DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | L&T Construction Ltd. | 15-Feb-2025 | 01-Jan-2025 | 31-Jan-2025 | 44.2 | 4.42 | 2.21 | 0.88 | 7.96 | 44.65 | 51 | 58 | HOLD — Variance 7% | PMC Review Pending | — | —
DMIC-N03-P02-RA-001 | DMIC/P02/LOA/2024-028 | DMIC-N03-P02 | SPML Infra Ltd. | 20-Nov-2024 | 01-Sep-2024 | 31-Oct-2024 | 15.8 | 0.79 | 0.79 | 0.32 | 2.84 | 16.74 | 8 | 8 | PASS | Paid | PFMS/2024/DPA/06348 | 10-Dec-2024
DMIC-N03-P02-RA-002 | DMIC/P02/LOA/2024-028 | DMIC-N03-P02 | SPML Infra Ltd. | 20-Dec-2024 | 01-Nov-2024 | 30-Nov-2024 | 22.4 | 2.24 | 1.12 | 0.45 | 4.03 | 22.62 | 18 | 22 | HOLD — Variance 4% | Paid — PMC Override | PFMS/2024/DPA/07238 | 10-Jan-2025
DMIC-N03-P02-RA-003 | DMIC/P02/LOA/2024-028 | DMIC-N03-P02 | SPML Infra Ltd. | 20-Jan-2025 | 01-Dec-2024 | 31-Dec-2024 | 28.6 | 2.86 | 1.43 | 0.57 | 5.15 | 28.89 | 25 | 30 | HOLD — Variance 5% | Approved | — | —
DMIC-N03-P03-RA-001 | DMIC/P03/LOA/2024-018 | DMIC-N03-P03 | L&T Power Ltd. | 10-Dec-2024 | 01-May-2024 | 30-Nov-2024 | 42.5 | 4.25 | 2.13 | 0.85 | 7.65 | 42.92 | 100 | 100 | PASS | Paid | PFMS/2024/DPA/07502 | 30-Dec-2024
DMIC-N03-P03-RA-002 | DMIC/P03/LOA/2024-018 | DMIC-N03-P03 | L&T Power Ltd. | 15-Feb-2025 | 01-Dec-2024 | 31-Jan-2025 | 28.8 | 2.88 | 1.44 | 0.58 | 5.18 | 29.08 | 65 | 72 | HOLD — Variance 7% | PMC Review Pending | — | —
DMIC-N03-P04-RA-001 | DMIC/P04/LOA/2024-031 | DMIC-N03-P04 | Sterlite Tech. | 15-Feb-2025 | 01-Oct-2024 | 31-Jan-2025 | 22.4 | 0 | 1.12 | 0.45 | 4.03 | 24.86 | 18 | 22 | HOLD — Variance 4% | Approved | — | —
DMIC-N04-P01-RA-001 | DMIC-N04/P01/LOA/2024-022 | DMIC-N04-P01 | Larsen & Toubro Ltd. | 15-Oct-2024 | 15-Feb-2024 | 14-Sep-2024 | 18.2 | 0.91 | 0.91 | 0.36 | 3.28 | 19.3 | 8 | 12 | HOLD — Variance 4% | Paid — PMC Override | PFMS/2024/DPA/05820 | 05-Nov-2024
DMIC-N04-P01-RA-002 | DMIC-N04/P01/LOA/2024-022 | DMIC-N04-P01 | Larsen & Toubro Ltd. | 15-Dec-2024 | 15-Sep-2024 | 14-Dec-2024 | 28.6 | 1.43 | 1.43 | 0.57 | 5.15 | 30.32 | 18 | 32 | RED — Variance 14% | HOLD — Satellite Dispute | — | —
DMIC-N07-P01-RA-001 | DMIC-N07/P01/LOA/2023-008 | DMIC-N07-P01 | NBCC (India) Ltd. | 15-Dec-2024 | 01-Jan-2023 | 30-Nov-2024 | 182.5 | 18.25 | 9.13 | 3.65 | 32.85 | 184.32 | 62 | 65 | PASS | Paid | PFMS/2024/DPA/07680 | 31-Dec-2024
DMIC-N07-P02-RA-001 | DMIC-N07/P02/LOA/2023-012 | DMIC-N07-P02 | Shapoorji Pallonji | 15-Jan-2025 | 01-Apr-2023 | 31-Dec-2024 | 148.2 | 14.82 | 7.41 | 2.96 | 26.68 | 150.69 | 55 | 58 | PASS | Paid | PFMS/2025/DPA/00542 | 05-Feb-2025

## M5_Contract_Register
IC-PMS MODULE 5 — CONTRACT MANAGEMENT ¦ LOA & CONTRACT REGISTER ¦ DMIC Programme
LOA No. | Package Code | Package Description | Contractor Name | Contract Type | LOA Value (₹ Cr) | LOA Date | Contract Start | Contract End | Actual Completion | SPI (Module 2) | CPI (Module 4) | Physical Progress (AI) | Cumulative RA Bills (₹ Cr) | VO Nos. Issued | VO Value (₹ Cr) | Contract Status | Performance Score (100) | BG Expiry
DMIC/P01/LOA/2024-012 | DMIC-N03-P01 | Trunk Infrastructure Zone A — Road Network (16 km), Drains, Utility Ducts | L&T Construction Ltd. | EPC Lump Sum (FIDIC Yellow) | 1089.5 | 15-Jun-2024 | 01-Jul-2024 | 30-Dec-2026 | — | 0.87 | 0.92 | 54 | 169.2 | 3 | 28.4 | Active — At Risk | 76.8 | 30-Jun-2026
DMIC/P02/LOA/2024-028 | DMIC-N03-P02 | Water Supply & Sewerage System — WTP + Transmission Mains | SPML Infra Ltd. | EPC Lump Sum (FIDIC Yellow) | 643 | 10-Aug-2024 | 01-Sep-2024 | 31-Mar-2027 | — | 0.91 | 0.93 | 28 | 66.8 | 1 | 8.2 | Active | 79.2 | 10-Aug-2026
DMIC/P03/LOA/2024-018 | DMIC-N03-P03 | 220/33kV Power Sub-station — 3×100MVA | L&T Power Ltd. | Item Rate (FIDIC Red) | 388 | 15-Apr-2024 | 01-May-2024 | 31-Dec-2025 | — | 0.96 | 0.97 | 82 | 71.3 | 0 | 0 | Active | 91.3 | 15-Apr-2026
DMIC/P04/LOA/2024-031 | DMIC-N03-P04 | ICT Infrastructure — OFC Backbone + SCCC Building + STMS | Sterlite Technologies Ltd. | EPC Lump Sum (FIDIC Yellow) | 812 | 15-Sep-2024 | 01-Oct-2024 | 30-Jun-2027 | — | 0.95 | 0.96 | 18 | 22.4 | 0 | 0 | Mobilisation | 82.3 | 15-Sep-2026
DMIC/P05/LOA/2024-038 | DMIC-N03-P05 | CETP — Common Effluent Treatment Plant (50 MLD) | VA Tech WABAG Ltd. | EPC Lump Sum (FIDIC Yellow) | 305 | 01-Nov-2024 | 15-Nov-2024 | 30-Sep-2027 | — | 0.97 | 0.96 | 12 | 14.8 | 0 | 0 | Active | 87.3 | 01-Nov-2026
DMIC/P06/LOA/2024-042 | DMIC-N03-P06 | Social Infrastructure — School, Hospital, Community Centre | Shapoorji Pallonji Co. | EPC Lump Sum (FIDIC Silver) | 498 | 20-Nov-2024 | 01-Dec-2024 | 31-Mar-2028 | — | 0.84 | 0.88 | 8 | 18.5 | 0 | 0 | Active — Delayed | 62.7 | 20-Nov-2026
DMIC-N04/P01/LOA/2024-022 | DMIC-N04-P01 | External Development Works — Internal Roads & Drainage | Larsen & Toubro Ltd. | EPC Lump Sum (FIDIC Yellow) | 420 | 01-Feb-2024 | 15-Feb-2024 | 14-Feb-2027 | — | 0.78 | 0.82 | 28 | 46.8 | 2 | 14.2 | Delayed | 58.4 | 01-Feb-2026
DMIC-N04/P02/LOA/2024-035 | DMIC-N04-P02 | CETP Works — Common Effluent Treatment 80 MLD | VA Tech WABAG Ltd. | EPC Lump Sum (FIDIC Yellow) | 280 | 15-Oct-2024 | 01-Nov-2024 | 30-Sep-2027 | — | 0.96 | 0.97 | 15 | 12.4 | 0 | 0 | Active | 84.1 | 15-Oct-2026
DMIC-N05/P01/LOA/2024-015 | DMIC-N05-P01 | Trunk Road Network — 15 km Multi-lane Road with Services | Dilip Buildcon Ltd. | EPC Lump Sum (FIDIC Yellow) | 520 | 15-Mar-2024 | 01-Apr-2024 | 31-Mar-2026 | — | 0.89 | 0.91 | 38 | 68.2 | 1 | 6.8 | Active | 81.6 | 15-Mar-2026
DMIC-N07/P01/LOA/2023-008 | DMIC-N07-P01 | NBCC Residential + Commercial Complex — Phase 1 | NBCC (India) Ltd. | Item Rate (FIDIC Red) | 1240 | 15-Dec-2022 | 01-Jan-2023 | 31-Dec-2025 | — | 0.94 | 0.96 | 72 | 330.7 | 2 | 18.4 | Active | 88.5 | 15-Dec-2025
DMIC-N07/P02/LOA/2023-012 | DMIC-N07-P02 | Industrial Plot Development — Infrastructure & Servicing | Shapoorji Pallonji Co. | EPC Lump Sum (FIDIC Yellow) | 980 | 01-Mar-2023 | 01-Apr-2023 | 31-Mar-2026 | — | 0.91 | 0.93 | 55 | 148.2 | 1 | 12.8 | Active | 84.8 | 01-Mar-2026
DMIC-N08/P01/LOA/2023-018 | DMIC-N08-P01 | Plug & Play Factory Buildings — 12 Units | VA Tech WABAG Ltd. | EPC Lump Sum (FIDIC Yellow) | 685 | 01-Sep-2023 | 01-Oct-2023 | 30-Sep-2026 | — | 0.97 | 0.99 | 48 | 182.6 | 1 | 8.4 | Active | 90.2 | 01-Sep-2026
DMIC-N08/P02/LOA/2024-008 | DMIC-N08-P02 | Social Infrastructure Phase 1 — School + Primary Health Centre | Shapoorji Pallonji Co. | EPC Lump Sum (FIDIC Yellow) | 498 | 01-Dec-2023 | 01-Jan-2024 | 31-Dec-2026 | — | 0.86 | 0.89 | 22 | 38.4 | 0 | 0 | Active | 76.4 | 01-Dec-2025
DMIC/PMC/LOA/2023-001 | DMIC-N03 to N08 (All) | PMC Services — Project Management Consultancy All Nodes | AECOM India Pvt. Ltd. | Percentage-based PMC (4%) | 560 | 01-Oct-2022 | 01-Nov-2022 | 31-Dec-2030 | — | 1.02 | 1.01 | 68 | 228.4 | 0 | 0 | Active | 92.8 | 01-Oct-2026
DMIC/SURVEY/LOA/2024-005 | DMIC-N03 to N08 | Geospatial Survey, Drone Mapping & GIS Services | Survey of India (Licensed) | Lump Sum + Unit Rate | 24.5 | 01-Jan-2024 | 15-Jan-2024 | 31-Dec-2026 | — | 1.05 | 1.02 | 80 | 14.8 | 0 | 0 | Active | 95.1 | 01-Jan-2026

## M6_Document_Register
IC-PMS MODULE 6 — DOCUMENT MANAGEMENT ¦ DRAWING REGISTER + DOCUMENT LOG ¦ DMIC-N03
Document Code | Document Title | Document Type | WBS Package | Discipline | Revision | Status | Issued By | Issued Date | Approved By | Approved Date | File Size (MB) | Transmittal No.
DRW-N03-CIV-0001 | Site Layout Plan — Dholera SIR Zone A (1:5000) | Drawing | DMIC-N03-P01 | Civil | C | IFC | L&T Engg. | 15-Aug-2024 | AECOM PMC | 28-Aug-2024 | 4.2 | TXL-N03-001
DRW-N03-CIV-0002 | Earthwork Cross Sections — Ch 0+000 to Ch 5+000 | Drawing | DMIC-N03-P01-WP01 | Civil | B | IFC | L&T Engg. | 22-Aug-2024 | AECOM PMC | 05-Sep-2024 | 8.6 | TXL-N03-001
DRW-N03-CIV-0003 | Road Cross Section — Standard Details (4-lane Divided) | Drawing | DMIC-N03-P01-WP03 | Civil | D | IFC | L&T Engg. | 01-Sep-2024 | AECOM PMC | 15-Sep-2024 | 2.1 | TXL-N03-002
DRW-N03-CIV-0004 | Retaining Wall Details — Type RW-1 (H=3.0m) | Drawing | DMIC-N03-P01 | Structural | A | IFA | L&T Engg. | 10-Oct-2024 | AECOM PMC | — | 1.8 | TXL-N03-004
DRW-N03-CIV-0005 | Culvert Design — Box Culvert 2m×1.5m (Typ.) | Drawing | DMIC-N03-P01 | Civil | B | IFC | L&T Engg. | 15-Oct-2024 | AECOM PMC | 25-Oct-2024 | 2.4 | TXL-N03-005
DRW-N03-CIV-0006 | Pile Layout Plan — Bridge P-1 Abutment | Drawing | DMIC-N03-P01 | Structural | A | IFC | L&T Engg. | 20-Oct-2024 | AECOM PMC | 05-Nov-2024 | 3.2 | TXL-N03-005
DRW-N03-CIV-0007 | Drainage Layout Plan — Zone A-1 (1:2000) | Drawing | DMIC-N03-P01-WP01 | Civil | C | IFC | L&T Engg. | 01-Nov-2024 | AECOM PMC | 15-Nov-2024 | 5.8 | TXL-N03-006
DRW-N03-CIV-0008 | Sub-Base & GSB Specification Details | Drawing | DMIC-N03-P01-WP02 | Civil | A | IFC | L&T Engg. | 15-Nov-2024 | AECOM PMC | 28-Nov-2024 | 1.4 | TXL-N03-007
DRW-N03-STR-0001 | Foundation Raft Details — WTP Building | Drawing | DMIC-N03-P02-WP01 | Structural | B | IFC | SPML Engg. | 20-Sep-2024 | AECOM PMC | 05-Oct-2024 | 6.2 | TXL-N03-003
DRW-N03-STR-0002 | WTP — Clarifier Tank Structural Design | Drawing | DMIC-N03-P02-WP01 | Structural | A | IFC | SPML Engg. | 01-Oct-2024 | AECOM PMC | 18-Oct-2024 | 4.8 | TXL-N03-003
DRW-N03-ELC-0001 | 220/33kV Sub-station Single Line Diagram | Drawing | DMIC-N03-P03 | Electrical | B | IFC | L&T Power | 15-Jun-2024 | AECOM PMC | 30-Jun-2024 | 3.6 | TXL-N03-008
DRW-N03-ELC-0002 | GIS Switchgear Layout — 220kV Bay | Drawing | DMIC-N03-P03-WP02 | Electrical | A | IFC | L&T Power | 01-Aug-2024 | AECOM PMC | 15-Aug-2024 | 2.8 | TXL-N03-009
DRW-N03-ELC-0003 | 33kV Busbar & Protection Schematic | Drawing | DMIC-N03-P03-WP02 | Electrical | A | IFA | L&T Power | 01-Nov-2024 | AECOM PMC | — | 2.1 | TXL-N03-010
DRW-N03-ICT-0001 | OFC Backbone Route Map — Dholera SIR (1:10000) | Drawing | DMIC-N03-P04-WP01 | ICT | B | IFC | Sterlite | 20-Sep-2024 | AECOM PMC | 05-Oct-2024 | 6.8 | TXL-N03-011
SPEC-N03-CIV-0001 | Technical Specification — Earthwork, Compaction & Grading | Specification | DMIC-N03-P01 | Civil | 1 | Approved | AECOM PMC | 01-Jun-2024 | NICDC Eng. | 15-Jun-2024 | 0.8 | TXL-N03-000
SPEC-N03-CIV-0002 | Technical Specification — GSB, WMM, DBM, BC Pavement | Specification | DMIC-N03-P01 | Civil | 2 | Approved | AECOM PMC | 01-Jun-2024 | NICDC Eng. | 15-Jun-2024 | 1.2 | TXL-N03-000
SPEC-N03-WTP-0001 | Technical Specification — WTP Equipment & Mechanical | Specification | DMIC-N03-P02 | Mechanical | 1 | Approved | SPML Engg. | 01-Jul-2024 | AECOM PMC | 20-Jul-2024 | 2.4 | TXL-N03-002
RFI-N03-P01-001 | RFI — Soil Bearing Capacity Discrepancy Zone A-1 Ch 2+500 | RFI | DMIC-N03-P01-WP01 | Civil | 1 | Closed | L&T Construction | 15-Sep-2024 | AECOM PMC | 25-Sep-2024 | 0.4 | —
RFI-N03-P01-002 | RFI — Road Camber Change Request Ch 4+000 to Ch 5+000 | RFI | DMIC-N03-P01-WP02 | Civil | 1 | Open | L&T Construction | 10-Nov-2024 | AECOM PMC | — | 0.3 | —
RFI-N03-P01-003 | RFI — Sub-grade CBR Value Below Minimum at Ch 1+850 | RFI | DMIC-N03-P01-WP02 | Civil | 1 | Open | L&T Construction | 20-Nov-2024 | AECOM PMC | — | 0.5 | —
RFI-N03-P02-001 | RFI — Pipe Alignment Clash with Existing Stormwater Drain | RFI | DMIC-N03-P02-WP02 | Civil | 1 | Closed | SPML Infra | 01-Nov-2024 | AECOM PMC | 15-Nov-2024 | 0.6 | —
RFI-N03-P03-001 | RFI — Transformer Foundation Depth Query | RFI | DMIC-N03-P03-WP01 | Structural | 1 | Closed | L&T Power | 01-Jun-2024 | AECOM PMC | 10-Jun-2024 | 0.3 | —
MIN-N03-NICDC-001 | Monthly Progress Meeting Minutes — October 2024 | Minutes | DMIC-N03 | Management | — | Approved | NICDC PMO | 05-Nov-2024 | NICDC PM Dir. | 08-Nov-2024 | 0.6 | —
MIN-N03-NICDC-002 | Monthly Progress Meeting Minutes — November 2024 | Minutes | DMIC-N03 | Management | — | Approved | NICDC PMO | 05-Dec-2024 | NICDC PM Dir. | 08-Dec-2024 | 0.7 | —
MIN-N03-NICDC-003 | Monthly Progress Meeting Minutes — December 2024 | Minutes | DMIC-N03 | Management | — | Approved | NICDC PMO | 05-Jan-2025 | NICDC PM Dir. | 09-Jan-2025 | 0.7 | —
LOA-N03-P01-001 | Letter of Award — DMIC-N03 Package P01 — L&T Construction | Contract Document | DMIC-N03-P01 | Legal | — | Executed | NICDC Legal | 15-Jun-2024 | NICDC MD | 15-Jun-2024 | 2.4 | —
BRD-N03-P01-001 | Bank Guarantee — Perf. Bond — L&T Const. — P01 — ₹108.95 Cr | Contract Document | DMIC-N03-P01 | Finance | — | Valid | SBI Ahmedabad | 15-Jun-2024 | NICDC Finance | 18-Jun-2024 | 0.8 | —
RPT-N03-MPR-202410 | Monthly Progress Report — DMIC-N03 — October 2024 | Report | DMIC-N03 | Management | — | Published | AECOM PMC | 10-Nov-2024 | NICDC MD | 15-Nov-2024 | 8.4 | —
RPT-N03-MPR-202411 | Monthly Progress Report — DMIC-N03 — November 2024 | Report | DMIC-N03 | Management | — | Published | AECOM PMC | 10-Dec-2024 | NICDC MD | 15-Dec-2024 | 9.2 | —
RPT-N03-MPR-202412 | Monthly Progress Report — DMIC-N03 — December 2024 | Report | DMIC-N03 | Management | — | Published | AECOM PMC | 10-Jan-2025 | NICDC MD | 15-Jan-2025 | 8.8 | —

## M7_Risk_Register
IC-PMS MODULE 7 — RISK REGISTER ¦ DMIC Corridor Programme ¦ ISO 31000 Compliant
Risk ID | Risk Title | WBS Scope | Risk Category | Probability (1-5) | Impact — Cost (1-5) | Impact — Schedule (1-5) | Risk Score (P×I) | RAG Rating | Risk Owner | Response Strategy | Response Action | Due Date | Residual Risk Score | Trend | Status
RISK-DMIC-001 | Land Acquisition Delay — DMIC-N04 Shendra-Bidkin Remaining 480 Ha | DMIC-N04 | Land Acquisition | 5 | 5 | 5 | 25 | CRIMSON | SPV MIDC Land Dept. | Transfer | Engage State Revenue Dept.; gazette notification expedited; alternate land bank identified | 15-Apr-2025 | 16 | Worsening | Open — Escalated to NICDC MD
RISK-DMIC-002 | Contractor Default Risk — L&T Dholera P01 (SPI 0.87 × 3 months) | DMIC-N03-P01 | Contractor | 4 | 5 | 5 | 20 | CRIMSON | PMC AECOM Lead | Mitigate | Weekly site review; mobilise additional equipment; L&T Board escalation letter sent | 01-Apr-2025 | 12 | Stable | Open — Under Active Management
RISK-DMIC-003 | Monsoon Delay Risk — Earthwork stoppage Jun–Sep 2025 | DMIC-N03-P01-WP01 | Natural Hazard | 5 | 3 | 4 | 15 | RED | DMIC-N03 SPV PM | Accept | Pre-monsoon completion of earthwork accelerated; revised programme issued | 30-Jun-2025 | 6 | Improving | Open — Being Managed
RISK-DMIC-004 | Forest Clearance Pending — DMIC-N05 Pithampur Reserved Forest 28 Ha | DMIC-N05 | Regulatory / EC | 4 | 4 | 4 | 16 | RED | NICDC Legal Cell | Mitigate | MoEFCC PARIVESH Stage 2 submitted 01-Dec-2024; Forest Advisory Committee hearing scheduled | 30-Apr-2025 | 8 | Stable | Open
RISK-DMIC-005 | Steel Price Escalation — Reinforcement Steel +18% over BOQ Rate | DMIC-N03 to N08 | Market / Inflation | 4 | 3 | 2 | 12 | AMBER | SPV CFO / Finance | Transfer | Price variation clause (CPWD SOR WPI-linked) invoked; additional ₹38 Cr contingency earmarked | 30-Jun-2025 | 9 | Stable | Open
RISK-DMIC-006 | DPR Inadequacy — Water Balance Error in DMIC-N03-P02 WTP Design | DMIC-N03-P02 | Design / Technical | 3 | 4 | 3 | 12 | AMBER | PMC Design Lead | Mitigate | Revised hydraulic design submitted by SPML; AECOM design review in progress | 15-Mar-2025 | 6 | Improving | Open
RISK-DMIC-007 | Labour Unrest — Migrant Labour Wage Dispute at Dholera Site | DMIC-N03 | Labour / HR | 3 | 2 | 3 | 9 | AMBER | L&T HR Manager | Mitigate | Wage disbursement moved to direct bank transfer (PFMS-linked); EPFO compliance verified | Ongoing | 4 | Improving | Open — Monitor
RISK-DMIC-008 | Underground Utility Conflict — Undisclosed Gas Pipeline at Ch 2+800 | DMIC-N03-P01-WP01 | Design / Survey | 2 | 4 | 3 | 12 | AMBER | L&T Site Eng. | Mitigate | GAIL notified; pipeline protection measures being designed; 3-week schedule impact flagged | 15-Feb-2025 | 6 | Stable | Open
RISK-DMIC-009 | Variation Order Accumulation — DMIC-N04-P01 at 9.2% of LOA | DMIC-N04-P01 | Scope Creep | 4 | 3 | 2 | 12 | AMBER | NICDC Programme Dir. | Mitigate | Scope freeze directive issued; VO committee review mandatory >1 Cr; board approval >10% threshold | 30-Apr-2025 | 8 | Worsening | Open — Watch
RISK-DMIC-010 | Pollution Liability — WTP Discharge Non-compliance (GPCB) | DMIC-N03-P02 | Regulatory / Env. | 3 | 4 | 2 | 12 | AMBER | SPML Environment Mgr | Transfer | Environmental insurance taken; GPCB consent conditions incorporated in design | 30-Sep-2025 | 6 | Stable | Open
RISK-DMIC-011 | IT System Integration Delay — PFMS-IC-PMS API | All Modules | Technology | 2 | 2 | 2 | 6 | GREEN | NICDC IT Lead | Mitigate | NIC development team engaged; UAT scheduled Q2 2025 | 30-Jun-2025 | 4 | Improving | Open
RISK-DMIC-012 | PMC Capacity Shortage — AECOM Key Personnel Attrition (3 of 8) | All DMIC Nodes | Resource | 3 | 3 | 3 | 9 | AMBER | NICDC HR & Contracts | Mitigate | Contractual penalty clause invoked; AECOM Mumbai office deploying replacement team | 15-Mar-2025 | 6 | Improving | Open
RISK-DMIC-013 | Bank Guarantee Expiry Risk — L&T P01 BG expires 30-Jun-2025 | DMIC-N03-P01 | Finance / Legal | 2 | 4 | 1 | 8 | AMBER | NICDC Finance | Mitigate | BG renewal notice sent; if not renewed by 01-Jun-2025, payment stoppage and NICDC call | 01-Jun-2025 | 4 | Stable | Open
RISK-DMIC-014 | NDVI Vegetation Loss Exceeding EC Limit — DMIC-N03 Zone B | DMIC-N03 | Environmental / EC | 3 | 4 | 3 | 12 | AMBER | NICDC Environment | Mitigate | Compensatory afforestation plan submitted to MoEFCC; satellite monitoring NDVI trigger activated | 31-Mar-2025 | 6 | Stable | Open
RISK-DMIC-015 | Political Risk — State Election Causing SPV Governance Gap | DMIC-N04, N05 | Political | 2 | 3 | 3 | 9 | AMBER | NICDC MD | Accept | Contingency governance plan with NICDC HQ as interim SPV administrator approved | 30-Jun-2025 | 6 | Stable | Open — Monitor
RISK-DMIC-016 | Supply Chain Disruption — Transformer Import Delay (220kV units) | DMIC-N03-P03 | Supply Chain | 2 | 4 | 4 | 16 | RED | L&T Power Procurement | Mitigate | Alternate vendor (Siemens India) qualified; advance order placed; buffer stock at Vadodara warehouse | 15-Apr-2025 | 8 | Improving | Open
RISK-DMIC-017 | Archaeological Finding — Indus Valley Period Artefacts at Ch 6+200 | DMIC-N03-P01 | Regulatory / Env. | 1 | 3 | 4 | 12 | AMBER | NICDC Legal / ASI | Transfer | ASI notified; excavation halt order received; alternative alignment Ch 5+800 to Ch 6+600 being evaluated | 30-Apr-2025 | 6 | Stable | Open — ASI Review
RISK-DMIC-018 | Currency Risk — Dollar-Linked Equipment Import for ICT Package | DMIC-N03-P04 | Market / Finance | 2 | 2 | 1 | 4 | GREEN | Sterlite CFO | Transfer | Forward contract hedging for USD 4.2 Mn; partial INR components sourced locally | 31-Dec-2025 | 3 | Stable | Open — Monitor
RISK-DMIC-019 | Commissioning Risk — WTP Quality Compliance (Turbidity NTU Target) | DMIC-N03-P02 | Technical / Quality | 2 | 3 | 2 | 6 | GREEN | SPML Technical Dir. | Mitigate | Pilot testing at 10 MLD proposed; full-scale commissioning protocol developed with GPCB | 31-Aug-2025 | 4 | Stable | Open
RISK-DMIC-020 | Geotechnical Risk — Black Cotton Soil Zone — DMIC-N05 Site | DMIC-N05-P01 | Design / Technical | 3 | 3 | 3 | 9 | AMBER | Dilip Buildcon Site Eng. | Mitigate | Lime stabilisation treatment design approved; additional boring at 100m grid intervals | 15-Mar-2025 | 6 | Improving | Open
OPP-DMIC-001 | Opportunity — Early Completion Bonus — DMIC-N03-P03 (Power Sub-stn) | DMIC-N03-P03 | Opportunity | 4 | 4 | 0 | 16 | OPPORTUNITY | L&T Power Ltd. | Exploit | Accelerated commissioning programme approved; bonus = ₹12 Cr if complete by 30-Nov-2025 | 30-Nov-2025 | 0 | Improving | Open — Target
OPP-DMIC-002 | Opportunity — Economies of Scale — Bulk Cement Procurement DMIC-N03+N04 | DMIC-N03, N04 | Opportunity | 3 | 3 | 0 | 9 | OPPORTUNITY | NICDC Procurement | Exploit | Joint procurement committee formed; Ultratech contract saves est. ₹8.4 Cr | 31-Mar-2025 | 0 | Stable | Realised — Partially

## M8_Resource_Register
IC-PMS MODULE 8 — RESOURCE MANAGEMENT ¦ LABOUR, EQUIPMENT & MATERIAL REGISTER ¦ DMIC-N03
Resource Code | Resource Name | Resource Type | Category | Unit | CPWD SOR 2024-25 Rate (₹) | Overtime Rate (₹) | Pool (Max Available) | Planned Units (Today) | Actual Units (Today) | Utilisation % | Responsible Contractor | WBS Assignment | Daily Cost (₹ Lakh) | Cumulative Cost (₹ Cr) | Status
LAB-MASON-SK-001 | Mason (Skilled) — Brick & Block Work | Labour | Skilled Labour | Per Day | 850 | 1275 | 280 | 248 | 242 | 97.6 | L&T Construction | DMIC-N03-P01 | 2.06 | 1.48 | Active — Over 90%
LAB-MASON-SK-002 | Mason (Skilled) — Plaster & Finishing | Labour | Skilled Labour | Per Day | 850 | 1275 | 120 | 108 | 105 | 97.2 | SPML Infra | DMIC-N03-P02 | 0.89 | 0.52 | Active — Over 90%
LAB-CARP-SK-001 | Carpenter (Skilled) — Formwork & Shuttering | Labour | Skilled Labour | Per Day | 920 | 1380 | 180 | 162 | 158 | 97.5 | L&T Construction | DMIC-N03-P01 | 1.45 | 0.98 | Active — Over 90%
LAB-STBND-SK-001 | Bar Bender & Steel Fixer (Skilled) | Labour | Skilled Labour | Per Day | 880 | 1320 | 200 | 185 | 183 | 99 | L&T Construction | DMIC-N03-P01 | 1.61 | 1.22 | Active — Critical 100%
LAB-WELD-SK-001 | Welder (Skilled) — 6G Certified | Labour | Skilled Labour | Per Day | 1200 | 1800 | 45 | 40 | 38 | 95 | L&T Power | DMIC-N03-P03 | 0.46 | 0.32 | Active
LAB-ELEC-SK-001 | Electrician (Licensed) — LV/MV | Labour | Skilled Labour | Per Day | 1100 | 1650 | 60 | 52 | 50 | 96.2 | L&T Power | DMIC-N03-P03 | 0.55 | 0.38 | Active
LAB-PLUMB-SK-001 | Plumber (Skilled) — Large Diameter Pipes | Labour | Skilled Labour | Per Day | 900 | 1350 | 80 | 72 | 70 | 97.2 | SPML Infra | DMIC-N03-P02 | 0.63 | 0.42 | Active
LAB-SEMI-001 | Semi-Skilled Labour — General Construction | Labour | Semi-Skilled | Per Day | 650 | 975 | 480 | 425 | 418 | 98.4 | L&T Construction | DMIC-N03-P01 | 2.72 | 1.98 | Active — Over 90%
LAB-UNSK-001 | Unskilled Labour — Earthwork (Helpers) | Labour | Unskilled | Per Day | 520 | 780 | 380 | 342 | 330 | 96.5 | L&T Construction | DMIC-N03-P01-WP01 | 1.72 | 1.25 | Active
LAB-SURV-001 | Land Surveyor (Total Station / GPS) | Labour | Technical Staff | Per Day | 2200 | 3300 | 18 | 16 | 15 | 93.8 | Survey Contractor | DMIC-N03-P01 | 0.33 | 0.22 | Active
LAB-QCSUP-001 | Quality Control Supervisor (Civil) | Labour | Technical Staff | Per Day | 2800 | 4200 | 12 | 11 | 11 | 100 | AECOM PMC | DMIC-N03-P01 | 0.31 | 0.24 | Active
LAB-SAFOFF-001 | Safety Officer (Certified) | Labour | HSE Staff | Per Day | 3500 | 5250 | 6 | 6 | 6 | 100 | L&T Safety Dept. | DMIC-N03 (All) | 0.21 | 0.18 | Active
EQP-EXCAV-20T | Excavator 20T (Komatsu PC200 / JCB JS200) | Equipment | Earth Moving | Per Day | 8500 | 12750 | 18 | 16 | 15 | 93.8 | L&T Construction | DMIC-N03-P01-WP01 | 1.28 | 0.92 | Active
EQP-EXCAV-32T | Excavator 32T (Komatsu PC300) | Equipment | Earth Moving | Per Day | 12000 | 18000 | 8 | 7 | 7 | 100 | L&T Construction | DMIC-N03-P01-WP01 | 0.84 | 0.58 | Active — 100%
EQP-BULL-D6 | Bulldozer D6 (CAT D6T) | Equipment | Earth Moving | Per Day | 9800 | 14700 | 12 | 10 | 10 | 100 | L&T Construction | DMIC-N03-P01-WP01 | 0.98 | 0.72 | Active — 100%
EQP-MOTOR-GR | Motor Grader 140G | Equipment | Earth Moving | Per Day | 8200 | 12300 | 8 | 7 | 6 | 85.7 | L&T Construction | DMIC-N03-P01-WP02 | 0.49 | 0.35 | Active
EQP-VCOMP-25T | Vibratory Compactor 25T (CAT CS64) | Equipment | Compaction | Per Day | 7500 | 11250 | 10 | 9 | 9 | 100 | L&T Construction | DMIC-N03-P01-WP02 | 0.68 | 0.48 | Active — 100%
EQP-TIPER-12CU | Tipper Truck 12 Cu.M (TATA 2518) | Equipment | Transport | Per Day | 4200 | 6300 | 45 | 40 | 38 | 95 | L&T Construction | DMIC-N03-P01 | 1.60 | 1.12 | Active
EQP-WTT-ROAD | Water Tanker (12,000 L) | Equipment | Compaction Support | Per Day | 3200 | 4800 | 6 | 5 | 5 | 100 | L&T Construction | DMIC-N03-P01-WP02 | 0.16 | 0.11 | Active
EQP-PAVER-ROAD | Paver Finisher — Bituminous (CAT AP600) | Equipment | Road Works | Per Day | 18000 | 27000 | 3 | 0 | 0 | 0 | L&T Construction | DMIC-N03-P01-WP03 | 0.00 | 0.00 | On Hold — Not Mobilised
EQP-CRANE-50T | Mobile Crane 50T (LIEBHERR LTM 1050) | Equipment | Lifting | Per Day | 15000 | 22500 | 3 | 2 | 2 | 100 | L&T Power | DMIC-N03-P03 | 0.30 | 0.22 | Active
EQP-BRCRANE-10T | Building Crane (10T Tower Crane) | Equipment | Lifting | Per Day | 6500 | 9750 | 4 | 3 | 3 | 100 | SPML Infra | DMIC-N03-P02 | 0.20 | 0.14 | Active
EQP-MANLIFT-15M | Aerial Work Platform — 15M Boom Lift | Equipment | Access | Per Day | 3800 | 5700 | 5 | 4 | 4 | 100 | L&T Power | DMIC-N03-P03 | 0.15 | 0.10 | Active
EQP-GPIPE-DN1200 | Pipe Laying Machine — DN 1200 (TRACTO) | Equipment | Pipeline | Per Day | 22000 | 33000 | 2 | 2 | 2 | 100 | SPML Infra | DMIC-N03-P02-WP02 | 0.44 | 0.30 | Active
EQP-CONCBATCH | Concrete Batching Plant 60 m3/hr | Equipment | Concrete | Per Day | 14000 | 21000 | 3 | 2 | 2 | 100 | L&T Construction | DMIC-N03-P01 | 0.28 | 0.20 | Active
EQP-DG-1000KVA | Diesel Generator Set 1000 KVA (Cummins) | Equipment | Power | Per Day | 6800 | 10200 | 6 | 5 | 5 | 100 | L&T Construction | DMIC-N03-P01 | 0.34 | 0.24 | Active
MAT-STEEL-TMT-25 | Reinforcement Steel TMT Fe-500 25mm (SAIL/TATA) | Material | Steel | MT | 58500 | — | — | 42 | 42 | 100 | L&T Construction | DMIC-N03-P01 | 2.46 | 52.80 | Active — Procurement
MAT-CEMENT-OPC-53 | OPC 53 Grade Cement — Bulk (Ultratech/ACC) | Material | Cement | MT | 7200 | — | — | 85 | 85 | 100 | L&T Construction | DMIC-N03-P01 | 0.61 | 18.42 | Active — Procurement
MAT-SAND-MSAND | M-Sand (Manufactured Sand) — CPWD Approved | Material | Aggregate | Cu.M | 1800 | — | — | 320 | 310 | 96.9 | L&T Construction | DMIC-N03-P01 | 0.56 | 12.25 | Active
MAT-AGATE-20MM | Coarse Aggregate 20mm (Granite) — Zone A | Material | Aggregate | Cu.M | 2200 | — | — | 280 | 275 | 98.2 | L&T Construction | DMIC-N03-P01 | 0.61 | 14.80 | Active
MAT-PIPE-DI-DN1200 | DI Pipe DN 1200 Class K9 (TATA Metaliks) | Material | Pipe | RMT | 28500 | — | — | 180 | 162 | 90 | SPML Infra | DMIC-N03-P02-WP02 | 4.62 | 24.50 | Active — Delivery Ongoing
MAT-CABLE-OFC-24F | OFC 24-Fibre HDPE Duct Cable | Material | Cable | RMT | 185 | — | — | 4500 | 4200 | 93.3 | Sterlite Tech. | DMIC-N03-P04-WP01 | 0.78 | 2.18 | Active — Laying

## M9_Reports_Analytics
IC-PMS MODULE 9 — REPORTS & ANALYTICS ¦ MONTHLY PROGRESS REPORT SUMMARY ¦ DMIC CORRIDOR ¦ FY 2024-25 TO 2025-26
DATA DATE: 28 MARCH 2026 ¦ Generated by IC-PMS Module 9 Reporting Engine ¦ Status: FINAL — Approved by NICDC MD
Report Month | Node | BCWS (₹ Cr) | BCWP (₹ Cr) | ACWP (₹ Cr) | BAC (₹ Cr) | SPI | CPI | EAC (₹ Cr) | ETC (₹ Cr) | CV (₹ Cr) | SV (₹ Cr) | % Complete (AI Satellite) | % Complete (Contractor) | Schedule Status | Total RED Risks | Open RA Bills (₹ Cr) | MPR Status
Jul-2024 | DMIC-N03 Dholera | 48.5 | 38.2 | 41.4 | 8450.0 | 0.79 | 0.92 | 8892.4 | 8854.2 | -3.2 | -10.3 | 5 | 8 | Behind Schedule (SPI<0.85) | 0 | 0 | Draft — Under PMC Review
Aug-2024 | DMIC-N03 Dholera | 125.8 | 102.4 | 110.2 | 8450.0 | 0.81 | 0.93 | 8844.3 | 8741.9 | -7.8 | -23.4 | 14 | 18 | Behind Schedule (SPI<0.85) | 0 | 0 | Approved
Sep-2024 | DMIC-N03 Dholera | 245.6 | 208.2 | 222.8 | 8450.0 | 0.85 | 0.93 | 8714.8 | 8492 | -14.6 | -37.4 | 22 | 26 | On Schedule (SPI>=0.85) | 1 | 0 | Approved
Oct-2024 | DMIC-N03 Dholera | 420.8 | 368.4 | 394.2 | 8450.0 | 0.88 | 0.93 | 8526.6 | 8132.4 | -25.8 | -52.4 | 31 | 35 | On Schedule | 1 | 24.8 | Approved
Nov-2024 | DMIC-N03 Dholera | 648.2 | 568.8 | 608.6 | 8450.0 | 0.88 | 0.93 | 8338 | 7729.4 | -39.8 | -79.4 | 38 | 42 | On Schedule | 2 | 56.2 | Approved
Dec-2024 | DMIC-N03 Dholera | 924.5 | 820.8 | 878.2 | 8450.0 | 0.89 | 0.93 | 8144.2 | 7265.9 | -57.4 | -103.7 | 45 | 52 | On Schedule | 2 | 38.5 | Approved
Jan-2025 | DMIC-N03 Dholera | 1248.6 | 1106.8 | 1184.2 | 8450.0 | 0.89 | 0.93 | 7942.7 | 6835.9 | -77.4 | -141.8 | 51 | 58 | On Schedule | 3 | 66.8 | Approved
Feb-2025 | DMIC-N03 Dholera | 1580.2 | 1374.4 | 1494.8 | 8450.0 | 0.87 | 0.92 | 9185.4 | 7810.7 | -120.4 | -205.8 | 54 | 61 | Behind Schedule (SPI<0.85) | 3 | 71.2 | Approved
Mar-2025 (Latest) | DMIC-N03 Dholera | 1580.2 | 1374.4 | 1494.8 | 8450.0 | 0.87 | 0.92 | 9185.4 | 7810.7 | -120.4 | -205.8 | 54 | 61 | Behind Schedule | 3 | 71.2 | Approved — Data Date 28-Mar
Oct-2024 | DMIC-N04 Shendra-Bidkin | 180.4 | 144.2 | 158.8 | 9200.0 | 0.8 | 0.91 | 9890.2 | 9731.4 | -14.6 | -36.2 | 12 | 18 | Behind Schedule | 4 | 28.6 | Approved
Jan-2025 | DMIC-N04 Shendra-Bidkin | 580.2 | 452.4 | 508.8 | 9200.0 | 0.78 | 0.89 | 10068.4 | 9560 | -56.4 | -127.8 | 24 | 36 | Delayed (SPI<0.80) | 5 | 46.8 | Approved
Mar-2025 (Latest) | DMIC-N04 Shendra-Bidkin | 824.8 | 648.2 | 724.4 | 9200.0 | 0.79 | 0.89 | 9964.8 | 9240.4 | -76.2 | -176.6 | 28 | 40 | Behind Schedule | 6 | 46.8 | Approved
Oct-2024 | DMIC-N05 Pithampur | 124.8 | 108.2 | 118.4 | 7800.0 | 0.87 | 0.91 | 8218.2 | 8099.8 | -10.2 | -16.6 | 12 | 15 | On Schedule | 2 | 0 | Approved
Mar-2025 (Latest) | DMIC-N05 Pithampur | 425.2 | 368.2 | 402.4 | 7800.0 | 0.87 | 0.92 | 8020.4 | 7618 | -34.2 | -57 | 28 | 30 | On Schedule | 2 | 0 | Approved
Oct-2024 | DMIC-N07 Greater Noida | 1284.2 | 1188.4 | 1228.8 | 9200.0 | 0.93 | 0.97 | 9352.4 | 8163.6 | -40.4 | -95.8 | 48 | 50 | On Schedule | 1 | 0 | Approved
Mar-2025 (Latest) | DMIC-N07 Greater Noida | 2184.8 | 2048.2 | 2104.4 | 9200.0 | 0.94 | 0.97 | 9288.6 | 7240.4 | -56.2 | -136.6 | 62 | 65 | On Schedule | 1 | 0 | Approved
Oct-2024 | DMIC-N08 Surat-Navsari | 684.2 | 648.4 | 668.2 | 9000.0 | 0.95 | 0.97 | 9092.4 | 8424.2 | -19.8 | -35.8 | 28 | 30 | On Schedule | 0 | 0 | Approved
Mar-2025 (Latest) | DMIC-N08 Surat-Navsari | 1548.6 | 1484.8 | 1524.4 | 9000.0 | 0.96 | 0.97 | 9041.8 | 7556.9 | -39.6 | -63.8 | 48 | 50 | On Schedule | 0 | 0 | Approved
KPI PROGRAMME DASHBOARD — DMIC CORRIDOR — AS AT 28 MARCH 2026
KPI | DMIC-N03 Dholera | DMIC-N04 Shendra | DMIC-N05 Pithampur | DMIC-N07 Greater Noida | DMIC-N08 Surat-Navsari | Programme Total / Avg | Target | RAG
Physical Progress % (AI-Verified) | 54% | 28% | 28% | 72% | 48% | 46% avg | 60% | AMBER
SPI (Schedule Performance Index) | 0.87 | 0.79 | 0.87 | 0.94 | 0.96 | 0.89 avg | ≥ 0.90 | AMBER
CPI (Cost Performance Index) | 0.92 | 0.89 | 0.92 | 0.97 | 0.97 | 0.93 avg | ≥ 0.90 | GREEN
EAC (₹ Cr) | 9,185 | 9,965 | 8,020 | 9,289 | 9,042 | 45,501 total | 44,500 | AMBER
Budget Overrun vs BAC | +₹735 Cr (+8.7%) | + ₹765 Cr (+8.3%) | + ₹220 Cr (+2.8%) | + ₹89 Cr (+1.0%) | + ₹42 Cr (+0.5%) | + ₹1,001 Cr (2.3%) | <5% | AMBER
Open RED Risks | 3 | 6 | 2 | 1 | 0 | 12 total | <8 | GREEN
Pending RA Bills Value | ₹ 71.2 Cr | ₹ 46.8 Cr | ₹ 0 | ₹ 0 | ₹ 0 | ₹ 118 Cr total | < ₹100 Cr | AMBER
Satellite AI vs Contractor Variance | 7% | 12% | 2% | 2% | 2% | 5% avg | < 5% | AMBER
Drawing IFC Completion % | 68% | 42% | 55% | 82% | 74% | 64% avg | 70% | AMBER
Contractor Performance Score (avg) | 76.8 | 58.4 | 81.6 | 88.5 | 90.2 | 79.1 avg | ≥ 80 | AMBER
RFI Ageing > 30 days (count) | 2 | 4 | 0 | 1 | 0 | 7 total | < 5 | AMBER
BG Expiry Alerts within 30 days | 1 | 1 | 1 | 0 | 0 | 3 total | 0 | AMBER
HSE — Zero Harm (LTIs this month) | 0 | 1 | 0 | 0 | 0 | 1 (N04 site) | 0 | RED
WhatsApp MPR Delivery (Days to MD) | Day 8 | Day 10 | Day 9 | Day 7 | Day 8 | 8.4 avg days | ≤ Day 10 | GREEN

## MasterData_OrgUsers
IC-PMS MASTER DATA — ORGANISATION & USER REGISTER ¦ DMIC Programme ¦ Access Control Matrix
User ID | Full Name | Designation | Organisation | Organisation Type | Primary Role (IC-PMS) | Module Access | Corridor Access | Authentication | Email | Status
USR-001 | Rajesh Kumar, IAS | Programme Director | NICDC HQ, New Delhi | Employer | NICDC PMO Director | All Modules (Full) | All Corridors | Aadhaar OTP + NIC SSO + DSC | rajesh.kumar@nicdc.gov.in | Active
USR-002 | Dr. Sunita Patel | Chief Project Manager | NICDC HQ, New Delhi | Employer | NICDC PMO Manager | All Modules (Edit) | All Corridors | Aadhaar OTP + NIC SSO | sunita.patel@nicdc.gov.in | Active
USR-003 | Vikram Mehta | Senior Project Engineer | NICDC DMIC-N03 | Employer | NICDC Site Engineer | M1 M2 M3 M4 M5 (Edit), M6-9 (View) | DMIC-N03 | Aadhaar OTP + NIC SSO | vikram.mehta@nicdc.gov.in | Active
USR-004 | Priya Sharma | SPV Project Manager | DSIR SPV Ltd., Ahmedabad | SPV | SPV Project Manager | M1-M9 (Edit in scope, View others) | DMIC-N03 | Aadhaar OTP + DSC | priya.sharma@dsirspv.in | Active
USR-005 | Rakesh Nair | SPV Finance Officer | DSIR SPV Ltd., Ahmedabad | SPV | SPV Finance Officer | M4 (Full), M5 (View), M9 (View) | DMIC-N03 | Aadhaar OTP | rakesh.nair@dsirspv.in | Active
USR-006 | James Wilson | PMC Project Director | AECOM India Pvt. Ltd., Mumbai | PMC | PMC Project Director | All Modules (Certify) | All DMIC Nodes | DSC Class 3 | james.wilson@aecom.com | Active
USR-007 | Suresh Krishnamurthy | PMC Resident Engineer | AECOM India Pvt. Ltd., Dholera | PMC | PMC Resident Engineer | M1-M8 (Edit/Certify), M9 (View) | DMIC-N03 | Aadhaar OTP | suresh.k@aecom.com | Active
USR-008 | Anita George | PMC Planning Engineer | AECOM India Pvt. Ltd., Dholera | PMC | PMC Planner | M2 (Full), M3 M7 (Edit), Others (View) | DMIC-N03 | Aadhaar OTP | anita.george@aecom.com | Active
USR-009 | Arjun Sharma | Contractor PM — L&T | L&T Construction Ltd., Ahmedabad | EPC Contractor | Contractor PM | M1 M2 (View Own), M4 (Bills Own), M5 (Own), M6 (Own), M8 (Own) | DMIC-N03-P01 | Aadhaar OTP | arjun.sharma@lntecc.com | Active
USR-010 | Rajiv Malhotra | Site Engineer — L&T | L&T Construction Ltd., Dholera | EPC Contractor | Contractor Site Eng. | M2 (Update Own), M8 (Labour/Equip log) | DMIC-N03-P01-WP01 | Aadhaar OTP | rajiv.malhotra@lntecc.com | Active
USR-011 | Kavita Singh | QC Manager — L&T | L&T Construction Ltd., Dholera | EPC Contractor | Contractor QC Mgr. | M6 (Upload Docs Own), M8 (View) | DMIC-N03-P01 | Aadhaar OTP | kavita.singh@lntecc.com | Active
USR-012 | Mohammed Iqbal | PM — SPML Infra | SPML Infra Ltd., Mumbai | EPC Contractor | Contractor PM | M4 (Bills Own), M5 (Own), M8 (Own), M6 (Own) | DMIC-N03-P02 | Aadhaar OTP | m.iqbal@spmlinfra.com | Active
USR-013 | Deepak Rathore | PM — L&T Power | L&T Power Ltd., Mumbai | EPC Contractor | Contractor PM | M4 (Bills Own), M5 (Own), M8 (Own) | DMIC-N03-P03 | Aadhaar OTP | deepak.rathore@ltpower.com | Active
USR-014 | Aisha Kapoor | PM — Sterlite Tech | Sterlite Technologies Ltd., Pune | EPC Contractor | Contractor PM | M4 (Bills Own), M5 (Own), M8 (Own), M6 (Own) | DMIC-N03-P04 | Aadhaar OTP | aisha.kapoor@sterlitetech.com | Active
USR-015 | Robert D'Souza | MD — DMIC-N04 SPV | AURIC SPV Ltd., Aurangabad | SPV | SPV Director | M1-M9 (View + Approve in scope) | DMIC-N04 | DSC Class 3 | robert.dsouza@auricspv.in | Active
USR-016 | Meera Pillai | Finance Director | NICDC Finance, New Delhi | Employer | NICDC Finance Director | M4 (Full), M5 (View), M9 (Full) | All Corridors | DSC Class 3 + Aadhaar | meera.pillai@nicdc.gov.in | Active
USR-017 | Abhijit Saxena | Risk Manager — PMC | AECOM India Pvt. Ltd. | PMC | PMC Risk Manager | M7 (Full), M9 (Edit), Others (View) | All DMIC Nodes | Aadhaar OTP | abhijit.saxena@aecom.com | Active
USR-018 | Gunjan Verma | IT Administrator | NICDC IT Cell, New Delhi | Employer | System Administrator | All Modules (Admin) | All Corridors | NIC SSO + Aadhaar + DSC | gunjan.verma@nicdc.gov.in | Active
USR-019 | Satish Rao | Data Analyst | NICDC PMO, New Delhi | Employer | Analytics Viewer | M9 (Full), All Others (View) | All Corridors | NIC SSO | satish.rao@nicdc.gov.in | Active
USR-020 | External Auditor | Senior Auditor | CAG of India, New Delhi | Government Auditor | Read-Only Auditor | All Modules (View Only, No Edit) | All Corridors | Digital ID issued by audit engagement | cag.auditor@cagindia.gov.in | Temporary — Audit Period

## MasterData_Calendars
IC-PMS MASTER DATA — WORKING CALENDAR MASTER ¦ DMIC Programme Calendars
Calendar Code | Calendar Name | Working Days per Week | Daily Hours | Project Holidays List | Notes
DMIC-6day | DMIC Construction 6-day Calendar | Monday–Saturday | 09:00–18:00 (9 hrs) | Republic Day (26-Jan), Holi, Eid (2 days), Independence Day (15-Aug), Gandhi Jayanti (02-Oct), Diwali (2 days), Christmas (25-Dec) = 8 holidays/year | Primary calendar for all construction packages
DMIC-7day | DMIC 7-day Emergency Calendar | Monday–Sunday | 08:00–18:00 (10 hrs) | None — full year working | For critical path activities with PMC approval. SPI < 0.85 trigger
DMIC-OFFICE | DMIC Office / Admin Calendar | Monday–Friday | 09:30–18:00 (8.5 hrs) | All national + state holidays per MHA list = 14–17/year | For NICDC, PMC, and Admin staff activities
DMIC-NIGHT | DMIC Night Shift Calendar | Monday–Saturday | 21:00–06:00 (9 hrs) | Same as DMIC-6day | Used for critical earthwork, concrete pours, and tunnelling
DMIC-MONSOON | DMIC Monsoon Restricted Calendar (Gujarat) | Monday–Saturday (weather-subject) | 08:00–17:00 (9 hrs) | Standard holidays + 15 monsoon restriction days (Jul–Aug as per site order) | Automatic trigger Jun 15 – Sep 15 for exposed earthwork activities
DMIC-PILOT | DMIC Mechanical/Electrical Testing Calendar | Monday–Saturday | 24 hrs (3 shifts) | None — testing & commissioning period | For HV energisation, WTP commissioning, ICT system testing