## Project Info
PROJECT MANAGEMENT INFORMATION SYSTEM – TEST DATA WORKBOOK
Road Construction Project ¦ NH-48 Widening (Km 145+000 to Km 165+000), Rajasthan
Parameter |  | Details
Project Name |  | 4-Lane Highway Construction – NH-48 (Rajasthan)
Project Code |  | BIPROS/NHAI/RJ/2025/001
Client |  | National Highways Authority of India (NHAI)
Contractor |  | ABC Infracon Pvt. Ltd.
Project Manager |  | Mr. Rajesh Kumar Sharma
Start Date |  | 01-Jan-2025
Planned Completion |  | 31-Dec-2026
Contract Value |  | ₹ 485.60 Crore
Total Length |  | 20.00 km
Project Location |  | Rajasthan State – NH-48 Corridor
PMS Version |  | v1.0 – Test Dataset April 2025
WORKBOOK SHEET INDEX
Sheet No. | Sheet Name |  | Description
1 | Project Info |  | Cover sheet – project metadata & workbook index
2 | Supervisor Daily Rpt |  | Daily executed works, resources, weather, photos & next-day plan
3 | Productivity Norms |  | Activity-wise manpower & equipment productivity norms
4 | Daily Cost Report |  | Supervisor work vs budgeted rates; resource & material costs
5 | BOQ & Budget |  | BOQ rates, budgeted unit rates, resource deployment & variance
6 | Approved Documents |  | Register of approved drawings, specs, method statements, ITP & plans

## Supervisor Daily Rpt
SUPERVISOR DAILY REPORT – Site Execution Log
Project: NH-48 Widening ¦ Contractor: ABC Infracon Pvt. Ltd. ¦ Period: 07-Apr-2025 to 21-Apr-2025
SECTION A – DAILY EXECUTED WORK BY SUPERVISOR
Date | Supervisor Name | Chain-age (km) | Activity | Work Executed (Unit) | Qty Executed | Unit | Cumulative Qty | Remarks
07-Apr-25 | R.K. Verma | 145+000 to 145+500 | Earthwork – Excavation | Cum | 850 | Cum | 850 | Normal progress
07-Apr-25 | R.K. Verma | 145+000 to 145+500 | Embankment Filling | Cum | 620 | Cum | 620 | Soil from borrow area
08-Apr-25 | R.K. Verma | 145+500 to 146+000 | Earthwork – Excavation | Cum | 900 | Cum | 1750 | Good weather
08-Apr-25 | R.K. Verma | 145+500 to 146+000 | Embankment Filling | Cum | 680 | Cum | 1300 | Compaction done 3 passes
09-Apr-25 | S.P. Singh | 146+000 to 146+600 | GSB – Granular Sub-Base | Cum | 480 | Cum | 480 | Quality checked
09-Apr-25 | S.P. Singh | 146+000 to 146+600 | WMM – Wet Mix Macadam | Cum | 320 | Cum | 320 | Lab test passed
10-Apr-25 | S.P. Singh | 146+600 to 147+000 | GSB – Granular Sub-Base | Cum | 390 | Cum | 870 | Slight delay – material
10-Apr-25 | S.P. Singh | 146+600 to 147+000 | WMM – Wet Mix Macadam | Cum | 270 | Cum | 590 | Pending compaction
11-Apr-25 | R.K. Verma | 147+000 to 147+600 | DBM – Dense Bituminous Macadam | MT | 320 | MT | 320 | Temp. 155°C maintained
11-Apr-25 | R.K. Verma | 147+000 to 147+600 | BC – Bituminous Concrete | MT | 180 | MT | 180 | Smooth finish achieved
12-Apr-25 | R.K. Verma | 147+600 to 148+000 | DBM – Dense Bituminous Macadam | MT | 290 | MT | 610 | Good paving conditions
12-Apr-25 | R.K. Verma | 147+600 to 148+000 | BC – Bituminous Concrete | MT | 160 | MT | 340 | Rolling complete
14-Apr-25 | M.D. Rao | 148+000 to 148+500 | Drainage – Catch Water Drain | Rm | 150 | Rm | 150 | RCC work in progress
14-Apr-25 | M.D. Rao | 148+000 to 148+500 | Culvert – Minor Culvert | Each | 2 | Each | 2 | Concreting done
15-Apr-25 | M.D. Rao | 148+500 to 149+000 | Drainage – Catch Water Drain | Rm | 180 | Rm | 330 | Shuttering removed
15-Apr-25 | M.D. Rao | 148+500 to 149+000 | Earthwork – Excavation | Cum | 750 | Cum | 2500 | Catch water drain trench
16-Apr-25 | S.P. Singh | 149+000 to 149+600 | GSB – Granular Sub-Base | Cum | 510 | Cum | 1380 | Material from crusher
17-Apr-25 | S.P. Singh | 149+600 to 150+000 | WMM – Wet Mix Macadam | Cum | 410 | Cum | 1000 | Moisture content OK
18-Apr-25 | R.K. Verma | 150+000 to 150+600 | DBM – Dense Bituminous Macadam | MT | 350 | MT | 960 | Night paving done
21-Apr-25 | R.K. Verma | 150+600 to 151+000 | BC – Bituminous Concrete | MT | 200 | MT | 540 | Final wearing course
SECTION B – DAILY RESOURCE DEPLOYMENT
Date | Resource Type | Resource Description | Nos. Planned | Nos. Deployed | Hours Worked | Idle Hours | Remarks
07-Apr-25 | Manpower | General Labourers | 40 | 38 | 8 | 0 | Full shift
07-Apr-25 | Manpower | Skilled Masons | 8 | 7 | 8 | 0 | 1 absent
07-Apr-25 | Equipment | Excavator (JCB 210) | 4 | 4 | 10 | 0 | All operational
07-Apr-25 | Equipment | Tipper / Dumper (10T) | 12 | 11 | 10 | 1 | 1 under maintenance
08-Apr-25 | Manpower | General Labourers | 40 | 40 | 8 | 0 | Full attendance
08-Apr-25 | Equipment | Compactor (Vibratory Roller) | 3 | 3 | 9 | 0 | Smooth operation
08-Apr-25 | Equipment | Motor Grader | 2 | 2 | 9 | 0 | Levelling complete
09-Apr-25 | Manpower | General Labourers | 40 | 36 | 8 | 0 | 4 on leave
09-Apr-25 | Equipment | Paver Finisher | 1 | 1 | 8 | 0 | GSB laying
09-Apr-25 | Equipment | Wet Mix Plant | 1 | 1 | 10 | 0 | WMM production
10-Apr-25 | Manpower | Skilled Operators | 6 | 5 | 8 | 1 | 1 on training
10-Apr-25 | Equipment | Excavator (JCB 210) | 4 | 3 | 8 | 2 | 1 breakdown – repaired
11-Apr-25 | Manpower | Hot Mix Plant Operators | 5 | 5 | 10 | 0 | Night shift included
11-Apr-25 | Equipment | Sensor Paver | 1 | 1 | 10 | 0 | DBM laying
11-Apr-25 | Equipment | Pneumatic Tyre Roller | 2 | 2 | 9 | 0 | BC compaction
12-Apr-25 | Manpower | General Labourers | 40 | 38 | 8 | 0 | Normal attendance
14-Apr-25 | Manpower | Carpenters / Shuttering | 10 | 10 | 8 | 0 | Culvert formwork
14-Apr-25 | Manpower | Concrete Batching Operators | 4 | 4 | 8 | 0 | Concrete mix M25
14-Apr-25 | Equipment | Concrete Mixer (1 Cum) | 3 | 3 | 8 | 0 | Good output
15-Apr-25 | Equipment | Tipper / Dumper (10T) | 12 | 12 | 10 | 0 | Full utilisation
SECTION C – DAILY WEATHER DATA
Date | Temp Max (°C) | Temp Min (°C) | Rainfall (mm) | Wind Speed (km/h) | Weather Condition | Working Hours | Remarks
07-Apr-25 | 36 | 22 | 0 | 12 | Clear & Sunny | 10 | Good paving weather
08-Apr-25 | 37 | 23 | 0 | 14 | Partly Cloudy | 10 | Suitable for earthwork
09-Apr-25 | 38 | 24 | 0 | 10 | Hot & Sunny | 10 | Bitumen temp monitored
10-Apr-25 | 35 | 22 | 2 | 18 | Overcast | 9 | Slight shower – 1 hr halt
11-Apr-25 | 36 | 21 | 0 | 11 | Clear | 10 | Night work feasible
12-Apr-25 | 37 | 22 | 0 | 13 | Sunny | 10 | All activities normal
14-Apr-25 | 38 | 24 | 0 | 9 | Hot | 10 | Concreting early morning
15-Apr-25 | 36 | 23 | 5 | 20 | Cloudy/Showers | 8 | 2 hr work stoppage
16-Apr-25 | 34 | 21 | 0 | 15 | Clear | 10 | Resumed full work
17-Apr-25 | 37 | 22 | 0 | 12 | Sunny | 10 | Normal
18-Apr-25 | 38 | 23 | 0 | 10 | Clear | 10 | Night paving continued
21-Apr-25 | 39 | 25 | 0 | 8 | Hot & Sunny | 10 | Wearing course complete
SECTION D – NEXT DAY PLAN & CONCERNS / REMARKS
Date | Next Day Activity | Chainagé | Target Qty | Unit | Concerns / Remarks | Action By | Due Date
07-Apr-25 | Continue Excavation + Embankment | 145+500–146+000 | 1600 | Cum | Ensure borrow area vehicles available | Site Engr. | 08-Apr-25
08-Apr-25 | GSB + WMM Laying | 146+000–146+600 | 800 | Cum | Crusher material delivery confirmation needed | Store Keeper | 09-Apr-25
09-Apr-25 | GSB + WMM continued | 146+600–147+000 | 660 | Cum | Compaction roller idle time to be reduced | Plant Incharge | 10-Apr-25
10-Apr-25 | DBM + BC Paving | 147+000–147+600 | 500 | MT | HMP to run overnight to meet targets | HMP Operator | 11-Apr-25
11-Apr-25 | DBM + BC continued | 147+600–148+000 | 450 | MT | Bitumen stock to be checked – min 20 MT | Store Keeper | 12-Apr-25
12-Apr-25 | Culvert + Drain work | 148+000–148+500 | 2 nos. | Each/Rm | Formwork to be readied by 0700 hrs | Carpenter | 14-Apr-25
14-Apr-25 | Culvert + Drainage | 148+500–149+000 | 330 | Rm | Concrete curing compound required | QC Engineer | 15-Apr-25
15-Apr-25 | GSB Laying | 149+000–149+600 | 510 | Cum | Rain forecast – have backup activity ready | Supervisor | 16-Apr-25
16-Apr-25 | WMM Laying | 149+600–150+000 | 410 | Cum | Moisture optimum to be checked before rolling | Lab Technician | 17-Apr-25
17-Apr-25 | DBM Night Paving | 150+000–150+600 | 350 | MT | Generator backup for night lighting required | Electrician | 18-Apr-25
18-Apr-25 | BC – Wearing Course | 150+600–151+000 | 200 | MT | Final level survey before paving | Survey Team | 21-Apr-25

## Productivity Norms
PRODUCTIVITY NORMS – Manpower & Equipment ¦ NH-48 Widening Project
SECTION A – MANPOWER PRODUCTIVITY NORMS (Activity-wise)
S.No. | Activity | Unit of Measurement | Output per Man per Day | No. of Men Required | Gang Output per Day | Remarks
1 | Earthwork – Excavation (Soft Rock) | Cum | 2.5 | 20 | 50 | Manual with mechanical support
2 | Earthwork – Excavation (Hard Rock) | Cum | 1.2 | 30 | 36 | Blasting + manual
3 | Embankment Filling & Compaction | Cum | 4 | 15 | 60 | Dozer + tipper gang
4 | GSB (Granular Sub-Base) Laying | Cum | 5 | 12 | 60 | Includes spreading & compaction
5 | WMM (Wet Mix Macadam) Laying | Cum | 4.5 | 14 | 63 | Paver + roller gang
6 | DBM (Dense Bituminous Macadam) | MT | 6 | 10 | 60 | HMP + paver + 2 rollers
7 | BC (Bituminous Concrete) | MT | 5 | 10 | 50 | Final wearing course
8 | Concrete – M25 (RCC Works) | Cum | 1.5 | 20 | 30 | Batching plant based
9 | Concrete – M30 (Culvert / Bridge) | Cum | 1.2 | 22 | 26 | Includes formwork gang
10 | Catch Water Drain (Stone Masonry) | Rm | 3 | 8 | 24 | Including mortar mix
11 | Pipe Culvert Installation | Each | 1 | 12 | 12 | 900mm dia NP3 pipe
12 | Road Marking (Thermoplastic) | Rm | 80 | 4 | 320 | Machine applied
13 | Sign Board Installation | Each | 2 | 6 | 12 | Including foundation
14 | Kerb Stone Laying | Rm | 15 | 5 | 75 | Pre-cast kerb
SECTION B – EQUIPMENT PRODUCTIVITY NORMS (Activity-wise)
S.No. | Equipment Type | Capacity / Specification | Activity | Unit | Output per Hour | Working Hrs/Day | Output per Day | Fuel Consumption (Ltrs/Hr) | Remarks
1 | Excavator | JCB 210 (1.0 Cum Bucket) | Excavation (Soft Soil) | Cum | 80 | 10 | 800 | 18 | Including cycle time
2 | Excavator | JCB 210 (1.0 Cum Bucket) | Excavation (Hard Rock) | Cum | 30 | 10 | 300 | 20 | Blasting support needed
3 | Tipper / Dumper | 10T Capacity | Earth Transport (2 km) | Cum | 15 | 10 | 150 | 8 | Per vehicle
4 | Motor Grader | 135 HP | Surface Levelling | Sqm | 1200 | 9 | 10800 | 14 | Embankment shaping
5 | Vibratory Roller | 10T Static Weight | Compaction (Earthwork) | Sqm | 900 | 9 | 8100 | 12 | 4 passes required
6 | Vibratory Roller | 10T Static Weight | Compaction (GSB/WMM) | Sqm | 1000 | 9 | 9000 | 12 | 3 passes
7 | Pneumatic Tyre Roller | 8T | Compaction (Bituminous) | Sqm | 1100 | 9 | 9900 | 10 | DBM/BC
8 | Wet Mix Plant | 60 TPH | WMM Production | MT | 55 | 9 | 495 | 35 | Including water addition
9 | Paver Finisher | Sensor Paver (5m) | WMM / GSB Laying | Sqm | 500 | 9 | 4500 | 14 | Good output
10 | Hot Mix Plant | 60 TPH | DBM / BC Production | MT | 55 | 10 | 550 | 40 | Drum type
11 | Asphalt Sensor Paver | 5.5m Width | DBM / BC Laying | MT | 60 | 10 | 600 | 18 | Temperature 145–155°C
12 | Concrete Batching Plant | 30 CumM/Hr | RCC Works | Cum | 25 | 8 | 200 | 28 | Including water & admixture
13 | Concrete Transit Mixer | 6 Cum | Concrete Transport | Cum | 18 | 8 | 144 | 7 | Per vehicle
14 | Backhoe Loader | 1.0 Cum | Drain Excavation | Cum | 60 | 9 | 540 | 16 | Narrow trench work
15 | Crane (Mobile) | 30T Capacity | Culvert Pipe Laying | Each | 4 | 8 | 32 | 22 | Including slings & rigging
SECTION C – RESOURCE DEPLOYMENT MATRIX (Weekly)
Resource Type | Resource Name | Qty Available | Week 1 (7–11 Apr) | Week 2 (14–18 Apr) | Week 3 (21–25 Apr) | Total Days | Utilisation % | Remarks
Manpower | General Labourers | 40 | 38 | 37 | 39 | 114 | 19% | High availability
Manpower | Skilled Operators | 8 | 7 | 8 | 8 | 23 | 19.17% | Good utilisation
Manpower | Supervisors | 3 | 3 | 3 | 3 | 9 | 20% | Full deployment
Manpower | Engineers (Site) | 4 | 4 | 4 | 4 | 12 | 20% | Full deployment
Equipment | Excavator JCB 210 | 4 | 4 | 3 | 4 | 11 | 18.33% | 1 breakdown on Apr 10
Equipment | Tipper / Dumper 10T | 12 | 11 | 12 | 12 | 35 | 19.44% | 1 maintenance – Apr 7
Equipment | Motor Grader | 2 | 2 | 2 | 2 | 6 | 20% | Fully utilised
Equipment | Vibratory Roller | 3 | 3 | 3 | 3 | 9 | 20% | Compaction as planned
Equipment | Paver Finisher | 1 | 1 | 1 | 1 | 3 | 20% | Continuous deployment
Equipment | Hot Mix Plant | 1 | 1 | 1 | 1 | 3 | 20% | Night ops week 2
Equipment | Concrete Batching Plant | 1 | 0 | 1 | 1 | 2 | 13.33% | Idle in week 1
Equipment | Concrete Transit Mixer | 3 | 0 | 3 | 3 | 6 | 13.33% | Culvert work week 2+
Material | Bitumen VG-30 (MT) | 200 | 85 | 90 | 0 | 175 | 5.833% | Adequate stock
Material | Aggregate (Cum) | 500 | 180 | 190 | 0 | 370 | 4.933% | Crusher supply
Material | Cement (Bags) | 2000 | 0 | 800 | 0 | 800 | 2.667% | For culvert works

## Daily Cost Report
DAILY COST REPORT – Supervisor Execution vs Budgeted Unit Rates
Project: NH-48 Widening ¦ Period: 07-Apr-2025 to 21-Apr-2025 ¦ All rates in ₹
SECTION A – UNIT RATE MASTER (Equipment / Manpower / Material / Sub-Contract)
S.No. | Resource Category | Resource Description | Unit | Budgeted Rate (₹) | Actual Rate (₹) | Variance (₹) | Variance % | Remarks
1 | Equipment | Excavator (JCB 210) | Hour | 1800 | 1850 | 50 | 2.778% | Over budget
2 | Equipment | Tipper / Dumper 10T | Hour | 900 | 880 | -20 | -2.222% | Under budget
3 | Equipment | Motor Grader 135HP | Hour | 2200 | 2250 | 50 | 2.273% | Over budget
4 | Equipment | Vibratory Roller 10T | Hour | 1600 | 1580 | -20 | -1.25% | Under budget
5 | Equipment | Paver Finisher (Sensor) | Hour | 3500 | 3600 | 100 | 2.857% | Over budget
6 | Equipment | Hot Mix Plant 60 TPH | Hour | 4200 | 4150 | -50 | -1.19% | Under budget
7 | Equipment | Concrete Batching Plant | Hour | 3000 | 3050 | 50 | 1.667% | Over budget
8 | Manpower | General Labourer | Day | 450 | 470 | 20 | 4.444% | Over budget
9 | Manpower | Skilled Mason | Day | 750 | 760 | 10 | 1.333% | Over budget
10 | Manpower | Equipment Operator | Day | 900 | 920 | 20 | 2.222% | Over budget
11 | Manpower | Supervisor | Day | 1800 | 1800 | 0 | 0% | On budget
12 | Manpower | Site Engineer | Day | 3500 | 3500 | 0 | 0% | On budget
13 | Material | Bitumen VG-30 | MT | 62000 | 63500 | 1500 | 2.419% | Over budget
14 | Material | Aggregate (20mm) | Cum | 1400 | 1420 | 20 | 1.429% | Over budget
15 | Material | Aggregate (10mm) | Cum | 1600 | 1650 | 50 | 3.125% | Over budget
16 | Material | Sand (Fine) | Cum | 1200 | 1180 | -20 | -1.667% | Under budget
17 | Material | Cement OPC 43 | Bag | 380 | 395 | 15 | 3.947% | Over budget
18 | Material | GSB Material | Cum | 800 | 810 | 10 | 1.25% | Over budget
19 | Material | WMM Aggregate | Cum | 900 | 920 | 20 | 2.222% | Over budget
20 | Sub-Contract | Earthwork Excavation | Cum | 180 | 185 | 5 | 2.778% | Over budget
21 | Sub-Contract | Embankment Compaction | Cum | 120 | 118 | -2 | -1.667% | Under budget
22 | Sub-Contract | Road Marking | Rm | 450 | 450 | 0 | 0% | On budget
23 | Sub-Contract | Concrete Culvert | Cum | 8500 | 8600 | 100 | 1.176% | Over budget
SECTION B – DAILY WORK EXECUTED vs BUDGETED COST
Date | Activity | Qty Executed | Unit | Budgeted Unit Rate (₹) | Actual Unit Rate (₹) | Budgeted Cost (₹) | Actual Cost (₹) | Variance (₹) | Variance % | Supervisor
07-Apr-25 | Earthwork – Excavation | 850 | Cum | 180 | 185 | 153000 | 157250 | 4250 | 2.778% | R.K. Verma
07-Apr-25 | Embankment Filling | 620 | Cum | 120 | 118 | 74400 | 73160 | -1240 | -1.667% | R.K. Verma
08-Apr-25 | Earthwork – Excavation | 900 | Cum | 180 | 185 | 162000 | 166500 | 4500 | 2.778% | R.K. Verma
08-Apr-25 | Embankment Filling | 680 | Cum | 120 | 118 | 81600 | 80240 | -1360 | -1.667% | R.K. Verma
09-Apr-25 | GSB – Granular Sub-Base | 480 | Cum | 800 | 810 | 384000 | 388800 | 4800 | 1.25% | S.P. Singh
09-Apr-25 | WMM – Wet Mix Macadam | 320 | Cum | 900 | 920 | 288000 | 294400 | 6400 | 2.222% | S.P. Singh
10-Apr-25 | GSB – Granular Sub-Base | 390 | Cum | 800 | 810 | 312000 | 315900 | 3900 | 1.25% | S.P. Singh
10-Apr-25 | WMM – Wet Mix Macadam | 270 | Cum | 900 | 920 | 243000 | 248400 | 5400 | 2.222% | S.P. Singh
11-Apr-25 | DBM – Dense Bituminous Macadam | 320 | MT | 4500 | 4620 | 1440000 | 1478400 | 38400 | 2.667% | R.K. Verma
11-Apr-25 | BC – Bituminous Concrete | 180 | MT | 5200 | 5320 | 936000 | 957600 | 21600 | 2.308% | R.K. Verma
12-Apr-25 | DBM – Dense Bituminous Macadam | 290 | MT | 4500 | 4620 | 1305000 | 1339800 | 34800 | 2.667% | R.K. Verma
12-Apr-25 | BC – Bituminous Concrete | 160 | MT | 5200 | 5320 | 832000 | 851200 | 19200 | 2.308% | R.K. Verma
14-Apr-25 | Drainage – CWD (Stone Masonry) | 150 | Rm | 2800 | 2820 | 420000 | 423000 | 3000 | 0.7143% | M.D. Rao
14-Apr-25 | Culvert – Minor | 2 | Each | 85000 | 87500 | 170000 | 175000 | 5000 | 2.941% | M.D. Rao
15-Apr-25 | Drainage – CWD | 180 | Rm | 2800 | 2820 | 504000 | 507600 | 3600 | 0.7143% | M.D. Rao
15-Apr-25 | Earthwork – Excavation | 750 | Cum | 180 | 185 | 135000 | 138750 | 3750 | 2.778% | M.D. Rao
16-Apr-25 | GSB – Granular Sub-Base | 510 | Cum | 800 | 810 | 408000 | 413100 | 5100 | 1.25% | S.P. Singh
17-Apr-25 | WMM – Wet Mix Macadam | 410 | Cum | 900 | 920 | 369000 | 377200 | 8200 | 2.222% | S.P. Singh
18-Apr-25 | DBM – Dense Bituminous Macadam | 350 | MT | 4500 | 4620 | 1575000 | 1617000 | 42000 | 2.667% | R.K. Verma
21-Apr-25 | BC – Bituminous Concrete | 200 | MT | 5200 | 5320 | 1040000 | 1064000 | 24000 | 2.308% | R.K. Verma
PERIOD TOTAL | [5 empty] | 10832000 | 11067300 | 235300 | 2.172%
SECTION C – MATERIAL CONSUMPTION (By Supervisor / Store Keeper)
Date | Material Description | Unit | Opening Stock | Received | Consumed | Closing Stock | Wastage % | Issued By | Received By
07-Apr-25 | Aggregate (20mm) | Cum | 120 | 50 | 45 | 125 | 50% | R.K. Verma | Store – Ajay
08-Apr-25 | Aggregate (20mm) | Cum | 125 | 60 | 55 | 130 | 30% | R.K. Verma | Store – Ajay
09-Apr-25 | GSB Material | Cum | 200 | 100 | 90 | 210 | 40% | S.P. Singh | Store – Ajay
09-Apr-25 | Aggregate (10mm) | Cum | 80 | 40 | 38 | 82 | 20% | S.P. Singh | Store – Ajay
10-Apr-25 | GSB Material | Cum | 210 | 80 | 75 | 215 | 30% | S.P. Singh | Store – Ajay
10-Apr-25 | WMM Aggregate | Cum | 150 | 60 | 55 | 155 | 40% | S.P. Singh | Store – Ajay
11-Apr-25 | Bitumen VG-30 | MT | 40 | 20 | 18 | 42 | 50% | R.K. Verma | Store – Pradeep
11-Apr-25 | Aggregate (20mm) | Cum | 130 | 50 | 47 | 133 | 30% | R.K. Verma | Store – Ajay
12-Apr-25 | Bitumen VG-30 | MT | 42 | 15 | 16 | 41 | 20% | R.K. Verma | Store – Pradeep
14-Apr-25 | Cement OPC 43 | Bag | 500 | 200 | 180 | 520 | 40% | M.D. Rao | Store – Pradeep
14-Apr-25 | Sand (Fine) | Cum | 60 | 20 | 18 | 62 | 30% | M.D. Rao | Store – Ajay
15-Apr-25 | Cement OPC 43 | Bag | 520 | 100 | 95 | 525 | 20% | M.D. Rao | Store – Pradeep
16-Apr-25 | GSB Material | Cum | 215 | 100 | 95 | 220 | 40% | S.P. Singh | Store – Ajay
17-Apr-25 | WMM Aggregate | Cum | 155 | 80 | 78 | 157 | 30% | S.P. Singh | Store – Ajay
18-Apr-25 | Bitumen VG-30 | MT | 41 | 25 | 22 | 44 | 50% | R.K. Verma | Store – Pradeep
21-Apr-25 | Bitumen VG-30 | MT | 44 | 20 | 18 | 46 | 40% | R.K. Verma | Store – Pradeep

## BOQ & Budget
BOQ & BUDGET – Rates, Resource Deployment & Variance Analysis
BOQ ITEM REGISTER – Rates & Budget vs Actual
Item No. | Description of Work | Unit | BOQ Qty | BOQ Rate (₹) | BOQ Amount (₹) | Budgeted Unit Rate (₹) | Budgeted Amount (₹) | Qty Executed (to date) | Actual Unit Rate (₹) | Actual Amount (₹) | % Work Complete | Cost Variance (₹) | Var %
1.1 | Earthwork – Excavation in all types of soil | Cum | 45000 | 175 | 7875000 | 180 | 8100000 | 5950 | 185 | 1100750 | 13.22% | -6999250 | -86.41%
1.2 | Earthwork – Embankment & Compaction | Cum | 38000 | 115 | 4370000 | 120 | 4560000 | 4100 | 118 | 483800 | 10.79% | -4076200 | -89.39%
2.1 | GSB – Granular Sub-Base (150mm) | Cum | 9500 | 780 | 7410000 | 800 | 7600000 | 1380 | 810 | 1117800 | 14.53% | -6482200 | -85.29%
2.2 | WMM – Wet Mix Macadam (250mm) | Cum | 7200 | 880 | 6336000 | 900 | 6480000 | 1000 | 920 | 920000 | 13.89% | -5560000 | -85.8%
3.1 | DBM – Dense Bituminous Macadam (50mm) | MT | 5800 | 4400 | 25520000 | 4500 | 26100000 | 960 | 4620 | 4435200 | 16.55% | -21664800 | -83.01%
3.2 | BC – Bituminous Concrete (40mm) | MT | 4200 | 5100 | 21420000 | 5200 | 21840000 | 540 | 5320 | 2872800 | 12.86% | -18967200 | -86.85%
4.1 | Catch Water Drain – Stone Masonry | Rm | 3600 | 2750 | 9900000 | 2800 | 10080000 | 330 | 2820 | 930600 | 9.167% | -9149400 | -90.77%
4.2 | Box Culvert – RCC M25 | Cum | 480 | 8200 | 3936000 | 8500 | 4080000 | 0 | 8600 | 0 | 0% | -4080000 | -100%
4.3 | Pipe Culvert – NP3 900mm | Each | 36 | 82000 | 2952000 | 85000 | 3060000 | 2 | 87500 | 175000 | 5.556% | -2885000 | -94.28%
5.1 | Road Marking – Thermoplastic | Rm | 22000 | 440 | 9680000 | 450 | 9900000 | 0 | 450 | 0 | 0% | -9900000 | -100%
5.2 | Sign Boards – Retro-reflective | Each | 180 | 18500 | 3330000 | 19000 | 3420000 | 0 | 19200 | 0 | 0% | -3420000 | -100%
5.3 | Kerb Stone Laying | Rm | 8400 | 340 | 2856000 | 350 | 2940000 | 0 | 355 | 0 | 0% | -2940000 | -100%
6.1 | Bridge – RCC M30 Substructure | Cum | 1200 | 12500 | 15000000 | 13000 | 15600000 | 0 | 13200 | 0 | 0% | -15600000 | -100%
6.2 | Bridge – Superstructure (PSC Girder) | Rm | 480 | 185000 | 88800000 | 190000 | 91200000 | 0 | 192000 | 0 | 0% | -91200000 | -100%
7.1 | Miscellaneous & Provisional | LS | 1 | 8500000 | 8500000 | 8500000 | 8500000 | 1 | 8500000 | 8500000 | 100% | 0 | 0%
GRAND TOTAL |  |  |  |  | 217885000 |  | 223460000 |  |  | 20535950 |  | -202924050

## Approved Documents
APPROVED DOCUMENTS REGISTER – Drawings, Specifications, Method Statements, ITP & Project Plans
Doc No. | Document Title | Category | Rev. | Date of Approval | Approved By | Applicable Work Items | Status | Reference Spec / Clause | Remarks
DRG/NH48/001 | General Arrangement – Road Cross Section | Drawing | R2 | 15-Jan-25 | Client – NHAI | All Road Works | Approved | MoRTH Sec 300 | 4-lane divided carriageway
DRG/NH48/002 | Pavement Design – Flexible Pavement | Drawing | R1 | 15-Jan-25 | Client – NHAI | DBM, BC, WMM, GSB | Approved | IRC:37-2018 | Design CBR 8%
DRG/NH48/003 | Culvert Layout – Box & Pipe Culverts | Drawing | R1 | 20-Jan-25 | Client – NHAI | Culvert Works | Approved | IRC:SP:13 | Minor culverts CH 148
DRG/NH48/004 | Drainage – Catch Water Drain Details | Drawing | R0 | 20-Jan-25 | Client – NHAI | CWD, Drain | Approved | MoRTH Sec 309 | Stone masonry
DRG/NH48/005 | Bridge GAD – CH 152+400 | Drawing | R1 | 01-Feb-25 | Client – NHAI | Bridge Works | Approved | IRC:6, IRC:112 | PSC T-Girder
DRG/NH48/006 | Typical Embankment Cross Section | Drawing | R0 | 15-Jan-25 | Client – NHAI | Earthwork | Approved | MoRTH Sec 305 | Borrow area from km 148
DRG/NH48/007 | Road Signage & Marking Layout | Drawing | R0 | 10-Feb-25 | Client – NHAI | Road Marking, Signs | Approved | IRC:67-2012 | Thermoplastic paint
SPEC/NH48/001 | Technical Specifications – Earthwork | Specification | R1 | 10-Jan-25 | Client – NHAI | Excavation, Embankment | Approved | MoRTH-5th Rev Sec 300-305 | Compaction 98% MDD
SPEC/NH48/002 | Technical Specifications – Sub-base & Base | Specification | R1 | 10-Jan-25 | Client – NHAI | GSB, WMM | Approved | MoRTH Sec 401-406 | Grading III for GSB
SPEC/NH48/003 | Technical Specifications – Bituminous Layers | Specification | R1 | 12-Jan-25 | Client – NHAI | DBM, BC | Approved | MoRTH Sec 507, 509 | VG-30 Bitumen
SPEC/NH48/004 | Technical Specifications – Concrete Works | Specification | R0 | 15-Jan-25 | Client – NHAI | RCC, PCC | Approved | IS 456:2000 / IRC:112 | M25, M30 grades
SPEC/NH48/005 | Technical Specifications – Drainage | Specification | R0 | 20-Jan-25 | Client – NHAI | CWD, Culverts | Approved | MoRTH Sec 309 | Stone masonry CM 1:4
MS/NH48/001 | Method Statement – Earthwork Excavation & Filling | Method Statement | R1 | 20-Feb-25 | QA/QC Head | Excavation, Embankment | Approved | MoRTH Sec 300-305 | Approved by IE
MS/NH48/002 | Method Statement – GSB & WMM Construction | Method Statement | R0 | 20-Feb-25 | QA/QC Head | GSB, WMM | Approved | MoRTH Sec 401 | Paver laying method
MS/NH48/003 | Method Statement – Bituminous Paving (DBM/BC) | Method Statement | R1 | 25-Feb-25 | QA/QC Head | DBM, BC | Approved | MoRTH Sec 507-509 | HMP temp control
MS/NH48/004 | Method Statement – Concrete Works (Culvert) | Method Statement | R0 | 01-Mar-25 | QA/QC Head | Culverts, RCC | Approved | IS 456:2000 | Curing regime 28 days
MS/NH48/005 | Method Statement – Blasting (Hard Rock) | Method Statement | R0 | 10-Mar-25 | QA/QC Head + Safety Mgr | Excavation (Rock) | Approved | Explosives Act 1884 | DGMS compliant
ITP/NH48/001 | Inspection & Test Plan – Earthwork | ITP | R1 | 05-Mar-25 | IE + Client | Excavation, Embankment | Approved | MoRTH + IS 2720 | Field density test per 1000 sqm
ITP/NH48/002 | Inspection & Test Plan – GSB & WMM | ITP | R1 | 05-Mar-25 | IE + Client | GSB, WMM | Approved | MORTH Sec 401-406 | Grading & compaction tests
ITP/NH48/003 | Inspection & Test Plan – Bituminous Works | ITP | R0 | 07-Mar-25 | IE + Client | DBM, BC | Approved | MoRTH Sec 507-509 | Core cutting per 500m
ITP/NH48/004 | Inspection & Test Plan – Concrete Works | ITP | R0 | 10-Mar-25 | IE + Client | Culvert, RCC | Approved | IS 456 + IRC:112 | Slump, cube test per 30 Cum
ITP/NH48/005 | Inspection & Test Plan – Bridge Works | ITP | R0 | 15-Mar-25 | IE + Client | Bridge Sub/Super Structure | Approved | IRC:6, IRC:112 | NDT, load testing
PLAN/NH48/001 | Master Construction Programme (Level 3) | Project Plan | R2 | 01-Jan-25 | PM + Client | All Works | Approved | Contract Clause 8.3 | Primavera P6 baseline
PLAN/NH48/002 | Monthly Work Programme – April 2025 | Project Plan | R0 | 01-Apr-25 | Site PM | Earthwork, GSB, DBM, BC | Approved | Internal | Monthly target 8 km
PLAN/NH48/003 | Resource Mobilisation Plan | Project Plan | R1 | 15-Jan-25 | PM | All Resources | Approved | Contract Schedule | Equipment & manpower
PLAN/NH48/004 | QA/QC Plan (Project Quality Plan) | Project Plan | R1 | 20-Jan-25 | QA/QC Manager + IE | All Works | Approved | ISO 9001:2015 | Annual internal audit
PLAN/NH48/005 | Health Safety & Environment Plan | Project Plan | R1 | 20-Jan-25 | Safety Manager + IE | All Works | Approved | OHSAS 45001 | Monthly safety meeting
PLAN/NH48/006 | Traffic Management Plan | Project Plan | R0 | 01-Feb-25 | Site PM + Traffic Consultant | All Works | Approved | IRC:SP:55 | Signed IRC scheme