RISK MASTER METADATA

Large-Scale Road Construction Project

National Highway Infrastructure | NHAI / EPC Contractor Framework

| Project | NH-48 Highway Widening — Rajasthan Corridor |
| --- | --- |
| Client | National Highways Authority of India (NHAI) |
| Contractor | ABC Infracon Pvt. Ltd. |
| Document Type | Risk Master Metadata & Mitigation Framework |
| Version | v1.0 — April 2025 |
| Classification | Project Confidential |

# 1. Introduction & Purpose

This Risk Master Metadata document establishes a comprehensive framework for identifying, classifying, assessing, and mitigating risks associated with large-scale road construction projects. The document is structured to serve as a master reference for Project Management Consultants (PMC), NHAI supervision teams, EPC contractors, and project financiers.

The framework aligns with:

- IS 15883 (Project Risk Management Guidelines)

- NHAI EPC Contract Conditions — Clause 19 (Force Majeure) and Clause 21 (Risk Allocation)

- World Bank Operational Policy OP 4.01 for Environmental Assessment

- IRC:SP:84 — Manual on Operation & Maintenance of NH Roads

- MOSRT&H Standard Bidding Documents for EPC Contracts

Risk management is an iterative and continuous process spanning all project phases — from pre-construction through commissioning and the defects liability period. This document defines the complete metadata schema, risk categories, risk register structure, and mitigation plans for each risk type.

# 2. Risk Master Metadata Schema

The Risk Master Metadata schema captures all attributes necessary for full lifecycle management of a project risk. The schema is divided into six logical groups.

### 2.1 Risk Identification

| Field Name | Description | Data Type / Format | Example Values |
| --- | --- | --- | --- |
| risk_id | Unique system-generated identifier | VARCHAR(20) | RK-2025-001 |
| risk_title | Short, descriptive risk name | VARCHAR(150) | Monsoon Delay Risk |
| risk_description | Detailed narrative of the risk event and potential impact | TEXT | Extended rainfall causing stoppage of earthwork and subgrade preparation |
| risk_category | Top-level classification of risk type | ENUM | Technical / Financial / Environmental / Legal / Force Majeure |
| risk_sub_category | Granular risk type within category | VARCHAR(100) | Geotechnical / Utility Conflict / Land Acquisition |
| risk_source | Point of origin of the risk | ENUM | Design / Contractor / Regulatory / External / Client |
| work_package_id | Linked WBS element identifier | VARCHAR(30) | WP-04 (Earthwork) |
| chainage_from | Start chainage of affected road stretch | DECIMAL | 142+000 |
| chainage_to | End chainage of affected road stretch | DECIMAL | 155+000 |
| project_phase | Phase during which risk may be realized | ENUM | Pre-Construction / Construction / Commissioning / DLP |

### 2.2 Risk Assessment

| Field Name | Description | Data Type / Format | Example Values |
| --- | --- | --- | --- |
| probability_score | Likelihood of risk occurrence on a 1–5 scale | INT (1–5) | 3 — Possible |
| impact_score | Severity of consequence on a 1–5 scale | INT (1–5) | 4 — Major |
| risk_rating | Composite P×I matrix result | ENUM | Critical / High / Medium / Low |
| cost_impact_inr | Estimated financial exposure in Indian Rupees | DECIMAL | 45,00,000 |
| schedule_impact_days | Estimated delay in working days | INT | 21 days |
| quality_impact_flag | Boolean flag for quality consequence | BOOLEAN + TEXT | Yes — Sub-grade compaction failure |
| safety_impact_level | HSE consequence level | ENUM | Fatality / Injury / Near Miss / None |
| risk_score_composite | Calculated risk score (P × I) | INT (1–25) | 12 |

### 2.3 Risk Ownership & Lifecycle

| Field Name | Description | Data Type / Format | Example Values |
| --- | --- | --- | --- |
| risk_owner_id | FK to project personnel — responsible for mitigation | FK → Personnel | ENG-047 (Site Engineer) |
| risk_raised_by | Person or team who identified the risk | VARCHAR(100) | PMC Inspection Team |
| raised_date | Date risk was first logged | DATE | 2025-03-15 |
| review_date | Next scheduled review date | DATE | 2025-04-15 |
| closure_date | Date when risk was resolved or formally closed | DATE | NULL (Open) |
| risk_status | Current lifecycle state of the risk | ENUM | Open / Monitoring / Escalated / Closed / Realized |
| is_realized | Boolean — has the risk become an actual issue? | BOOLEAN | FALSE |
| linked_issue_id | FK to Issue Register if risk is realized | FK → Issues | ISS-2025-012 |

### 2.4 Mitigation & Response

| Field Name | Description | Data Type / Format | Example Values |
| --- | --- | --- | --- |
| response_strategy | Primary risk treatment approach | ENUM | Avoid / Mitigate / Transfer / Accept |
| mitigation_action | Specific action plan to reduce probability or impact | TEXT | Pre-position dewatering pumps before monsoon onset; build drainage channels |
| contingency_plan | Fallback action if risk is triggered despite mitigation | TEXT | Activate extended night-shift schedule; deploy reserve plant |
| residual_risk_rating | Post-mitigation risk rating | ENUM | Medium |
| mitigation_cost_inr | Estimated cost of implementing mitigation measures | DECIMAL | 8,00,000 |
| insurance_applicable | Whether risk is transferable via insurance/bond | BOOLEAN | Yes — CAR Policy |
| contract_clause_ref | Relevant NHAI/EPC contract clause reference | VARCHAR(50) | Clause 19.4 — Force Majeure |

### 2.5 Classification Tags

| Field Name | Description | Data Type / Format | Example Values |
| --- | --- | --- | --- |
| risk_type | Nature of the risk | ENUM | Pure / Speculative |
| trigger_event | Specific event or condition that activates the risk | TEXT | IMD forecast: rainfall > 50mm in 24 hrs |
| early_warning_indicator | Leading signal to monitor proactively | TEXT | Weekly soil moisture readings; IMD 5-day forecast |
| affected_stakeholder | Primary stakeholder impacted | MULTI-SELECT | Contractor / NHAI / Environment / Public / Subcontractor |
| escalation_level | Level at which risk must be escalated | ENUM | Site / PMC / NHAI RO / NHAI HQ |
| is_critical_path_risk | Boolean — does risk affect critical path activity? | BOOLEAN | TRUE |
| risk_zone | Geographic/administrative zone of the project affected | VARCHAR(100) | Zone B — Ajmer District |

### 2.6 Audit & Compliance

| Field Name | Description | Data Type / Format | Example Values |
| --- | --- | --- | --- |
| created_by | User who created the risk record | VARCHAR(100) | PMC Risk Manager |
| created_at | Timestamp of creation | DATETIME | 2025-03-15T09:30:00 |
| last_updated_by | Last person to modify the record | VARCHAR(100) | Project Director |
| last_updated_at | Timestamp of last update | DATETIME | 2025-03-28T14:00:00 |
| version_number | Revision number of the risk record | INT | 3 |
| approval_status | Current approval workflow status | ENUM | Draft / Under Review / Approved / Archived |
| approved_by | Name/ID of approving authority | VARCHAR(100) | DGM — Project Management, NHAI |

# 3. Risk Probability × Impact Matrix

The 5×5 Probability-Impact Matrix below is used to calculate the composite Risk Score. Scores are colour-coded to indicate risk severity and required escalation level.

| Probability \ Impact | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic |
| --- | --- | --- | --- | --- | --- |
| 5 — Almost Certain | 5 | 10 | 15 | 20 | 25 |
| 4 — Likely | 4 | 8 | 12 | 16 | 20 |
| 3 — Possible | 3 | 6 | 9 | 12 | 15 |
| 2 — Unlikely | 2 | 4 | 6 | 8 | 10 |
| 1 — Rare | 1 | 2 | 3 | 4 | 5 |

| Score Range | Rating | Escalation Level | Review Frequency |
| --- | --- | --- | --- |
| 20 – 25 | CRITICAL | NHAI HQ / MD | Daily |
| 12 – 19 | HIGH | PMC / NHAI RO | Weekly |
| 6 – 11 | MEDIUM | Site / PMC | Fortnightly |
| 1 – 5 | LOW | Site Engineer | Monthly |

# 4. Risk Categories, Register & Mitigation Plans

This section provides a detailed breakdown of each risk category, including individual risks with their probability/impact ratings, and comprehensive risk mitigation plans covering strategy, action, ownership, and timeline.

## 4.1 Land Acquisition & Utility Shifting Risks

Land acquisition delays and utility conflicts are the most common causes of cost overrun and schedule slippage in Indian NH projects. Forest and Revenue land involvement, ROW encroachments, and underground utilities create compounding delays.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-LA-01 | Delayed Handover of Right-of-Way (ROW) | 4 / 5 | 5 / 5 | ₹1.5 Cr / month delay | 60–120 days | CRITICAL | Construction |
| RK-LA-02 | Encroachment by Structures / Jhuggi Settlements | 3 / 5 | 4 / 5 | ₹30–60 Lakhs | 30–60 days | HIGH | Construction |
| RK-LA-03 | Underground Utility Conflict (OFC, Pipeline, HT Cable) | 4 / 5 | 4 / 5 | ₹20–80 Lakhs | 15–45 days | HIGH | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Avoid | Prioritize ROW clearance verification before mobilization. Conduct drone-based ROW survey in pre-construction phase. | PMC / NHAI RO | Pre-Construction |
| Mitigate | Engage District Collector and SDM for expedited LA proceedings under RFCTLARR Act 2013. Issue Section 3A notifications with adequate lead time. | NHAI Project Director | Month 1–3 |
| Transfer | Include utility shifting as a NHAI-borne obligation in the EPC contract. Engage BSNL/PGCIL/GAIL for advance shifting agreements. | NHAI Authority Engineer | Pre-Award |
| Contingency | Re-sequence construction to work in cleared stretches first. Maintain alternate work fronts. Invoke EOT provisions under Clause 40. | EPC Contractor | On Trigger |

Early Warning Indicators:

- Less than 80% ROW cleared at mobilization minus 30 days

- More than 3 utility conflicts per km unresolved

- Any litigation filed against LA award

## 4.2 Geological & Geotechnical Risks

Subsurface conditions different from those assumed during design are a perennial risk in NH projects, particularly in Rajasthan where hard rock strata, expansive soils (kota stone, black cotton soil zones), and unexpected groundwater can severely impact earthwork productivity and foundation design.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-GEO-01 | Unexpected Rock Formation in Cut Sections | 3 / 5 | 4 / 5 | ₹50 Lakhs – 2 Cr | 20–45 days | HIGH | Construction |
| RK-GEO-02 | Black Cotton / Expansive Soil Subgrade | 3 / 5 | 3 / 5 | ₹20–60 Lakhs | 10–30 days | MEDIUM | Construction |
| RK-GEO-03 | Groundwater Ingress in Embankment / Foundation Zone | 2 / 5 | 4 / 5 | ₹30–90 Lakhs | 15–40 days | HIGH | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Avoid | Commission comprehensive sub-surface investigation at 500m intervals before finalization of design. Use seismic refraction surveys in suspected rock zones. | Design Consultant / PMC | Pre-Construction |
| Mitigate | Provide for rock excavation BOQ with blasting permits pre-arranged with district mining office. Stockpile lime/fly ash for soil stabilization. | EPC Contractor | Month 2–6 |
| Mitigate | Provide French drains, interceptor drains, and blanket drainage layers in high water table zones. Maintain groundwater level monitoring wells. | EPC Site Engineer | Ongoing |
| Transfer | Invoke price escalation provisions for excess rock exceeding threshold quantities defined in BOQ. | Contracts Manager | On Trigger |

Early Warning Indicators:

- GI borehole data showing rock at less than 1.5m depth

- Field CBR below 2% in subgrade zone

- Groundwater level less than 2m below FGL in embankment zone

## 4.3 Monsoon & Adverse Weather Risks

The NH-48 Rajasthan corridor is subject to Southwest monsoon from July to September. Flash floods and desert weather extremes (dust storms, extreme heat) can suspend critical activities including earthwork, bituminous paving, and bridge concreting.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-MW-01 | Monsoon Flooding of Work Sites / Embankments | 4 / 5 | 4 / 5 | ₹40–80 Lakhs | 21–45 days | HIGH | Construction |
| RK-MW-02 | Extreme Heat (>45°C) Suspending Bituminous Paving | 3 / 5 | 3 / 5 | ₹10–25 Lakhs | 10–20 days | MEDIUM | Construction |
| RK-MW-03 | Dust Storms (Andhi) Disrupting Operations | 3 / 5 | 2 / 5 | ₹5–15 Lakhs | 3–7 days | LOW | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Avoid | Schedule all earthwork and embankment filling to be completed by end of June. Maintain monsoon-free work schedule for critical earthwork. | Planning Engineer | Month 1–5 |
| Mitigate | Pre-position dewatering pumps (minimum 2 per active work front). Construct temporary berms and silt traps. Engage IMD 5-day weather advisory service. | Site Manager | Pre-Monsoon |
| Mitigate | Shift bituminous paving to early morning operations (4 AM to 9 AM) during summer months to maintain mat temperature. Use high-viscosity VG-40 grade bitumen. | QC Engineer | April–June |
| Accept | Maintain weather log and claim Force Majeure EOT provisions under contract for rainfall exceeding recorded 10-year average. | Contracts Manager | On Trigger |

Early Warning Indicators:

- IMD orange/red rainfall alert for project district

- River gauge at upstream bridge crossing exceeding 60% of HFL

- Temperature forecast exceeding 44°C for 3+ consecutive days

## 4.4 Material Availability & Price Escalation Risks

Road construction is highly material-intensive. Volatility in bitumen, steel, cement, and aggregates — driven by global commodity cycles, GST amendments, OPEC decisions, and logistics disruptions — can severely impact project viability and contractor margins.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-MAT-01 | Bitumen Price Escalation / Shortage | 3 / 5 | 4 / 5 | ₹80 Lakhs – 2.5 Cr | 5–15 days | HIGH | Construction |
| RK-MAT-02 | Steel / Reinforcement Non-Availability for Bridges | 2 / 5 | 4 / 5 | ₹60 Lakhs – 1.5 Cr | 10–30 days | HIGH | Construction |
| RK-MAT-03 | Quarry Closure / Aggregate Shortage | 3 / 5 | 3 / 5 | ₹30–70 Lakhs | 15–25 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Mitigate | Procure bitumen on quarterly forward contracts from IOC/HPCL with contractual price lock. Maintain minimum 30-day buffer stock. | Procurement Manager | Month 1 onwards |
| Transfer | Invoke NHAI price escalation formula (MOSRT&H circular) for bitumen and steel exceeding 5% base price variation. | Contracts Manager | Per billing cycle |
| Avoid | Identify at least 2 approved quarry sources per material category. Obtain advance approval from PMC for all material sources. | QC Manager | Pre-Construction |
| Mitigate | Utilize recycled asphalt pavement (RAP) up to 20% in bituminous base course where DPR permits. Explore pre-qualification of secondary aggregates. | Design / QC | On Trigger |

Early Warning Indicators:

- Bitumen price variance greater than 8% MoM on IOC schedule

- Any quarry receiving show-cause or closure notice from district mining authority

- National steel price index exceeding 10% above base month

## 4.5 Labour & Equipment Risks

Availability of skilled and unskilled labour — particularly in remote NH corridors — and equipment reliability are critical to maintaining productivity targets. Labour law compliance, migrant worker welfare, and equipment breakdown management are key sub-risks.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-LAB-01 | Labour Shortage / Seasonal Migration | 3 / 5 | 3 / 5 | ₹20–50 Lakhs | 15–30 days | MEDIUM | Construction |
| RK-LAB-02 | Labour Unrest / Strike | 2 / 5 | 4 / 5 | ₹40–1.2 Cr | 5–30 days | HIGH | Construction |
| RK-LAB-03 | Critical Equipment Breakdown (Motor Grader, Paver, Roller) | 3 / 5 | 3 / 5 | ₹15–40 Lakhs | 5–15 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Mitigate | Engage minimum 2 registered labour contractors from Rajasthan, UP, and Odisha. Provide dignified camp facilities, ESIC/PF coverage, and contract wage transparency. | HR / Admin Manager | Month 1 |
| Avoid | Implement Grievance Redressal Mechanism with 24-hour hotline. Conduct fortnightly labour welfare meetings. Ensure timely wage disbursement via DBT. | Labour Welfare Officer | Ongoing |
| Mitigate | Maintain AMC agreements with OEM for all critical equipment. Pre-position minimum 15% spare critical components (slat conveyor, vibration drum bearings). Identify and empanel 2 local equipment hire agencies. | Plant & Machinery Manager | Month 1 onwards |
| Transfer | Obtain Contractors' All Risk (CAR) insurance and Equipment Breakdown insurance for all plant above Rs. 25 Lakhs in value. | Finance / Insurance | Pre-Mobilization |

Early Warning Indicators:

- Daily labour attendance below 75% of planned deployment for 3 consecutive days

- Any written complaint submitted to Labour Commissioner

- Equipment utilization rate below 60% for critical plant

## 4.6 Environmental & Forest Clearance Risks

Projects traversing or adjoining forest/wildlife zones in Rajasthan require Stage-I and Stage-II Forest Clearance under the Forest Conservation Act 1980. Non-compliance with EMP conditions, wildlife crossings, or tree felling orders can trigger work stoppage orders and litigation.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-ENV-01 | Delay in Forest / Wildlife Clearance | 3 / 5 | 5 / 5 | ₹1–3 Cr | 90–180 days | CRITICAL | Construction |
| RK-ENV-02 | Non-Compliance with EMP / ESMP Conditions | 2 / 5 | 4 / 5 | ₹30–80 Lakhs | 15–30 days | HIGH | Construction |
| RK-ENV-03 | Discovery of Archaeological / Heritage Assets in Excavation | 1 / 5 | 5 / 5 | ₹50 Lakhs – 2 Cr | 30–180 days | HIGH | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Avoid | Initiate forest diversion proposals and wildlife NOC applications minimum 24 months before project mobilization. Engage MoEFCC-empanelled consultant for EIA. | NHAI / PMC Environment | Pre-Award |
| Mitigate | Establish Environment & Social Management Unit on site with dedicated Environment Officer. Conduct monthly EMP compliance audits and submit quarterly DEIAA reports. | Environment Officer | Ongoing |
| Mitigate | Conduct preliminary archaeological survey along alignment in collaboration with ASI. Include contingency clause in construction schedule for heritage zone encounters. | PMC / Design | Pre-Construction |
| Transfer | Forest clearance condition remains NHAI's responsibility under EPC contract. Claim EOT and additional costs for delays attributable to NHAI obligations. | Contracts Manager | On Trigger |

Early Warning Indicators:

- Any green bench petition filed against the project in NGT

- MoEFCC inspection notice received

- Tree felling more than 15 days behind schedule

## 4.7 Financial & Contractor Default Risks

Contractor financial distress — arising from delayed payments, inadequate working capital, or over-leveraged balance sheets — can cause project abandonment, quality compromise, and subcontractor cascading failures. This is increasingly prevalent in large NH EPC contracts in India.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-FIN-01 | Contractor Cash Flow Stress / Delayed NHAI Payments | 3 / 5 | 4 / 5 | ₹2–8 Cr | 30–90 days | HIGH | Construction |
| RK-FIN-02 | Contractor Financial Default / Insolvency | 2 / 5 | 5 / 5 | ₹15–50 Cr | 180+ days | CRITICAL | Construction |
| RK-FIN-03 | Subcontractor Payment Default / Walk-Off | 3 / 5 | 3 / 5 | ₹50 Lakhs – 2 Cr | 15–45 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Mitigate | Ensure NHAI processes IPC within 28 days per contract. Implement e-measurement and e-billing to reduce payment cycle time. Maintain 3-month working capital reserve. | Finance / Contracts | Ongoing |
| Transfer | Obtain Performance Bank Guarantee of 10% contract value from scheduled bank. Include step-in rights and direct payment to critical subcontractors in contract. | NHAI Legal | Pre-Award |
| Avoid | Conduct rigorous financial due diligence at bid evaluation stage. Verify order-book-to-net-worth ratio and current ratio of shortlisted bidders. | NHAI / MEA | Pre-Award |
| Contingency | Activate termination for convenience clause. Invoke PBG. Fast-track retendering with 6-month interim management by PMC team. | NHAI PD / Legal | On Trigger |

Early Warning Indicators:

- IPC payment pending beyond 35 days

- Contractor submitting MIS with less than 30-day working capital

- More than 2 subcontractors filing payment claims

## 4.8 Design Change & Scope Creep Risks

Mid-project design changes driven by IRC standard revisions, NH classification upgrades, or utility discovery are a major source of variation orders (VOs) and time overruns in NHAI projects.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-DES-01 | Change in Geometric Design Standards (IRC Update) | 2 / 5 | 3 / 5 | ₹30–80 Lakhs | 15–30 days | MEDIUM | Construction |
| RK-DES-02 | Grade Separator / Flyover Addition by NHAI | 2 / 5 | 4 / 5 | ₹5–20 Cr | 60–180 days | HIGH | Construction |
| RK-DES-03 | Pavement Design Revision due to Traffic Data Update | 2 / 5 | 3 / 5 | ₹1–5 Cr | 20–45 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Avoid | Freeze design at approved DPR stage with formal NHAI concurrence. Establish Change Control Board (CCB) for any mid-project design change requests. | PMC Design Lead | Month 1 |
| Transfer | Price all NHAI-directed scope additions as Variation Orders per contract. Ensure VO approvals precede execution to protect cash flow. | Contracts Manager | On Trigger |
| Mitigate | Incorporate design contingency in baseline schedule (10% float for design-related activities). Maintain digital As-Built model updated monthly. | Planning Engineer | Ongoing |

Early Warning Indicators:

- Any IRC or MOSRT&H circular received during project execution

- NHAI DGM requesting feasibility study for new structure mid-project

- Traffic count data showing greater than 20% variance from DPR assumptions

## 4.9 Safety, Health & Environment (HSE) Risks

Road construction is among the highest-risk industrial activities in India. Fatal accidents, occupational health hazards (silica dust, heat stress), and third-party accident liability during construction are key HSE risks with significant legal, reputational, and schedule consequences.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-HSE-01 | Fatal Construction Accident | 2 / 5 | 5 / 5 | ₹50 Lakhs – 2 Cr (legal, compensation) | 15–60 days (work stoppage) | CRITICAL | Construction |
| RK-HSE-02 | Third-Party Road Accident in Work Zone | 3 / 5 | 4 / 5 | ₹20–80 Lakhs | 5–15 days | HIGH | Construction |
| RK-HSE-03 | Hazardous Material Spill (Bitumen, Fuel) | 2 / 5 | 3 / 5 | ₹10–30 Lakhs | 3–7 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Mitigate | Implement ISO 45001 OHSMS with daily toolbox talks, PPE enforcement, and monthly third-party HSE audits. Deploy dedicated HSE Officer per 5 km active stretch. | HSE Manager | Ongoing |
| Avoid | Install IRC:SP:55 compliant traffic management plan at all active work zones. Deploy solar-powered variable message signs (VMS), barricades, and trained traffic marshals. | Traffic & Safety Eng. | Before Commencement |
| Transfer | Maintain Workmen's Compensation Policy (WCP) and Third-Party Liability Policy with sum insured appropriate to project size. Register all workers under ESIC. | HR / Insurance | Day 1 |
| Contingency | Maintain 24x7 First Aid Room with qualified nurse on site. Pre-tie empanelment agreements with nearest district hospital and trauma centre. | Site Medical Officer | Pre-Mobilization |

Early Warning Indicators:

- Any near-miss event reported

- HSE audit non-conformance greater than 5 per month

- Traffic incident rate exceeding 1 per month in work zone

## 4.10 Law & Order / Third-Party Risks

Road construction projects in politically sensitive corridors can attract protests, blockades, and court injunctions. Local community opposition, inter-district boundary disputes, and contractor-subcontractor disputes can cause prolonged work stoppage.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-LO-01 | Community Agitation / Dharna Against Land Acquisition | 3 / 5 | 4 / 5 | ₹30–1.5 Cr | 15–60 days | HIGH | Construction |
| RK-LO-02 | Court Injunction / NGT Stay Order | 2 / 5 | 5 / 5 | ₹1–5 Cr | 60–365 days | CRITICAL | Construction |
| RK-LO-03 | Contractor-Subcontractor Dispute / Arbitration | 2 / 5 | 3 / 5 | ₹50 Lakhs – 1.5 Cr | 30–90 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Avoid | Establish Community Liaison Unit with local representative as point of contact. Conduct community engagement meetings before commencement in each village / town panchayat. | Social Officer / PMC | Pre-Construction |
| Mitigate | Retain NHAI's empanelled legal counsel for pre-emptive legal monitoring. Respond to all RTI queries within 30 days. Maintain documentation of LA compliance. | NHAI Legal | Ongoing |
| Transfer | Court cases and LA litigation are NHAI's risk — contractor to claim EOT for delays due to judicial orders. | Contracts Manager | On Trigger |
| Mitigate | Include Dispute Adjudication Board (DAB) mechanism in subcontracts. Resolve subcontractor disputes within 21 days of formal notice. | Project Director | On Trigger |

Early Warning Indicators:

- Local newspaper reports of community opposition

- Any PIL or RTI received referencing the project

- Formal legal notice from any affected party

## 4.11 Force Majeure Risks

Force Majeure events — including war, earthquake, terrorist activity, and epidemic/pandemic — are typically excluded from contractor liability under NHAI EPC contract Clause 19. However, they require formal declaration, documentation, and insurance claim processes to be managed effectively.

Risk Register

| Risk ID | Risk Title | Probability | Impact | Cost Impact | Schedule Impact | Rating | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RK-FM-01 | Earthquake / Natural Disaster | 1 / 5 | 5 / 5 | ₹5–50 Cr | 30–365 days | HIGH | Construction |
| RK-FM-02 | Epidemic / Pandemic (COVID-type Event) | 1 / 5 | 5 / 5 | ₹2–15 Cr | 30–180 days | HIGH | Construction |
| RK-FM-03 | National Emergency / War / Civil Unrest | 1 / 5 | 4 / 5 | ₹1–8 Cr | 15–90 days | MEDIUM | Construction |

Mitigation Plan

| Strategy | Mitigation Action | Responsible Owner | Timeline |
| --- | --- | --- | --- |
| Accept | Issue formal Force Majeure notice to NHAI within 14 days of triggering event per Clause 19.2. Maintain independent damage assessment log. | Project Director | On Trigger |
| Transfer | Invoke CAR (Contractors' All Risk) insurance claim for material damage. Claim additional time under Clause 40 (Extension of Time) with supporting documentation. | Finance / Insurance | On Trigger |
| Mitigate | Maintain emergency response plan including evacuation procedures, emergency contact directory, and coordination protocol with NDRF, SDRF, and District Disaster Management Authority. | HSE / Site Manager | Pre-Mobilization |

Early Warning Indicators:

- District Disaster Management Authority issuing advisory

- IMD cyclone/flood watch for project region

- National health authority declaring disease outbreak in project state

# 5. Consolidated Risk Register Summary

The table below provides a consolidated view of all top-priority risks across categories, their current status, and ownership. This serves as the executive dashboard for weekly risk review meetings.

| Risk ID | Risk Title | Category | Rating | Risk Owner | Status |
| --- | --- | --- | --- | --- | --- |
| RK-LA-01 | Delayed ROW Handover | Land Acquisition | CRITICAL | NHAI PD | Open |
| RK-LA-03 | Utility Conflict (OFC/Pipeline) | Land Acquisition | HIGH | NHAI AE | Monitoring |
| RK-GEO-01 | Unexpected Rock Formation | Geotechnical | HIGH | EPC Contractor | Open |
| RK-MW-01 | Monsoon Site Flooding | Weather | HIGH | Site Manager | Monitoring |
| RK-MAT-01 | Bitumen Price Escalation | Materials | HIGH | Procurement Mgr. | Open |
| RK-LAB-02 | Labour Unrest / Strike | Labour | HIGH | HR Manager | Monitoring |
| RK-ENV-01 | Forest Clearance Delay | Environmental | CRITICAL | NHAI/PMC Env. | Open |
| RK-FIN-02 | Contractor Default | Financial | CRITICAL | NHAI PD | Monitoring |
| RK-HSE-01 | Fatal Construction Accident | HSE | CRITICAL | HSE Manager | Open |
| RK-LO-02 | Court Injunction / Stay Order | Legal | CRITICAL | NHAI Legal | Monitoring |
| RK-DES-02 | Mid-Project Grade Separator Addition | Design | HIGH | PMC Design | Open |
| RK-FM-01 | Earthquake / Natural Disaster | Force Majeure | HIGH | Project Director | Monitoring |

# 6. Risk Governance & Review Protocol

## 6.1 Risk Management Roles & Responsibilities

| Role | Responsibility | Reporting Frequency |
| --- | --- | --- |
| NHAI Project Director | Overall risk ownership; approval of Critical/High rated risks; contract actions | Weekly to NHAI RO |
| PMC Risk Manager | Risk identification, scoring, register maintenance, early warning monitoring | Weekly to NHAI PD |
| EPC Project Manager | Implementation of mitigation actions; reporting realized risks; escalation | Daily site log; weekly risk update |
| Site Engineers / Package Heads | First-level risk identification; early warning observation; contingency activation | Daily to EPC PM |
| Legal / Finance / Insurance | Contract risk mitigation; insurance claims; financial risk monitoring | Monthly; on trigger |

## 6.2 Risk Review Meeting Schedule

| Meeting Type | Frequency | Participants | Output |
| --- | --- | --- | --- |
| Site Risk Huddle | Daily | Site Eng., HSE, PMC | Early warning log |
| Weekly Risk Review | Every Monday | PMC, EPC PM, NHAI PD | Updated risk register |
| Monthly Risk Committee | Last Friday of month | All stakeholders | Escalation decisions |
| Quarterly Risk Audit | Every 3 months | Independent PMC + NHAI | Audit report to HQ |

## 6.3 Risk Escalation Threshold

Any risk whose score increases by 3 or more points between review cycles must be immediately escalated to the next authority level. Any risk newly rated as Critical must be reported to NHAI Headquarters within 48 hours with a mitigation action plan.

## 6.4 Risk Register Maintenance

The Risk Master Register shall be maintained as a live digital document in the Project Management Information System (PMIS). Version control is mandatory — each approved update increments the version number. Archived versions are retained for the life of the project plus 10 years per NHAI document retention policy.

# 7. Glossary of Terms

| Abbreviation | Full Form |
| --- | --- |
| BOQ | Bill of Quantities |
| CAR | Contractors' All Risk (Insurance Policy) |
| CCB | Change Control Board |
| DAB | Dispute Adjudication Board |
| DBT | Direct Benefit Transfer |
| DLP | Defects Liability Period |
| DPR | Detailed Project Report |
| EMP | Environmental Management Plan |
| EOT | Extension of Time |
| EPC | Engineering, Procurement & Construction |
| ESIC | Employees' State Insurance Corporation |
| FGL | Finished Ground Level |
| HFL | Highest Flood Level |
| IMD | India Meteorological Department |
| IPC | Interim Payment Certificate |
| IRC | Indian Roads Congress |
| MoEFCC | Ministry of Environment, Forest & Climate Change |
| MOSRT&H | Ministry of Road Transport and Highways |
| NDRF | National Disaster Response Force |
| NGT | National Green Tribunal |
| NHAI | National Highways Authority of India |
| OFC | Optical Fibre Cable |
| OHSMS | Occupational Health & Safety Management System |
| PBG | Performance Bank Guarantee |
| PMC | Project Management Consultant |
| PMIS | Project Management Information System |
| RAP | Recycled Asphalt Pavement |
| RFCTLARR | Right to Fair Compensation and Transparency in Land Acquisition, Rehabilitation and Resettlement Act, 2013 |
| ROW | Right of Way |
| VMS | Variable Message Sign |
| VO | Variation Order |
| WBS | Work Breakdown Structure |
| WCP | Workmen's Compensation Policy |